## Summary
Hours summary by resource
All figures are formulas: tasks roll up to activities, activities roll up here.
Hours by role and phase
Code | Role | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total hours | Person-weeks
PM | Program / Project Manager | 454 | 434 | 444 | 402 | 1734 | 43.35
CA | Cloud / Platform Architect | 306 | 48 | 153 | 185 | 692 | 17.3
DO | Platform / DevOps Engineer | 917 | 334 | 581 | 817 | 2649 | 66.225
SE | Security Engineer | 414 | 96 | 273 | 244 | 1027 | 25.675
AIA | AI Architect | 131 | 511 | 521 | 195 | 1358 | 33.95
AIE | AI / ML Engineer | 0 | 2024 | 2581 | 1143 | 5748 | 143.7
DE | Data Engineer | 162 | 1227 | 885 | 661 | 2935 | 73.375
DG | Data Architect / Governance | 346 | 170 | 37 | 201 | 754 | 18.85
DEV | Full-stack Developer | 0 | 319 | 1306 | 406 | 2031 | 50.775
BA | Business Analyst / Product Owner | 491 | 493 | 795 | 446 | 2225 | 55.625
QA | QA / Test Engineer | 76 | 712 | 983 | 488 | 2259 | 56.475
CM | Change & Training Lead | 16 | 97 | 222 | 253 | 588 | 14.7
| Total | 3313 | 6465 | 8781 | 5441 | 24000 | 600
Hours by role and track
Code | Role | AI Platform Setup | AI Data Readiness | AI Use Cases | Program Management | Total hours
PM | Program / Project Manager | 8 | 16 | 246 | 1464 | 1734
CA | Cloud / Platform Architect | 467 | 113 | 16 | 96 | 692
DO | Platform / DevOps Engineer | 1917 | 470 | 262 | 0 | 2649
SE | Security Engineer | 641 | 199 | 187 | 0 | 1027
AIA | AI Architect | 499 | 212 | 551 | 96 | 1358
AIE | AI / ML Engineer | 1739 | 1114 | 2895 | 0 | 5748
DE | Data Engineer | 93 | 2071 | 771 | 0 | 2935
DG | Data Architect / Governance | 0 | 738 | 16 | 0 | 754
DEV | Full-stack Developer | 732 | 0 | 1299 | 0 | 2031
BA | Business Analyst / Product Owner | 174 | 510 | 1541 | 0 | 2225
QA | QA / Test Engineer | 739 | 505 | 1015 | 0 | 2259
CM | Change & Training Lead | 8 | 114 | 466 | 0 | 588
| Total | 7017 | 6062 | 9265 | 1656 | 24000
Hours by role and owner team
Code | Role | Platform Engineering | Foundry | AI Data Lake | Factory | All teams | Total hours
PM | Program / Project Manager | 8 | 0 | 16 | 246 | 1464 | 1734
CA | Cloud / Platform Architect | 543 | 0 | 53 | 0 | 96 | 692
DO | Platform / DevOps Engineer | 1878 | 358 | 224 | 189 | 0 | 2649
SE | Security Engineer | 688 | 153 | 76 | 110 | 0 | 1027
AIA | AI Architect | 0 | 887 | 0 | 375 | 96 | 1358
AIE | AI / ML Engineer | 209 | 2969 | 32 | 2538 | 0 | 5748
DE | Data Engineer | 105 | 415 | 1644 | 771 | 0 | 2935
DG | Data Architect / Governance | 0 | 0 | 723 | 31 | 0 | 754
DEV | Full-stack Developer | 537 | 348 | 0 | 1146 | 0 | 2031
BA | Business Analyst / Product Owner | 69 | 161 | 338 | 1657 | 0 | 2225
QA | QA / Test Engineer | 440 | 653 | 192 | 974 | 0 | 2259
CM | Change & Training Lead | 0 | 8 | 114 | 466 | 0 | 588
| Total | 4477 | 5952 | 3412 | 8503 | 1656 | 24000

## Estimate Overview
Estimate overview: 24,000 hours
All figures are live formulas over the Task Breakdown sheet.
Track | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total hours | % of total
AI Platform Setup | 1432 | 1792 | 2152 | 1641 | 7017 | 29.24%
AI Data Readiness | 858 | 2128 | 1945 | 1131 | 6062 | 25.26%
AI Use Cases | 609 | 2131 | 4270 | 2255 | 9265 | 38.6%
Program Management | 414 | 414 | 414 | 414 | 1656 | 6.9%
Total | 3313 | 6465 | 8781 | 5441 | 24000 | 100%
Target hours | 24000
Planned minus target | 0 | On target
Role mix check
Role | Hours | % of total | Typical range for AI programs | Comment
PM – Program / Project Manager | 1734 | 7.225% | 6–10% | Program across 3 teams and many plants
CA – Cloud / Platform Architect | 692 | 2.883% | 2–4% | Architecture front-loaded in Phase 1
DO – Platform / DevOps Engineer | 2649 | 11.04% | 8–12% | Landing zone, IaC, DR, plant gateways
SE – Security Engineer | 1027 | 4.279% | 4–7% | Identity, OT security, pen test, SOX controls
AIA – AI Architect | 1358 | 5.658% | 4–6% | Design authority for agents and RAG
AIE – AI / ML Engineer | 5748 | 23.95% | 18–25% | Largest role: agents, RAG, gateway, evaluation
DE – Data Engineer | 2935 | 12.23% | 10–15% | SAP, MES, PI pipelines and plant onboarding
DG – Data Architect / Governance | 754 | 3.142% | 2–4% | Classification, catalog, lineage
DEV – Full-stack Developer | 2031 | 8.463% | 7–10% | Teams app, web, mobile, admin panel
BA – Business Analyst / Product Owner | 2225 | 9.271% | 8–12% | Requirements, KPIs, golden test sets
QA – QA / Test Engineer | 2259 | 9.412% | 9–13% | Testing inside every item
CM – Change & Training Lead | 588 | 2.45% | 2–4% | Training and adoption across plants

## Phase 1
Phase 1: tasks and hours for each item (Foundation / Assess / Discover)
Bold rows are the slide items; the rows beneath are their implementation tasks (green = linked to Task Breakdown).
ID | Item / task | Owner team | Deliverable | PM | CA | DO | SE | AIA | AIE | DE | DG | DEV | BA | QA | CM | Total hours | % of phase
AI Platform Setup: Foundation
PS-1.01 | Azure landing zone, subscriptions, VNets, private endpoints | Platform Engineering | Landing zone deployed | 0 | 77 | 197 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 334 | 10.08%
PS-1.01.01 | Define management-group and subscription hierarchy (prod, non-prod, sandbox) |  |  | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.4528%
PS-1.01.02 | Design hub-and-spoke network, IP address plan and DNS |  |  | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.9055%
PS-1.01.03 | Deploy hub VNet, Azure Firewall and spoke VNets |  |  | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1.238%
PS-1.01.04 | Set up ExpressRoute / VPN to Ball data centers and plants |  |  | 0 | 10 | 31 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1.388%
PS-1.01.05 | Configure private endpoints and private DNS zones for PaaS services |  |  | 0 | 0 | 41 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1.539%
PS-1.01.06 | Apply Azure Policy baseline (allowed regions, tagging, no public IPs) |  |  | 0 | 5 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.207%
PS-1.01.07 | Enable Defender for Cloud and diagnostic settings |  |  | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
PS-1.01.08 | Validate connectivity and policy compliance |  |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 30 | 0.9055%
PS-1.01.09 | Detailed design and design review |  |  | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0.5131%
PS-1.01.10 | Promote through dev / test / prod and release |  |  | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0.332%
PS-1.01.11 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0.332%
PS-1.01.12 | Defect fixing and rework after testing |  |  | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0.6641%
PS-1.02 | Entra ID SSO, MFA / PIM, conditional access | Platform Engineering | Identity and access configuration | 0 | 24 | 16 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 145 | 4.377%
PS-1.02.01 | Register enterprise apps and app registrations for platform services |  |  | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
PS-1.02.02 | Configure SSO (OIDC / SAML) for web, mobile and Teams clients |  |  | 0 | 0 | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0.8452%
PS-1.02.03 | Enforce MFA and create conditional access policies (device, location, risk) |  |  | 0 | 8 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0.8452%
PS-1.02.04 | Set up PIM for privileged roles with approval and time limits |  |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.4829%
PS-1.02.05 | Create managed identities for services and agents |  |  | 0 | 8 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
PS-1.02.06 | Test sign-in flows and break-glass accounts |  |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 20 | 0.6037%
PS-1.02.07 | Detailed design and design review |  |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.2415%
PS-1.02.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.1509%
PS-1.03 | RBAC / ABAC roles and fine-grained permissions | Platform Engineering | Role and permission matrix | 0 | 27 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 133 | 4.014%
PS-1.03.01 | Gather personas and access needs (plant ops, engineers, analysts, admins) |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 30 | 0.9055%
PS-1.03.02 | Design role model and permission matrix (RBAC + ABAC attributes: plant, region, function) |  |  | 0 | 15 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1.238%
PS-1.03.03 | Create Entra security groups and custom Azure roles |  |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
PS-1.03.04 | Map agent and tool permissions to roles |  |  | 0 | 5 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
PS-1.03.05 | Document access request and periodic access review process |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.3018%
PS-1.03.06 | Detailed design and design review |  |  | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.2113%
PS-1.03.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.1509%
PS-1.04 | Key Vault, TDE / TLS encryption | Platform Engineering | Key and secret management in place | 0 | 5 | 32 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 2.656%
PS-1.04.01 | Deploy Key Vaults per environment with private endpoints |  |  | 0 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.4829%
PS-1.04.02 | Define secret, key and certificate naming and rotation policy |  |  | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.3622%
PS-1.04.03 | Enable TDE with customer-managed keys on SQL, PostgreSQL and Storage |  |  | 0 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.7244%
PS-1.04.04 | Enforce TLS 1.2+ and manage certificates for custom domains |  |  | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.4829%
PS-1.04.05 | Configure vault RBAC and audit logging |  |  | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.3622%
PS-1.04.06 | Detailed design and design review |  |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.1509%
PS-1.04.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.09055%
PS-1.05 | Front Door + API Management gateway | Platform Engineering | APIM instance with policies | 0 | 40 | 131 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 211 | 6.369%
PS-1.05.01 | Design gateway topology (Front Door to APIM to backends) |  |  | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
PS-1.05.02 | Deploy Front Door with WAF policy |  |  | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.9055%
PS-1.05.03 | Deploy APIM in internal VNet mode with custom domains |  |  | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.9357%
PS-1.05.04 | Configure products, subscriptions and JWT validation policy |  |  | 0 | 0 | 26 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.087%
PS-1.05.05 | Configure rate limiting, quotas, routing and request validation policies |  |  | 0 | 10 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.087%
PS-1.05.06 | Test routing, throttling and authentication failure paths |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0.6037%
PS-1.05.07 | Detailed design and design review |  |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.3018%
PS-1.05.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.2113%
PS-1.05.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.2113%
PS-1.05.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0.4226%
PS-1.06 | Terraform / Bicep IaC, GitHub Actions CI/CD | Platform Engineering | IaC modules and pipelines | 0 | 35 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 299 | 9.025%
PS-1.06.01 | Choose IaC standard, repository structure and module conventions |  |  | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.7546%
PS-1.06.02 | Set up remote state, environments and workload identity for pipelines |  |  | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0.7848%
PS-1.06.03 | Build reusable modules: network, storage, Key Vault, APIM, AKS, AI services |  |  | 0 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 2.445%
PS-1.06.04 | Build GitHub Actions pipelines: plan, approval gates, apply |  |  | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1.238%
PS-1.06.05 | Add policy-as-code and security scanning (tfsec / Checkov) |  |  | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.7546%
PS-1.06.06 | Build application CI/CD templates (build, test, container push, deploy) |  |  | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0.7848%
PS-1.06.07 | Test pipelines end to end in non-prod |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0.6037%
PS-1.06.08 | Detailed design and design review |  |  | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.4528%
PS-1.06.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.3018%
PS-1.06.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.3018%
PS-1.06.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
PS-1.07 | ACR, AKS and Container Apps | Platform Engineering | Container hosting platform | 0 | 31 | 171 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 6.701%
PS-1.07.01 | Decide hosting model per workload (AKS, Container Apps, Functions) |  |  | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.4528%
PS-1.07.02 | Deploy Azure Container Registry with private endpoint and image scanning |  |  | 0 | 0 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
PS-1.07.03 | Deploy AKS cluster: node pools, autoscaling, workload identity |  |  | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1.539%
PS-1.07.04 | Install ingress controller, cert-manager and Key Vault CSI driver |  |  | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0.7848%
PS-1.07.05 | Deploy Container Apps environment inside the VNet |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
PS-1.07.06 | Apply pod security, network policies and Defender for Containers |  |  | 0 | 0 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.7546%
PS-1.07.07 | Set up GPU node pool for self-hosted models |  |  | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.7546%
PS-1.07.08 | Detailed design and design review |  |  | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0.332%
PS-1.07.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.2113%
PS-1.07.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.2113%
PS-1.07.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.4528%
| Subtotal: AI Platform Setup |  |  | 0 | 239 | 791 | 306 | 0 | 0 | 0 | 0 | 0 | 20 | 76 | 0 | 1432 | 43.22%
AI Data Readiness: Assess
DR-1.01 | Inventory sources: SAP S/4HANA, MES, AVEVA PI, SharePoint, Coupa | AI Data Lake | Source system inventory | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 87 | 0 | 82 | 0 | 0 | 218 | 6.58%
DR-1.01.01 | Run workshops with SAP, MES, AVEVA PI, SharePoint and Coupa owners |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 49 | 0 | 0 | 74 | 2.234%
DR-1.01.02 | Document systems, tables, volumes, refresh rates and access methods |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 25 | 0 | 0 | 0 | 0 | 62 | 1.871%
DR-1.01.03 | Identify document repositories (specs, SOPs, quality records) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 25 | 0 | 0 | 37 | 1.117%
DR-1.01.04 | Build the data source register |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 25 | 0.7546%
DR-1.01.05 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0.3622%
DR-1.01.06 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0.2415%
DR-1.02 | Classify data and tag PII | AI Data Lake | Data classification and PII tags | 0 | 0 | 0 | 40 | 0 | 0 | 20 | 96 | 0 | 0 | 0 | 0 | 156 | 4.709%
DR-1.02.01 | Define classification scheme (public, internal, confidential, restricted) |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 30 | 0.9055%
DR-1.02.02 | Run Purview automated classification scans |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 30 | 0.9055%
DR-1.02.03 | Review results and tag PII / sensitive columns |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 31 | 0 | 0 | 0 | 0 | 41 | 1.238%
DR-1.02.04 | Define handling rules per class for AI use |  |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 30 | 0.9055%
DR-1.02.05 | Apply sensitivity labels to documents |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.3018%
DR-1.02.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 0.2717%
DR-1.02.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0.1811%
DR-1.03 | Name data owners and stewards | AI Data Lake | Data ownership RACI | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 27 | 0 | 16 | 88 | 2.656%
DR-1.03.01 | Identify owners per domain (production, quality, supply, finance) |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 20 | 0.6037%
DR-1.03.02 | Define steward responsibilities and RACI |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 16 | 0.4829%
DR-1.03.03 | Kick-off and training for stewards |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 16 | 24 | 0.7244%
DR-1.03.04 | Ownership sign-off |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 20 | 0.6037%
DR-1.03.05 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0.1509%
DR-1.03.06 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0.09055%
DR-1.04 | ADLS Gen2 / Blob storage tiers | Platform Engineering | Storage accounts and lifecycle rules | 0 | 21 | 61 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 2.958%
DR-1.04.01 | Design zones (raw, curated, serving) and container layout |  |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.3622%
DR-1.04.02 | Deploy ADLS Gen2 with hierarchical namespace and private endpoints |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
DR-1.04.03 | Configure lifecycle tiers (hot, cool, archive) |  |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.3622%
DR-1.04.04 | Set ACLs aligned to the role model |  |  | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
DR-1.04.05 | Enable soft delete and versioning |  |  | 0 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.4829%
DR-1.04.06 | Detailed design and design review |  |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.1509%
DR-1.04.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.09055%
DR-1.04.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.09055%
DR-1.04.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.2113%
DR-1.05 | Azure SQL, PostgreSQL + pgvector | Platform Engineering | Databases provisioned | 0 | 22 | 65 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 119 | 3.592%
DR-1.05.01 | Size and design databases (application metadata, vectors) |  |  | 0 | 12 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
DR-1.05.02 | Deploy Azure SQL and PostgreSQL Flexible Server |  |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.7546%
DR-1.05.03 | Enable pgvector extension and create schemas |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 0.4829%
DR-1.05.04 | Configure high availability, backups and private access |  |  | 0 | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
DR-1.05.05 | Set up schema migration tooling (Flyway / Liquibase) |  |  | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 0.4829%
DR-1.05.06 | Detailed design and design review |  |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0.1811%
DR-1.05.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.1207%
DR-1.05.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.1207%
DR-1.05.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.2415%
DR-1.06 | Catalog and lineage baseline in Purview | AI Data Lake | Purview scans and catalog | 0 | 0 | 0 | 20 | 0 | 0 | 41 | 118 | 0 | 0 | 0 | 0 | 179 | 5.403%
DR-1.06.01 | Deploy Purview Unified Catalog and register sources |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 30 | 0.9055%
DR-1.06.02 | Configure scans for SAP, SQL, ADLS and SharePoint |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 31 | 0.9357%
DR-1.06.03 | Build business glossary of manufacturing terms |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 41 | 1.238%
DR-1.06.04 | Set up catalog collections and access |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 30 | 0.9055%
DR-1.06.05 | Capture baseline lineage |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 30 | 0.9055%
DR-1.06.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | 0.3018%
DR-1.06.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 7 | 0.2113%
| Subtotal: AI Data Readiness |  |  | 16 | 43 | 126 | 76 | 0 | 0 | 142 | 330 | 0 | 109 | 0 | 16 | 858 | 25.9%
AI Use Cases: Discover
UC-1.01 | Build use-case backlog with plant and business owners | Factory | Use-case backlog | 40 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 119 | 0 | 0 | 179 | 5.403%
UC-1.01.01 | Plan and run discovery workshops at plants and functions |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 61 | 1.841%
UC-1.01.02 | Capture pain points and ideas in a standard template |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 41 | 1.238%
UC-1.01.03 | Map ideas to agent types and architecture |  |  | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.6037%
UC-1.01.04 | Consolidate the backlog |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 40 | 1.207%
UC-1.01.05 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0.3018%
UC-1.01.06 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 7 | 0.2113%
UC-1.02 | Rank by value and data readiness | Factory | Prioritized use-case list | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 58 | 0 | 0 | 106 | 3.2%
UC-1.02.01 | Define scoring (value, feasibility, data readiness, risk) |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 24 | 0.7244%
UC-1.02.02 | Score each use case |  |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 24 | 0 | 0 | 56 | 1.69%
UC-1.02.03 | Leadership prioritization session |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 0.4829%
UC-1.02.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0.1811%
UC-1.02.05 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0.1207%
UC-1.03 | Set success KPIs and baselines | Factory | KPI baseline | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 91 | 0 | 0 | 111 | 3.35%
UC-1.03.01 | Define KPIs per use case (MTTR, OEE, scrap, time saved) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 41 | 1.238%
UC-1.03.02 | Collect baseline data |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 40 | 1.207%
UC-1.03.03 | KPI sign-off with owners |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0.6037%
UC-1.03.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0.1811%
UC-1.03.05 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0.1207%
UC-1.04 | Pick pilots: Analyst agent, Spec agent | Factory | Pilot charters | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 71 | 2.143%
UC-1.04.01 | Confirm pilot plants and users |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 20 | 0.6037%
UC-1.04.02 | Write pilot charters (scope, KPIs, team, success criteria) |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 28 | 0.8452%
UC-1.04.03 | Solution outline for Analyst and Spec agents |  |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.4829%
UC-1.04.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0.1207%
UC-1.04.05 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0.09055%
UC-1.05 | Define approval rules per use case | Factory | Human approval rules | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 71 | 2.143%
UC-1.05.01 | Classify agent actions by risk (read, recommend, act) |  |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 24 | 0.7244%
UC-1.05.02 | Define approvers and thresholds |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0.4829%
UC-1.05.03 | Security and audit requirements |  |  | 0 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.7244%
UC-1.05.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0.1207%
UC-1.05.05 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0.09055%
UC-1.06 | Responsible-AI review | Foundry | Responsible-AI assessment | 0 | 0 | 0 | 16 | 39 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 71 | 2.143%
UC-1.06.01 | Complete Responsible-AI impact assessment |  |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 24 | 0.7244%
UC-1.06.02 | Privacy and security review |  |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.4829%
UC-1.06.03 | Agree mitigations and sign-off |  |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 24 | 0.7244%
UC-1.06.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.1207%
UC-1.06.05 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.09055%
| Subtotal: AI Use Cases |  |  | 72 | 0 | 0 | 32 | 107 | 0 | 20 | 16 | 0 | 362 | 0 | 0 | 609 | 18.38%
Program Management: Mobilize
PM-1.01 | Program management, planning, status and steering (added) | All teams | Plans, status reports, RAID log | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 12.5%
PM-1.01.01 | Phase plan and schedule |  |  | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 2.203%
PM-1.01.02 | Weekly status reporting and RAID log |  |  | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 3.682%
PM-1.01.03 | Steering committee preparation |  |  | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 2.203%
PM-1.01.04 | Architecture design authority reviews |  |  | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1.449%
PM-1.01.05 | Resource and vendor coordination |  |  | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 2.958%
| Subtotal: Program Management |  |  | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 12.5%
| Phase 1 total |  |  | 454 | 306 | 917 | 414 | 131 | 0 | 162 | 346 | 0 | 491 | 76 | 16 | 3313 | 100%
| Person-weeks at the hours per week set on the Resources sheet | [14 empty] | 82.825

## Phase 2
Phase 2: tasks and hours for each item (Core AI build / Prepare / Pilot)
Bold rows are the slide items; the rows beneath are their implementation tasks (green = linked to Task Breakdown).
ID | Item / task | Owner team | Deliverable | PM | CA | DO | SE | AIA | AIE | DE | DG | DEV | BA | QA | CM | Total hours | % of phase
AI Platform Setup: Core AI build
PS-2.01 | AI Foundry hub and projects | Foundry | Foundry hub, projects, connections | 0 | 0 | 37 | 16 | 40 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 2.428%
PS-2.01.01 | Design Foundry hub and project structure per domain and environment |  |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2475%
PS-2.01.02 | Deploy Foundry hub with managed VNet and private endpoints |  |  | 0 | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0.4331%
PS-2.01.03 | Create projects and connect AI Search, Storage, Key Vault, App Insights |  |  | 0 | 0 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0.495%
PS-2.01.04 | Deploy base chat and embedding models with capacity / PTU plan |  |  | 0 | 0 | 0 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.3712%
PS-2.01.05 | Set up project RBAC and developer access |  |  | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.1856%
PS-2.01.06 | Smoke-test model endpoints from the SDK |  |  | 0 | 0 | 0 | 0 | 4 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2475%
PS-2.01.07 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.1237%
PS-2.01.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.07734%
PS-2.01.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.07734%
PS-2.01.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0.1701%
PS-2.02 | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Foundry | Model router with quotas and fallbacks | 0 | 0 | 86 | 24 | 68 | 160 | 0 | 0 | 0 | 0 | 49 | 0 | 387 | 5.986%
PS-2.02.01 | Define model routing policy (task type, cost, latency, fallback) |  |  | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.4795%
PS-2.02.02 | Configure APIM AI gateway backends: Azure OpenAI, Anthropic, Gemini, self-hosted |  |  | 0 | 0 | 43 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0.9435%
PS-2.02.03 | Implement token-based rate limits and quotas per team and agent |  |  | 0 | 0 | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0.5568%
PS-2.02.04 | Implement retry and fallback across regions and models |  |  | 0 | 0 | 0 | 0 | 6 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0.6651%
PS-2.02.05 | Deploy self-hosted model (vLLM on AKS) behind the gateway |  |  | 0 | 0 | 12 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.7579%
PS-2.02.06 | Emit token metrics and log prompts / responses securely |  |  | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.3712%
PS-2.02.07 | Use managed identity for model access (no keys in apps) |  |  | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.3712%
PS-2.02.08 | Load and failover testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49 | 0.7579%
PS-2.02.09 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0.2939%
PS-2.02.10 | Promote through dev / test / prod and release |  |  | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0.2011%
PS-2.02.11 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0.2011%
PS-2.02.12 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.3867%
PS-2.03 | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Foundry | Orchestration framework and reference agent | 0 | 0 | 22 | 0 | 130 | 358 | 0 | 0 | 74 | 0 | 73 | 0 | 657 | 10.16%
PS-2.03.01 | Evaluate and select orchestration options (Foundry Agent Service, Semantic Kernel, LangGraph) |  |  | 0 | 0 | 0 | 0 | 37 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0.959%
PS-2.03.02 | Define agent design standards: tools, state, guardrails, handoff |  |  | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.4795%
PS-2.03.03 | Build orchestration service skeleton (API, sessions, state store) |  |  | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 37 | 0 | 0 | 0 | 110 | 1.701%
PS-2.03.04 | Implement tool calling and agent-to-agent handoff |  |  | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1.129%
PS-2.03.05 | Implement checkpoints, retries, timeouts and human-in-the-loop hooks |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.7579%
PS-2.03.06 | Build a reference agent end to end |  |  | 0 | 0 | 0 | 0 | 18 | 73 | 0 | 0 | 37 | 0 | 0 | 0 | 128 | 1.98%
PS-2.03.07 | Write developer guide and starter template |  |  | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.1856%
PS-2.03.08 | Integration and failure-mode testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 73 | 1.129%
PS-2.03.09 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0.495%
PS-2.03.10 | Promote through dev / test / prod and release |  |  | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0.3403%
PS-2.03.11 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0.3403%
PS-2.03.12 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0.6651%
PS-2.04 | Memory layer: working, conversation, long-term | Foundry | Memory services | 0 | 0 | 9 | 0 | 44 | 171 | 20 | 0 | 0 | 0 | 31 | 0 | 275 | 4.254%
PS-2.04.01 | Design memory types and retention (working, conversation, long-term, episodic) |  |  | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.3094%
PS-2.04.02 | Implement conversation memory store in Cosmos DB with TTL |  |  | 0 | 0 | 0 | 0 | 0 | 31 | 10 | 0 | 0 | 0 | 0 | 0 | 41 | 0.6342%
PS-2.04.03 | Implement working memory / session state in Redis |  |  | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0.4022%
PS-2.04.04 | Implement long-term semantic memory with embeddings |  |  | 0 | 0 | 0 | 0 | 0 | 41 | 10 | 0 | 0 | 0 | 0 | 0 | 51 | 0.7889%
PS-2.04.05 | Add summarization and memory pruning |  |  | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0.4022%
PS-2.04.06 | Add PII handling and per-user isolation |  |  | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.464%
PS-2.04.07 | Test recall quality and user isolation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 31 | 0.4795%
PS-2.04.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0.2166%
PS-2.04.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.1392%
PS-2.04.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.1392%
PS-2.04.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.2784%
PS-2.05 | Prompt library, templates, versioning | Foundry | Prompt repository with versioning | 0 | 0 | 4 | 0 | 6 | 76 | 0 | 0 | 0 | 16 | 16 | 0 | 118 | 1.825%
PS-2.05.01 | Define prompt template standards and metadata |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 4 | 0 | 0 | 16 | 0.2475%
PS-2.05.02 | Set up prompt repository with versioning and approvals |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.3094%
PS-2.05.03 | Build system-prompt and guardrail templates for each agent type |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 12 | 0 | 0 | 32 | 0.495%
PS-2.05.04 | Wire prompt versions into the deployment pipeline |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.1856%
PS-2.05.05 | Regression-test prompts against a sample set |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 16 | 0.2475%
PS-2.05.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0.09281%
PS-2.05.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.06187%
PS-2.05.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.06187%
PS-2.05.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.1237%
PS-2.06 | Content Safety and Prompt Shields | Foundry | Safety policies configured | 0 | 0 | 7 | 40 | 30 | 80 | 0 | 0 | 0 | 0 | 41 | 0 | 198 | 3.063%
PS-2.06.01 | Define safety policy and severity thresholds |  |  | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.3094%
PS-2.06.02 | Enable Azure AI Content Safety filters per model deployment |  |  | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.232%
PS-2.06.03 | Enable Prompt Shields for jailbreak and indirect injection |  |  | 0 | 0 | 0 | 10 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.3867%
PS-2.06.04 | Add PII detection and redaction on inputs and outputs |  |  | 0 | 0 | 0 | 10 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.464%
PS-2.06.05 | Set up blocklists and safety incident logging |  |  | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.464%
PS-2.06.06 | Red-team testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 41 | 0.6342%
PS-2.06.07 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1547%
PS-2.06.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.1083%
PS-2.06.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.1083%
PS-2.06.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0.2011%
| Subtotal: AI Platform Setup |  |  | 0 | 0 | 165 | 80 | 318 | 909 | 20 | 0 | 74 | 16 | 210 | 0 | 1792 | 27.72%
AI Data Readiness: Prepare
DR-2.01 | Pipelines from SAP, MES and file shares | AI Data Lake | Ingestion pipelines | 0 | 0 | 24 | 0 | 0 | 0 | 501 | 64 | 0 | 57 | 86 | 0 | 732 | 11.32%
DR-2.01.01 | Define ingestion pattern per source (batch, CDC, event) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 14 | 0 | 0 | 0 | 0 | 43 | 0.6651%
DR-2.01.02 | Set up SAP connectivity (SAP Datasphere / BDC / ODP) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86 | 1.33%
DR-2.01.03 | Build SAP pipelines: materials, orders, maintenance, quality notifications |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 114 | 1.763%
DR-2.01.04 | Build MES pipelines: production, downtime, scrap |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86 | 1.33%
DR-2.01.05 | Build SharePoint and file-share connectors for documents |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 57 | 0.8817%
DR-2.01.06 | Map business rules and transformations with users |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 57 | 0 | 0 | 71 | 1.098%
DR-2.01.07 | Add scheduling, alerting and error handling |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 57 | 0.8817%
DR-2.01.08 | Reconciliation testing against source systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 86 | 1.33%
DR-2.01.09 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 36 | 0.5568%
DR-2.01.10 | Promote through dev / test / prod and release |  |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.3712%
DR-2.01.11 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 24 | 0.3712%
DR-2.01.12 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 48 | 0.7425%
DR-2.02 | Document ingestion: OCR, parsing, chunking | Foundry | Document ingestion pipeline | 0 | 0 | 12 | 0 | 18 | 159 | 123 | 0 | 0 | 0 | 49 | 0 | 361 | 5.584%
DR-2.02.01 | Profile document types (PDF specs, scans, Excel, drawings) |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 24 | 0.3712%
DR-2.02.02 | Set up Azure AI Document Intelligence for OCR and layout |  |  | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.3867%
DR-2.02.03 | Build parsing for tables, headers and sections |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 25 | 0 | 0 | 0 | 0 | 0 | 62 | 0.959%
DR-2.02.04 | Implement chunking strategy (structure-aware, size, overlap) |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0.5723%
DR-2.02.05 | Extract metadata (plant, product, revision, date) |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 25 | 0 | 0 | 0 | 0 | 0 | 37 | 0.5723%
DR-2.02.06 | Build incremental ingestion (new, changed, deleted documents) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 61 | 0.9435%
DR-2.02.07 | Quality checks on extracted text |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49 | 0.7579%
DR-2.02.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.2784%
DR-2.02.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.1856%
DR-2.02.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.1856%
DR-2.02.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.3712%
DR-2.03 | Embedding models: text-embedding-3, Cohere, BGE / E5 | Foundry | Embedding service | 0 | 0 | 4 | 0 | 22 | 77 | 0 | 0 | 0 | 0 | 16 | 0 | 119 | 1.841%
DR-2.03.01 | Benchmark embedding models on Ball documents |  |  | 0 | 0 | 0 | 0 | 8 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0.5104%
DR-2.03.02 | Select model and vector dimensions |  |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.1237%
DR-2.03.03 | Deploy embedding endpoints (Foundry and self-hosted BGE / E5) |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2475%
DR-2.03.04 | Build batch embedding job with retries |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2475%
DR-2.03.05 | Embedding quality testing |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 24 | 0.3712%
DR-2.03.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0.09281%
DR-2.03.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.06187%
DR-2.03.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.06187%
DR-2.03.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.1237%
DR-2.04 | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Foundry | Search indexes | 0 | 0 | 9 | 0 | 44 | 150 | 41 | 0 | 0 | 0 | 41 | 0 | 285 | 4.408%
DR-2.04.01 | Design index schema and fields |  |  | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.3867%
DR-2.04.02 | Deploy Azure AI Search (tier, replicas, partitions) |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1547%
DR-2.04.03 | Build indexers / push pipeline from the chunk store |  |  | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 62 | 0.959%
DR-2.04.04 | Configure vector + BM25 hybrid search and semantic ranker |  |  | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.4795%
DR-2.04.05 | Add filters (plant, document type, security) |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 30 | 0.464%
DR-2.04.06 | Tune relevance with test queries |  |  | 0 | 0 | 0 | 0 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0.5414%
DR-2.04.07 | Search quality testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 41 | 0.6342%
DR-2.04.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0.2166%
DR-2.04.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.1392%
DR-2.04.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.1392%
DR-2.04.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0.2939%
DR-2.05 | Data quality validation rules | AI Data Lake | Data quality rules and reports | 0 | 0 | 10 | 0 | 0 | 0 | 152 | 65 | 0 | 25 | 49 | 0 | 301 | 4.656%
DR-2.05.01 | Define quality rules with data owners |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 50 | 0.7734%
DR-2.05.02 | Implement rules (completeness, validity, freshness) in pipelines |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73 | 1.129%
DR-2.05.03 | Build data quality dashboard and alerts |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 37 | 0.5723%
DR-2.05.04 | Define issue triage process |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 25 | 0.3867%
DR-2.05.05 | Test the rules |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 49 | 0 | 61 | 0.9435%
DR-2.05.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 15 | 0.232%
DR-2.05.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1547%
DR-2.05.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1547%
DR-2.05.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0.3094%
DR-2.06 | Fabric / OneLake for analytics | AI Data Lake | Fabric workspace and lakehouse | 0 | 24 | 60 | 0 | 0 | 0 | 205 | 41 | 0 | 0 | 0 | 0 | 330 | 5.104%
DR-2.06.01 | Design Fabric workspaces and capacity |  |  | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.2784%
DR-2.06.02 | Provision Fabric capacity and workspaces |  |  | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.4795%
DR-2.06.03 | Set up OneLake shortcuts to ADLS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 0.3867%
DR-2.06.04 | Build lakehouse / warehouse models (production, quality, supply) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 98 | 1.516%
DR-2.06.05 | Build semantic model for the Analyst agent |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 49 | 0.7579%
DR-2.06.06 | Apply workspace security and governance |  |  | 0 | 6 | 18 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 49 | 0.7579%
DR-2.06.07 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 16 | 0.2475%
DR-2.06.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0.1701%
DR-2.06.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 0.1701%
DR-2.06.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 22 | 0.3403%
| Subtotal: AI Data Readiness |  |  | 0 | 24 | 119 | 0 | 84 | 386 | 1022 | 170 | 0 | 82 | 241 | 0 | 2128 | 32.92%
AI Use Cases: Pilot
UC-2.01 | Analyst agent: plain-English questions over Fabric / SQL | Factory | Analyst agent | 0 | 0 | 24 | 0 | 35 | 316 | 121 | 0 | 48 | 73 | 98 | 0 | 715 | 11.06%
UC-2.01.01 | Gather question catalog and metric definitions |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49 | 0.7579%
UC-2.01.02 | Prepare semantic model and metadata for NL-to-SQL / DAX |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73 | 1.129%
UC-2.01.03 | Build NL-to-SQL tool with schema grounding |  |  | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1.516%
UC-2.01.04 | Add result explanation and chart generation |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 24 | 0 | 0 | 0 | 73 | 1.129%
UC-2.01.05 | Add guardrails (row limits, read-only, row-level security) |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 24 | 0 | 0 | 0 | 0 | 0 | 61 | 0.9435%
UC-2.01.06 | Integrate with orchestrator and memory |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 24 | 0 | 0 | 0 | 61 | 0.9435%
UC-2.01.07 | Accuracy testing on the golden set |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 24 | 98 | 0 | 170 | 2.63%
UC-2.01.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0.5414%
UC-2.01.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.3712%
UC-2.01.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.3712%
UC-2.01.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0.727%
UC-2.02 | Spec agent: RAG over specs and SOPs | Factory | Spec agent | 0 | 0 | 19 | 0 | 28 | 251 | 48 | 0 | 48 | 74 | 98 | 0 | 566 | 8.755%
UC-2.02.01 | Collect spec and SOP corpus with document owners |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 37 | 0 | 0 | 61 | 0.9435%
UC-2.02.02 | Build retrieval chain with citations |  |  | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1.129%
UC-2.02.03 | Handle revisions and plant-specific variants |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 24 | 0 | 0 | 0 | 0 | 0 | 61 | 0.9435%
UC-2.02.04 | Format answers with source links |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 48 | 0.7425%
UC-2.02.05 | Integrate with the orchestrator |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 24 | 0 | 0 | 0 | 61 | 0.9435%
UC-2.02.06 | Accuracy testing with SMEs |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 37 | 98 | 0 | 159 | 2.459%
UC-2.02.07 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0.4331%
UC-2.02.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0.2939%
UC-2.02.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0.2939%
UC-2.02.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0.5723%
UC-2.03 | Deliver in Teams / Copilot | Factory | Teams app | 0 | 0 | 7 | 16 | 10 | 16 | 0 | 0 | 117 | 0 | 33 | 0 | 199 | 3.078%
UC-2.03.01 | Register Teams app / Copilot agent |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 24 | 0.3712%
UC-2.03.02 | Build bot with adaptive cards and SSO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 49 | 0.7579%
UC-2.03.03 | Connect to orchestrator API through APIM |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 32 | 0.495%
UC-2.03.04 | Admin approval and publish to Teams catalog |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 24 | 0.3712%
UC-2.03.05 | Test across desktop, web and mobile |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 33 | 0.5104%
UC-2.03.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1547%
UC-2.03.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.1083%
UC-2.03.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0.1083%
UC-2.03.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13 | 0.2011%
UC-2.04 | Pilot at one or two plants | Factory | Pilot run | 48 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 154 | 0 | 97 | 348 | 5.383%
UC-2.04.01 | Pilot plan and schedule |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0.7425%
UC-2.04.02 | Train pilot users |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 73 | 1.129%
UC-2.04.03 | Hypercare support during the pilot |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 49 | 0 | 0 | 98 | 1.516%
UC-2.04.04 | Weekly pilot reviews |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 24 | 97 | 1.5%
UC-2.04.05 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 19 | 0.2939%
UC-2.04.06 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 13 | 0.2011%
UC-2.05 | Collect user feedback and evaluations | Factory | Feedback and evaluation report | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 59 | 16 | 0 | 107 | 1.655%
UC-2.05.01 | Capture in-app ratings and comments |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2475%
UC-2.05.02 | Run user surveys and interviews |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 33 | 0.5104%
UC-2.05.03 | Analyse feedback and evaluation results |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 16 | 0 | 48 | 0.7425%
UC-2.05.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0.09281%
UC-2.05.05 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0.06187%
UC-2.06 | Go / no-go against KPIs | Factory | Go / no-go decision | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 51 | 0.7889%
UC-2.06.01 | Compare KPIs to baseline |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12 | 0.1856%
UC-2.06.02 | Write pilot report and recommendation |  |  | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 24 | 0.3712%
UC-2.06.03 | Steering committee decision |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.1856%
UC-2.06.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0.0464%
UC-2.07 | Hypercare and production support for live agents (added) | Factory | Stable agents in production, issue log | 8 | 0 | 0 | 0 | 0 | 65 | 16 | 0 | 32 | 8 | 16 | 0 | 145 | 2.243%
UC-2.07.01 | L2 support for live agents (monitor, triage, answer users) |  |  | 0 | 0 | 0 | 0 | 0 | 41 | 16 | 0 | 16 | 0 | 0 | 0 | 73 | 1.129%
UC-2.07.02 | Fix production defects and tune prompts / retrieval |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 16 | 0 | 16 | 0 | 56 | 0.8662%
UC-2.07.03 | Weekly operations and quality review |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 0.2475%
| Subtotal: AI Use Cases |  |  | 68 | 0 | 50 | 16 | 85 | 729 | 185 | 0 | 245 | 395 | 261 | 97 | 2131 | 32.96%
Program Management: Build
PM-2.01 | Program management, planning, status and steering (added) | All teams | Plans, status reports, RAID log | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 6.404%
PM-2.01.01 | Phase plan and schedule |  |  | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1.129%
PM-2.01.02 | Weekly status reporting and RAID log |  |  | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 1.887%
PM-2.01.03 | Steering committee preparation |  |  | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1.129%
PM-2.01.04 | Architecture design authority reviews |  |  | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0.7425%
PM-2.01.05 | Resource and vendor coordination |  |  | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1.516%
| Subtotal: Program Management |  |  | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 6.404%
| Phase 2 total |  |  | 434 | 48 | 334 | 96 | 511 | 2024 | 1227 | 170 | 319 | 493 | 712 | 97 | 6465 | 100%
| Person-weeks at the hours per week set on the Resources sheet | [14 empty] | 161.625

## Phase 3
Phase 3: tasks and hours for each item (Scale / Enrich / Expand)
Bold rows are the slide items; the rows beneath are their implementation tasks (green = linked to Task Breakdown).
ID | Item / task | Owner team | Deliverable | PM | CA | DO | SE | AIA | AIE | DE | DG | DEV | BA | QA | CM | Total hours | % of phase
AI Platform Setup: Scale
PS-3.01 | Redis semantic, embedding and response caches | Platform Engineering | Cache layer | 0 | 15 | 54 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 16 | 0 | 148 | 1.685%
PS-3.01.01 | Design cache strategy and TTLs (semantic, embedding, response) |  |  | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.1822%
PS-3.01.02 | Deploy Azure Cache for Redis with private endpoint |  |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.2847%
PS-3.01.03 | Implement semantic cache in the AI gateway |  |  | 0 | 0 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0.3644%
PS-3.01.04 | Implement embedding cache in the ingestion pipeline |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.1367%
PS-3.01.05 | Add cache metrics and invalidation |  |  | 0 | 0 | 12 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.2278%
PS-3.01.06 | Measure hit rate and answer correctness |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 16 | 0.1822%
PS-3.01.07 | Detailed design and design review |  |  | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.07972%
PS-3.01.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.05694%
PS-3.01.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.05694%
PS-3.01.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1139%
PS-3.02 | Service Bus, Event Grid, Durable Functions | Platform Engineering | Event bus and async workflows | 0 | 33 | 136 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 31 | 0 | 261 | 2.972%
PS-3.02.01 | Design event model, topics and queues |  |  | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.2278%
PS-3.02.02 | Deploy Service Bus namespaces, topics and dead-letter queues |  |  | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.353%
PS-3.02.03 | Deploy Event Grid topics and subscriptions |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.2278%
PS-3.02.04 | Build Durable Functions for long-running agent workflows |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 61 | 0.6947%
PS-3.02.05 | Build Logic Apps for notifications and approvals |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 30 | 0.3416%
PS-3.02.06 | Set up monitoring and dead-letter alerting |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.2278%
PS-3.02.07 | Test retries, ordering and poison-message handling |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 31 | 0.353%
PS-3.02.08 | Detailed design and design review |  |  | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0.148%
PS-3.02.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.1025%
PS-3.02.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.1025%
PS-3.02.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0.1936%
PS-3.03 | Tool and MCP registry with permissions | Foundry | MCP tool registry | 0 | 0 | 16 | 57 | 82 | 219 | 0 | 0 | 57 | 0 | 57 | 0 | 488 | 5.557%
PS-3.03.01 | Define MCP server standards and tool contract |  |  | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0.3303%
PS-3.03.02 | Build tool registry (catalog, owners, versions) |  |  | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 43 | 0 | 0 | 0 | 86 | 0.9794%
PS-3.03.03 | Build MCP servers: SAP S/4HANA, SharePoint, AVEVA PI, FactoryTalk MES, Coupa, Azure SQL |  |  | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1.139%
PS-3.03.04 | Implement per-tool permissions and on-behalf-of authentication |  |  | 0 | 0 | 0 | 43 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0.6491%
PS-3.03.05 | Register MCP servers behind APIM |  |  | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 28 | 0.3189%
PS-3.03.06 | Threat-model tools (read vs write actions) |  |  | 0 | 0 | 0 | 14 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0.4897%
PS-3.03.07 | Contract and permission testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 57 | 0.6491%
PS-3.03.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
PS-3.03.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.1822%
PS-3.03.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.1822%
PS-3.03.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0.3644%
PS-3.04 | Human-in-the-loop review and escalation | Foundry | Approval and escalation workflows | 0 | 0 | 13 | 0 | 19 | 73 | 0 | 0 | 185 | 49 | 49 | 0 | 388 | 4.419%
PS-3.04.01 | Define approval points and escalation rules with the business |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 37 | 0.4214%
PS-3.04.02 | Build approval request UI (Teams adaptive cards and web) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 73 | 0.8313%
PS-3.04.03 | Implement pause / resume in the orchestrator |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.558%
PS-3.04.04 | Build edit-and-feedback capture |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 37 | 0 | 0 | 0 | 49 | 0.558%
PS-3.04.05 | Build escalation and SLA timers |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 37 | 0 | 0 | 0 | 49 | 0.558%
PS-3.04.06 | Define audit trail of decisions |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12 | 0.1367%
PS-3.04.07 | Test approval and timeout scenarios |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49 | 0.558%
PS-3.04.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0.2164%
PS-3.04.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0.148%
PS-3.04.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13 | 0.148%
PS-3.04.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 25 | 0.2847%
PS-3.05 | Admin panel: agent registry, users, policies | Platform Engineering | Admin portal | 0 | 24 | 16 | 24 | 0 | 0 | 0 | 0 | 291 | 49 | 73 | 0 | 477 | 5.432%
PS-3.05.01 | Gather admin requirements and wireframes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 37 | 0.4214%
PS-3.05.02 | Build agent registry screens (create, version, enable / disable) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 73 | 0.8313%
PS-3.05.03 | Build user and role management screens |  |  | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 61 | 0.6947%
PS-3.05.04 | Build policy, prompt and knowledge-base management screens |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 61 | 0.6947%
PS-3.05.05 | Build logs, usage and chargeback views |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 61 | 0.6947%
PS-3.05.06 | Security review |  |  | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.1367%
PS-3.05.07 | UAT with administrators |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 73 | 0 | 85 | 0.968%
PS-3.05.08 | Detailed design and design review |  |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
PS-3.05.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.1822%
PS-3.05.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0.1822%
PS-3.05.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 31 | 0.353%
PS-3.06 | Tracing in Azure Monitor and App Insights | Platform Engineering | Dashboards and traces | 0 | 7 | 101 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 1.697%
PS-3.06.01 | Instrument services with OpenTelemetry |  |  | 0 | 0 | 10 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0.41%
PS-3.06.02 | Enable Foundry tracing for agent runs |  |  | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.1708%
PS-3.06.03 | Configure Log Analytics workspaces and retention |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.2278%
PS-3.06.04 | Build dashboards: latency, errors, token use, agent steps |  |  | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.353%
PS-3.06.05 | Set up trace correlation across gateway, agents and tools |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.2278%
PS-3.06.06 | Detailed design and design review |  |  | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.07972%
PS-3.06.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.05694%
PS-3.06.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.05694%
PS-3.06.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1139%
PS-3.07 | Platform security assessment and penetration test (added) | Platform Engineering | Pen-test report and closed findings | 0 | 8 | 24 | 65 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 145 | 1.651%
PS-3.07.01 | Threat-model the end-to-end platform |  |  | 0 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
PS-3.07.02 | Scope and run external penetration test |  |  | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0.4669%
PS-3.07.03 | Remediate findings across platform, agents and apps |  |  | 0 | 0 | 24 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 56 | 0.6377%
PS-3.07.04 | Retest and close findings |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 24 | 0.2733%
PS-3.08 | Developer enablement and Foundry training (added) | Foundry | Training curriculum, labs, office hours | 0 | 0 | 0 | 0 | 24 | 64 | 0 | 0 | 0 | 0 | 0 | 8 | 96 | 1.093%
PS-3.08.01 | Build training curriculum for agent developers |  |  | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0.3644%
PS-3.08.02 | Hands-on labs using Foundry templates |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
PS-3.08.03 | Weekly office hours and design clinics |  |  | 0 | 0 | 0 | 0 | 8 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0.3644%
PS-3.08.04 | Enablement communications |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0.09111%
| Subtotal: AI Platform Setup |  |  | 0 | 87 | 360 | 146 | 125 | 476 | 0 | 0 | 610 | 98 | 242 | 8 | 2152 | 24.51%
AI Data Readiness: Enrich
DR-3.01 | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Foundry | Knowledge graph | 0 | 0 | 17 | 0 | 99 | 246 | 98 | 0 | 0 | 0 | 49 | 0 | 509 | 5.797%
DR-3.01.01 | Design ontology (plants, lines, equipment, products, specs, suppliers) |  |  | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.558%
DR-3.01.02 | Deploy Cosmos DB for Gremlin |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.1367%
DR-3.01.03 | Build graph load pipelines from SAP / MES master data |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73 | 0.8313%
DR-3.01.04 | Implement GraphRAG indexing over documents |  |  | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1.116%
DR-3.01.05 | Build graph query tools for agents (Gremlin / Cypher) |  |  | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0.6947%
DR-3.01.06 | Validate ontology with SMEs |  |  | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 50 | 0.5694%
DR-3.01.07 | Graph quality testing |  |  | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 49 | 0 | 74 | 0.8427%
DR-3.01.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.2847%
DR-3.01.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0.1936%
DR-3.01.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0.1936%
DR-3.01.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0.3758%
DR-3.02 | Entity extraction and relationship linking | Foundry | Entity extraction model | 0 | 0 | 9 | 0 | 14 | 149 | 61 | 0 | 0 | 20 | 20 | 0 | 273 | 3.109%
DR-3.02.01 | Define entity types and linking rules |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 0 | 30 | 0.3416%
DR-3.02.02 | Build LLM / AI Language extraction pipeline |  |  | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0.5808%
DR-3.02.03 | Resolve entities to master data (SAP material, equipment IDs) |  |  | 0 | 0 | 0 | 0 | 0 | 31 | 41 | 0 | 0 | 0 | 0 | 0 | 72 | 0.82%
DR-3.02.04 | Write relationships to the graph |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 30 | 0.3416%
DR-3.02.05 | Precision / recall evaluation |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 40 | 0.4555%
DR-3.02.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0.1594%
DR-3.02.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.1025%
DR-3.02.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.1025%
DR-3.02.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.205%
DR-3.03 | Event Hubs streaming of plant telemetry | AI Data Lake | Streaming pipeline | 0 | 29 | 72 | 0 | 0 | 0 | 274 | 22 | 0 | 0 | 57 | 0 | 454 | 5.17%
DR-3.03.01 | Design streaming architecture and select tags |  |  | 0 | 29 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 58 | 0.6605%
DR-3.03.02 | Deploy Event Hubs with capture to ADLS |  |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0.41%
DR-3.03.03 | Connect AVEVA PI historian to Event Hubs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 71 | 0.8086%
DR-3.03.04 | Build stream processing for aggregates (Stream Analytics / Fabric Real-Time) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86 | 0.9794%
DR-3.03.05 | Set up anomaly alerting |  |  | 0 | 0 | 21 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 64 | 0.7288%
DR-3.03.06 | Throughput and lag testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 57 | 0.6491%
DR-3.03.07 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 22 | 0.2505%
DR-3.03.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.1708%
DR-3.03.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 0.1708%
DR-3.03.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 0.3416%
DR-3.04 | Semantic memory indexes per domain | Foundry | Domain indexes | 0 | 0 | 7 | 0 | 10 | 122 | 40 | 0 | 0 | 20 | 0 | 0 | 199 | 2.266%
DR-3.04.01 | Define knowledge domains (maintenance, quality, supply, specs) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0.2278%
DR-3.04.02 | Build domain indexes and query routing |  |  | 0 | 0 | 0 | 0 | 0 | 51 | 20 | 0 | 0 | 0 | 0 | 0 | 71 | 0.8086%
DR-3.04.03 | Domain-specific chunking and metadata |  |  | 0 | 0 | 0 | 0 | 0 | 31 | 20 | 0 | 0 | 0 | 0 | 0 | 51 | 0.5808%
DR-3.04.04 | Retrieval tuning per domain |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.2278%
DR-3.04.05 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1139%
DR-3.04.06 | Promote through dev / test / prod and release |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.07972%
DR-3.04.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.07972%
DR-3.04.08 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0.148%
DR-3.05 | Row and document-level security on indexes | Platform Engineering | Security trimming on search | 0 | 13 | 0 | 107 | 0 | 73 | 0 | 0 | 0 | 0 | 49 | 0 | 242 | 2.756%
DR-3.05.01 | Map document ACLs from SharePoint / SAP to index fields |  |  | 0 | 0 | 0 | 37 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.558%
DR-3.05.02 | Implement security-trimming filters in retrieval |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.558%
DR-3.05.03 | Sync ACL changes to the index |  |  | 0 | 0 | 0 | 24 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0.41%
DR-3.05.04 | Security review |  |  | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0.4214%
DR-3.05.05 | Negative access testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49 | 0.558%
DR-3.05.06 | Detailed design and design review |  |  | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0.148%
DR-3.05.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0.1025%
DR-3.06 | Golden test sets for evaluation | Factory | Golden datasets | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 15 | 0 | 132 | 73 | 0 | 268 | 3.052%
DR-3.06.01 | Collect real questions from plant users |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49 | 0.558%
DR-3.06.02 | Write expected answers and sources with SMEs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 73 | 0.8313%
DR-3.06.03 | Store test sets in a versioned repository |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
DR-3.06.04 | Wire test sets into the evaluation pipeline |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
DR-3.06.05 | Review coverage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 73 | 0.8313%
DR-3.06.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 15 | 0.1708%
DR-3.06.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0.1139%
| Subtotal: AI Data Readiness |  |  | 0 | 42 | 105 | 107 | 123 | 638 | 473 | 37 | 0 | 172 | 248 | 0 | 1945 | 22.15%
AI Use Cases: Expand
UC-3.01 | Maintenance agent: AVEVA PI signals + work orders | Factory | Maintenance agent | 0 | 0 | 28 | 0 | 43 | 378 | 146 | 0 | 73 | 98 | 98 | 0 | 864 | 9.839%
UC-3.01.01 | Gather requirements with maintenance teams |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49 | 0.558%
UC-3.01.02 | Build AVEVA PI tool: tag lookup, trends, anomalies |  |  | 0 | 0 | 0 | 0 | 0 | 73 | 49 | 0 | 0 | 0 | 0 | 0 | 122 | 1.389%
UC-3.01.03 | Build SAP PM tool: work orders, history, notifications |  |  | 0 | 0 | 0 | 0 | 0 | 61 | 49 | 0 | 0 | 0 | 0 | 0 | 110 | 1.253%
UC-3.01.04 | RAG over equipment manuals and failure history |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 0 | 0 | 0 | 73 | 0.8313%
UC-3.01.05 | Root-cause and recommended-action logic |  |  | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0.8313%
UC-3.01.06 | Draft work orders with approval step |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 49 | 0 | 0 | 0 | 86 | 0.9794%
UC-3.01.07 | Surface agent in Teams / Plant Ops app |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0.2733%
UC-3.01.08 | SME and functional testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 49 | 98 | 0 | 171 | 1.947%
UC-3.01.09 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0.4897%
UC-3.01.10 | Promote through dev / test / prod and release |  |  | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0.3189%
UC-3.01.11 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0.3189%
UC-3.01.12 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0.6491%
UC-3.02 | Quality agent: defect and SPC triage | Factory | Quality agent | 0 | 0 | 24 | 0 | 37 | 318 | 121 | 0 | 49 | 98 | 98 | 0 | 745 | 8.484%
UC-3.02.01 | Gather requirements with quality teams |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49 | 0.558%
UC-3.02.02 | Connect SPC, inspection and defect data |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73 | 0.8313%
UC-3.02.03 | Defect triage and pattern detection |  |  | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1.116%
UC-3.02.04 | RAG over quality procedures and NCRs |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 0 | 0 | 0 | 73 | 0.8313%
UC-3.02.05 | Draft NCR / CAPA with approval step |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 37 | 0 | 0 | 0 | 86 | 0.9794%
UC-3.02.06 | Surface agent in user channels |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0.1367%
UC-3.02.07 | Testing with quality engineers |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 49 | 98 | 0 | 220 | 2.505%
UC-3.02.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0.4214%
UC-3.02.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
UC-3.02.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
UC-3.02.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.558%
UC-3.03 | Supply agent: SAP / Coupa supply risk | Factory | Supply agent | 0 | 0 | 24 | 0 | 37 | 317 | 121 | 0 | 48 | 98 | 98 | 0 | 743 | 8.461%
UC-3.03.01 | Gather requirements with supply chain |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49 | 0.558%
UC-3.03.02 | Build SAP MM / Coupa tools: inventory, POs, supplier data |  |  | 0 | 0 | 0 | 0 | 0 | 73 | 73 | 0 | 0 | 0 | 0 | 0 | 146 | 1.663%
UC-3.03.03 | Supply risk signals and scoring |  |  | 0 | 0 | 0 | 0 | 0 | 73 | 24 | 0 | 0 | 0 | 0 | 0 | 97 | 1.105%
UC-3.03.04 | Alerts and recommended actions |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 24 | 0 | 0 | 0 | 73 | 0.8313%
UC-3.03.05 | Surface agent in user channels |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0.2733%
UC-3.03.06 | Testing with planners |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 49 | 98 | 0 | 220 | 2.505%
UC-3.03.07 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0.4214%
UC-3.03.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
UC-3.03.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
UC-3.03.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.558%
UC-3.04 | Planner agent coordinating other agents | Foundry | Planner agent | 0 | 0 | 16 | 0 | 97 | 291 | 0 | 0 | 0 | 0 | 73 | 0 | 477 | 5.432%
UC-3.04.01 | Design multi-agent coordination (routing, handoff, shared context) |  |  | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.558%
UC-3.04.02 | Build intent router and task planner |  |  | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1.116%
UC-3.04.03 | Implement handoff protocol with specialist agents |  |  | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0.8313%
UC-3.04.04 | Add conflict and loop safeguards |  |  | 0 | 0 | 0 | 0 | 24 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0.8313%
UC-3.04.05 | Multi-agent scenario testing |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 73 | 0 | 97 | 1.105%
UC-3.04.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
UC-3.04.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.1822%
UC-3.04.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.1822%
UC-3.04.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.353%
UC-3.05 | Plant Ops web and mobile apps | Factory | Web and mobile apps | 0 | 0 | 24 | 20 | 35 | 0 | 0 | 0 | 478 | 61 | 102 | 0 | 720 | 8.2%
UC-3.05.01 | UX research and wireframes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 41 | 0.4669%
UC-3.05.02 | UI design system and screens |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 61 | 0.6947%
UC-3.05.03 | Build web app (chat, dashboards, approvals) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 163 | 1.856%
UC-3.05.04 | Build mobile app (React Native / PWA) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 122 | 1.389%
UC-3.05.05 | SSO, device policies and offline handling |  |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 61 | 0.6947%
UC-3.05.06 | Accessibility and usability review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 40 | 0.4555%
UC-3.05.07 | Functional and device testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 102 | 1.162%
UC-3.05.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0.3986%
UC-3.05.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.2733%
UC-3.05.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0.2733%
UC-3.05.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 47 | 0.5352%
UC-3.06 | Roll out to more plants | Factory | Plant rollout | 66 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 158 | 0 | 214 | 503 | 5.728%
UC-3.06.01 | Rollout wave plan |  |  | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 66 | 0.7516%
UC-3.06.02 | Plant readiness assessments |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 65 | 0.7402%
UC-3.06.03 | Train-the-trainer and user training |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 1.48%
UC-3.06.04 | Go-live support |  |  | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 33 | 0 | 33 | 131 | 1.492%
UC-3.06.05 | Rollout communications |  |  | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 66 | 0.7516%
UC-3.06.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 27 | 0.3075%
UC-3.06.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0.205%
UC-3.07 | Hypercare and production support for live agents (added) | Factory | Stable agents in production, issue log | 12 | 0 | 0 | 0 | 0 | 98 | 24 | 0 | 48 | 12 | 24 | 0 | 218 | 2.483%
UC-3.07.01 | L2 support for live agents (monitor, triage, answer users) |  |  | 0 | 0 | 0 | 0 | 0 | 61 | 24 | 0 | 24 | 0 | 0 | 0 | 109 | 1.241%
UC-3.07.02 | Fix production defects and tune prompts / retrieval |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 24 | 0 | 24 | 0 | 85 | 0.968%
UC-3.07.03 | Weekly operations and quality review |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 24 | 0.2733%
| Subtotal: AI Use Cases |  |  | 78 | 0 | 116 | 20 | 249 | 1467 | 412 | 0 | 696 | 525 | 493 | 214 | 4270 | 48.63%
Program Management: Scale
PM-3.01 | Program management, planning, status and steering (added) | All teams | Plans, status reports, RAID log | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 4.715%
PM-3.01.01 | Phase plan and schedule |  |  | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0.8313%
PM-3.01.02 | Weekly status reporting and RAID log |  |  | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 1.389%
PM-3.01.03 | Steering committee preparation |  |  | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0.8313%
PM-3.01.04 | Architecture design authority reviews |  |  | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0.5466%
PM-3.01.05 | Resource and vendor coordination |  |  | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1.116%
| Subtotal: Program Management |  |  | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 4.715%
| Phase 3 total |  |  | 444 | 153 | 581 | 273 | 521 | 2581 | 885 | 37 | 1306 | 795 | 983 | 222 | 8781 | 100%
| Person-weeks at the hours per week set on the Resources sheet | [14 empty] | 219.525

## Phase 4
Phase 4: tasks and hours for each item (Optimize / Sustain / Industrialize)
Bold rows are the slide items; the rows beneath are their implementation tasks (green = linked to Task Breakdown).
ID | Item / task | Owner team | Deliverable | PM | CA | DO | SE | AIA | AIE | DE | DG | DEV | BA | QA | CM | Total hours | % of phase
AI Platform Setup: Optimize
PS-4.01 | Evaluation: AI eval SDK, RAGAS, hallucination checks | Foundry | Evaluation suite and quality gates | 0 | 0 | 12 | 0 | 42 | 208 | 0 | 0 | 0 | 24 | 73 | 0 | 359 | 6.598%
PS-4.01.01 | Define evaluation metrics per use case (groundedness, relevance, correctness, safety) |  |  | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 24 | 0.4411%
PS-4.01.02 | Set up Azure AI evaluation SDK and RAGAS pipeline |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.9006%
PS-4.01.03 | Build hallucination and groundedness checks |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0.68%
PS-4.01.04 | Add evaluation gate to CI/CD |  |  | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.5697%
PS-4.01.05 | Run online evaluation on sampled production traffic |  |  | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0.68%
PS-4.01.06 | Build evaluation dashboard |  |  | 0 | 0 | 0 | 0 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.5514%
PS-4.01.07 | Review results with the business |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 73 | 0 | 85 | 1.562%
PS-4.01.08 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.3308%
PS-4.01.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.2205%
PS-4.01.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.2205%
PS-4.01.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.4411%
PS-4.02 | Token usage tracking and budgets per agent | Foundry | Usage dashboard and alerts | 0 | 0 | 65 | 0 | 6 | 32 | 0 | 0 | 0 | 16 | 0 | 0 | 119 | 2.187%
PS-4.02.01 | Define cost-allocation tags (team, agent, use case) |  |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 0.2941%
PS-4.02.02 | Capture token metrics per call from the gateway |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
PS-4.02.03 | Build usage and chargeback dashboard |  |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.4595%
PS-4.02.04 | Configure budgets and alerts per agent |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
PS-4.02.05 | Set up monthly usage review |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 24 | 0.4411%
PS-4.02.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0.1103%
PS-4.02.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.07352%
PS-4.02.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.07352%
PS-4.02.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.147%
PS-4.03 | A/B testing of prompts and models | Foundry | A/B testing framework | 0 | 0 | 5 | 0 | 8 | 98 | 0 | 0 | 32 | 0 | 16 | 0 | 159 | 2.922%
PS-4.03.01 | Design experiment framework (traffic split, success metrics) |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
PS-4.03.02 | Implement traffic splitting in gateway / orchestrator |  |  | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 16 | 0 | 0 | 0 | 41 | 0.7535%
PS-4.03.03 | Build experiment results analysis |  |  | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.4595%
PS-4.03.04 | Build experiment admin screen |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0.2941%
PS-4.03.05 | Run first prompt / model experiment |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 32 | 0.5881%
PS-4.03.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.147%
PS-4.03.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.09189%
PS-4.03.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.09189%
PS-4.03.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0.2022%
PS-4.04 | Backup, DR, point-in-time recovery | Platform Engineering | DR plan with tested restore | 0 | 36 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 240 | 4.411%
PS-4.04.01 | Define RPO / RTO per component |  |  | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.3308%
PS-4.04.02 | Configure database backups and point-in-time restore |  |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0.4595%
PS-4.04.03 | Configure storage geo-redundancy and soft delete |  |  | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.3308%
PS-4.04.04 | Back up AI Search indexes and configuration as code |  |  | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.5697%
PS-4.04.05 | Plan secondary-region deployment |  |  | 0 | 6 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0.68%
PS-4.04.06 | Write DR runbook |  |  | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.3308%
PS-4.04.07 | Run DR drill |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49 | 0.9006%
PS-4.04.08 | Detailed design and design review |  |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.2205%
PS-4.04.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.147%
PS-4.04.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.147%
PS-4.04.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
PS-4.05 | SLO alerting to Teams / PagerDuty | Platform Engineering | Alert rules and runbooks | 0 | 4 | 72 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 1.581%
PS-4.05.01 | Define SLOs and SLIs per service |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.2757%
PS-4.05.02 | Create alert rules and action groups |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.3676%
PS-4.05.03 | Integrate alerts with Teams / PagerDuty |  |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1838%
PS-4.05.04 | Write on-call runbooks |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0.2757%
PS-4.05.05 | Set up security alerting from Defender / Sentinel |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.1838%
PS-4.05.06 | Detailed design and design review |  |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.07352%
PS-4.05.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.05514%
PS-4.05.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.05514%
PS-4.05.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0.1103%
PS-4.06 | On-prem MES gateway, plant to cloud | Platform Engineering | Plant connectivity gateway | 0 | 93 | 236 | 99 | 0 | 0 | 65 | 0 | 0 | 0 | 65 | 0 | 558 | 10.26%
PS-4.06.01 | Assess plant network zones (ISA-95 / Purdue) and OT security rules |  |  | 0 | 33 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1.213%
PS-4.06.02 | Design plant-to-cloud pattern (Azure Arc, IoT Edge, self-hosted gateway) |  |  | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0.6065%
PS-4.06.03 | Deploy edge gateway at the pilot plant |  |  | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 1.195%
PS-4.06.04 | Configure outbound-only secure connectivity and certificates |  |  | 0 | 0 | 49 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 1.507%
PS-4.06.05 | Connect MES and AVEVA PI data feeds |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 65 | 1.195%
PS-4.06.06 | OT security review |  |  | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0.6065%
PS-4.06.07 | Failover and latency testing |  |  | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 114 | 2.095%
PS-4.06.08 | Detailed design and design review |  |  | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0.4962%
PS-4.06.09 | Promote through dev / test / prod and release |  |  | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.3308%
PS-4.06.10 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.3308%
PS-4.06.11 | Defect fixing and rework after testing |  |  | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0.68%
PS-4.07 | Run handover: SRE, ServiceNow and support model (added) | Platform Engineering | Support model, ITSM integration, runbooks | 8 | 8 | 56 | 0 | 0 | 16 | 8 | 0 | 16 | 0 | 8 | 0 | 120 | 2.205%
PS-4.07.01 | Define L1 / L2 / L3 support model and SLAs |  |  | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
PS-4.07.02 | Integrate alerts and incidents with ServiceNow |  |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 40 | 0.7352%
PS-4.07.03 | Runbooks and knowledge-transfer sessions to run team |  |  | 0 | 0 | 24 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 48 | 0.8822%
PS-4.07.04 | Operational readiness review |  |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 16 | 0.2941%
| Subtotal: AI Platform Setup |  |  | 8 | 141 | 601 | 109 | 56 | 354 | 73 | 0 | 48 | 40 | 211 | 0 | 1641 | 30.16%
AI Data Readiness: Sustain
DR-4.01 | Automated re-indexing and freshness checks | AI Data Lake | Scheduled refresh jobs | 0 | 0 | 20 | 0 | 0 | 32 | 60 | 6 | 0 | 0 | 0 | 0 | 118 | 2.169%
DR-4.01.01 | Define freshness SLAs per source |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0.147%
DR-4.01.02 | Schedule incremental re-indexing |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40 | 0.7352%
DR-4.01.03 | Freshness monitoring and alerts |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 32 | 0.5881%
DR-4.01.04 | Re-embed content when models change |  |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
DR-4.01.05 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0.1103%
DR-4.01.06 | Promote through dev / test / prod and release |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.07352%
DR-4.01.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0.07352%
DR-4.01.08 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0.147%
DR-4.02 | End-to-end lineage in Purview | AI Data Lake | Lineage maps | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 76 | 0 | 0 | 0 | 0 | 108 | 1.985%
DR-4.02.01 | Connect pipeline lineage (Data Factory / Fabric) to Purview |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 24 | 0.4411%
DR-4.02.02 | Add lineage from indexes and agents back to sources |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 33 | 0 | 0 | 0 | 0 | 41 | 0.7535%
DR-4.02.03 | Publish lineage views for auditors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 33 | 0.6065%
DR-4.02.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0.1103%
DR-4.02.05 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0.07352%
DR-4.03 | Retention and archive policies | AI Data Lake | Retention policies applied | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 71 | 1.305%
DR-4.03.01 | Define retention per data class and legal holds |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 32 | 0.5881%
DR-4.03.02 | Configure lifecycle and deletion policies |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
DR-4.03.03 | Apply retention to logs and conversation history |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 0.2941%
DR-4.03.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0.07352%
DR-4.03.05 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0.05514%
DR-4.04 | Search index and storage backups | Platform Engineering | Backup jobs | 0 | 4 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 79 | 1.452%
DR-4.04.01 | Automate AI Search index export / rebuild scripts |  |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0.4411%
DR-4.04.02 | Set storage and database backup schedules |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
DR-4.04.03 | Restore test |  |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 24 | 0.4411%
DR-4.04.04 | Detailed design and design review |  |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.07352%
DR-4.04.05 | Promote through dev / test / prod and release |  |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.05514%
DR-4.04.06 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.05514%
DR-4.04.07 | Defect fixing and rework after testing |  |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.09189%
DR-4.05 | Data drift monitoring | Foundry | Drift monitors | 0 | 0 | 3 | 0 | 5 | 58 | 32 | 0 | 0 | 0 | 0 | 0 | 98 | 1.801%
DR-4.05.01 | Define drift signals (data, embeddings, answer quality) |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.2205%
DR-4.05.02 | Build drift jobs and dashboards |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 48 | 0.8822%
DR-4.05.03 | Set alert thresholds and review cadence |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 20 | 0.3676%
DR-4.05.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.09189%
DR-4.05.05 | Promote through dev / test / prod and release |  |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.05514%
DR-4.05.06 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.05514%
DR-4.05.07 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0.1287%
DR-4.06 | Onboard new plants and regions | AI Data Lake | Plant onboarding kit | 0 | 0 | 22 | 0 | 0 | 0 | 310 | 80 | 0 | 147 | 0 | 98 | 657 | 12.07%
DR-4.06.01 | Plant data readiness checklist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 49 | 0 | 0 | 73 | 1.342%
DR-4.06.02 | Parameterize pipelines for plant codes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 147 | 2.702%
DR-4.06.03 | Connect plant sources and validate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 98 | 1.801%
DR-4.06.04 | Onboard local data owners |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 98 | 122 | 2.242%
DR-4.06.05 | Plant go-live sign-off |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 98 | 1.801%
DR-4.06.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 32 | 0.5881%
DR-4.06.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0.4043%
DR-4.06.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 22 | 0.4043%
DR-4.06.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 43 | 0.7903%
| Subtotal: AI Data Readiness |  |  | 0 | 4 | 120 | 16 | 5 | 90 | 434 | 201 | 0 | 147 | 16 | 98 | 1131 | 20.79%
AI Use Cases: Industrialize
UC-4.01 | Sustainability agent: energy and carbon reporting | Factory | Sustainability agent | 0 | 0 | 20 | 0 | 29 | 254 | 121 | 0 | 0 | 98 | 73 | 0 | 595 | 10.94%
UC-4.01.01 | Gather requirements with sustainability team (energy, carbon, water, recycled content) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49 | 0.9006%
UC-4.01.02 | Connect energy meters and utility data |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73 | 1.342%
UC-4.01.03 | Build emission-factor and calculation tools |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 0 | 0 | 0 | 73 | 1.342%
UC-4.01.04 | Draft ESG and customer sustainability reports |  |  | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1.342%
UC-4.01.05 | Detect energy-saving opportunities |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.9006%
UC-4.01.06 | Validate numbers with sustainability team |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 49 | 73 | 0 | 170 | 3.124%
UC-4.01.07 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0.533%
UC-4.01.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.3676%
UC-4.01.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.3676%
UC-4.01.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0.7168%
UC-4.02 | Partner APIs for customers and suppliers | Platform Engineering | Partner API products | 0 | 16 | 52 | 61 | 0 | 0 | 0 | 0 | 153 | 0 | 41 | 0 | 323 | 5.936%
UC-4.02.01 | Define partner use cases and API contracts |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 30 | 0.5514%
UC-4.02.02 | Build APIs and publish in the APIM developer portal |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 0 | 0 | 81 | 1.489%
UC-4.02.03 | Partner onboarding: OAuth clients, keys, quotas |  |  | 0 | 0 | 26 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0.8454%
UC-4.02.04 | Security testing and penetration test |  |  | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.5697%
UC-4.02.05 | Integration testing with a first partner |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 41 | 0 | 76 | 1.397%
UC-4.02.06 | Detailed design and design review |  |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
UC-4.02.07 | Promote through dev / test / prod and release |  |  | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0.2022%
UC-4.02.08 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0.2022%
UC-4.02.09 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 21 | 0.386%
UC-4.03 | Approved write-back actions into SAP | Factory | SAP write-back actions | 0 | 0 | 19 | 58 | 29 | 201 | 0 | 0 | 115 | 57 | 114 | 0 | 593 | 10.9%
UC-4.03.01 | Select write actions (create notification, work order, PO change) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 43 | 0.7903%
UC-4.03.02 | Build write tools via SAP APIs / BAPIs |  |  | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 86 | 0 | 0 | 0 | 115 | 2.114%
UC-4.03.03 | Enforce approvals and dual control |  |  | 0 | 0 | 0 | 29 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 1.581%
UC-4.03.04 | Idempotency, rollback and audit logging |  |  | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 29 | 0 | 0 | 0 | 86 | 1.581%
UC-4.03.05 | Security review |  |  | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0.533%
UC-4.03.06 | Testing in SAP QA system |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 114 | 0 | 128 | 2.353%
UC-4.03.07 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0.533%
UC-4.03.08 | Promote through dev / test / prod and release |  |  | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0.3492%
UC-4.03.09 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0.3492%
UC-4.03.10 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0.7168%
UC-4.04 | Reusable agent templates | Foundry | Agent template library | 0 | 0 | 5 | 0 | 40 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 2.922%
UC-4.04.01 | Extract common patterns from built agents |  |  | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0.5881%
UC-4.04.02 | Build template repository (agent, RAG, tool, evaluation) |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0.9006%
UC-4.04.03 | Build scaffolding pipeline for new agents |  |  | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0.6065%
UC-4.04.04 | Template documentation |  |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.2941%
UC-4.04.05 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0.147%
UC-4.04.06 | Promote through dev / test / prod and release |  |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.09189%
UC-4.04.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.09189%
UC-4.04.08 | Defect fixing and rework after testing |  |  | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0.2022%
UC-4.05 | Adoption tracking and change management | Factory | Adoption dashboard and training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 61 | 0 | 155 | 240 | 4.411%
UC-4.05.01 | Define adoption metrics |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0.4411%
UC-4.05.02 | Build adoption dashboard |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 48 | 0.8822%
UC-4.05.03 | Build change network of plant champions |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 49 | 0.9006%
UC-4.05.04 | Ongoing training and communications |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 73 | 1.342%
UC-4.05.05 | Adoption reviews |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0.4411%
UC-4.05.06 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 13 | 0.2389%
UC-4.05.07 | Documentation, runbook and knowledge transfer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0.1654%
UC-4.06 | Retire or refresh low-value agents | Factory | Agent portfolio review | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 51 | 0.9373%
UC-4.06.01 | Quarterly agent value review |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 18 | 0.3308%
UC-4.06.02 | Decide refresh or retire per agent |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0.2205%
UC-4.06.03 | Decommission or upgrade plan |  |  | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 18 | 0.3308%
UC-4.06.04 | Detailed design and design review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0.05514%
UC-4.07 | Hypercare and production support for live agents (added) | Factory | Stable agents in production, issue log | 16 | 0 | 0 | 0 | 0 | 130 | 33 | 0 | 66 | 16 | 33 | 0 | 294 | 5.403%
UC-4.07.01 | L2 support for live agents (monitor, triage, answer users) |  |  | 0 | 0 | 0 | 0 | 0 | 81 | 33 | 0 | 33 | 0 | 0 | 0 | 147 | 2.702%
UC-4.07.02 | Fix production defects and tune prompts / retrieval |  |  | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 33 | 0 | 33 | 0 | 115 | 2.114%
UC-4.07.03 | Weekly operations and quality review |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 32 | 0.5881%
| Subtotal: AI Use Cases |  |  | 28 | 16 | 96 | 119 | 110 | 699 | 154 | 0 | 358 | 259 | 261 | 155 | 2255 | 41.44%
Program Management: Hand-over
PM-4.01 | Program management, planning, status and steering (added) | All teams | Plans, status reports, RAID log | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 7.609%
PM-4.01.01 | Phase plan and schedule |  |  | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1.342%
PM-4.01.02 | Weekly status reporting and RAID log |  |  | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 2.242%
PM-4.01.03 | Steering committee preparation |  |  | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1.342%
PM-4.01.04 | Architecture design authority reviews |  |  | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0.8822%
PM-4.01.05 | Resource and vendor coordination |  |  | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1.801%
| Subtotal: Program Management |  |  | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 7.609%
| Phase 4 total |  |  | 402 | 185 | 817 | 244 | 195 | 1143 | 661 | 201 | 406 | 446 | 488 | 253 | 5441 | 100%
| Person-weeks at the hours per week set on the Resources sheet | [14 empty] | 136.025

## Activity Hours
Activity hours by resource (rolled up from Task Breakdown)
Every hour figure here is a formula over the Task Breakdown sheet.
ID | Track | Phase | Phase name | Activity | Owner team | Deliverable | Tasks | PM | CA | DO | SE | AIA | AIE | DE | DG | DEV | BA | QA | CM | Total hours
PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Platform Engineering | Landing zone deployed | 12 | 0 | 77 | 197 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 334
PS-1.02 | AI Platform Setup | Phase 1 | Foundation | Entra ID SSO, MFA / PIM, conditional access | Platform Engineering | Identity and access configuration | 8 | 0 | 24 | 16 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 145
PS-1.03 | AI Platform Setup | Phase 1 | Foundation | RBAC / ABAC roles and fine-grained permissions | Platform Engineering | Role and permission matrix | 7 | 0 | 27 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 133
PS-1.04 | AI Platform Setup | Phase 1 | Foundation | Key Vault, TDE / TLS encryption | Platform Engineering | Key and secret management in place | 7 | 0 | 5 | 32 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88
PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Platform Engineering | APIM instance with policies | 10 | 0 | 40 | 131 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 211
PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Platform Engineering | IaC modules and pipelines | 11 | 0 | 35 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 299
PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Platform Engineering | Container hosting platform | 11 | 0 | 31 | 171 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222
PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Foundry | Foundry hub, projects, connections | 10 | 0 | 0 | 37 | 16 | 40 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 157
PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Foundry | Model router with quotas and fallbacks | 12 | 0 | 0 | 86 | 24 | 68 | 160 | 0 | 0 | 0 | 0 | 49 | 0 | 387
PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Foundry | Orchestration framework and reference agent | 12 | 0 | 0 | 22 | 0 | 130 | 358 | 0 | 0 | 74 | 0 | 73 | 0 | 657
PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Foundry | Memory services | 11 | 0 | 0 | 9 | 0 | 44 | 171 | 20 | 0 | 0 | 0 | 31 | 0 | 275
PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Foundry | Prompt repository with versioning | 9 | 0 | 0 | 4 | 0 | 6 | 76 | 0 | 0 | 0 | 16 | 16 | 0 | 118
PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Foundry | Safety policies configured | 10 | 0 | 0 | 7 | 40 | 30 | 80 | 0 | 0 | 0 | 0 | 41 | 0 | 198
PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Platform Engineering | Cache layer | 10 | 0 | 15 | 54 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 16 | 0 | 148
PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Platform Engineering | Event bus and async workflows | 11 | 0 | 33 | 136 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 31 | 0 | 261
PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Foundry | MCP tool registry | 11 | 0 | 0 | 16 | 57 | 82 | 219 | 0 | 0 | 57 | 0 | 57 | 0 | 488
PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Foundry | Approval and escalation workflows | 11 | 0 | 0 | 13 | 0 | 19 | 73 | 0 | 0 | 185 | 49 | 49 | 0 | 388
PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Platform Engineering | Admin portal | 11 | 0 | 24 | 16 | 24 | 0 | 0 | 0 | 0 | 291 | 49 | 73 | 0 | 477
PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Platform Engineering | Dashboards and traces | 9 | 0 | 7 | 101 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 149
PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Foundry | Evaluation suite and quality gates | 11 | 0 | 0 | 12 | 0 | 42 | 208 | 0 | 0 | 0 | 24 | 73 | 0 | 359
PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Foundry | Usage dashboard and alerts | 9 | 0 | 0 | 65 | 0 | 6 | 32 | 0 | 0 | 0 | 16 | 0 | 0 | 119
PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Foundry | A/B testing framework | 9 | 0 | 0 | 5 | 0 | 8 | 98 | 0 | 0 | 32 | 0 | 16 | 0 | 159
PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Platform Engineering | DR plan with tested restore | 11 | 0 | 36 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 240
PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Platform Engineering | Alert rules and runbooks | 9 | 0 | 4 | 72 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86
PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Platform Engineering | Plant connectivity gateway | 11 | 0 | 93 | 236 | 99 | 0 | 0 | 65 | 0 | 0 | 0 | 65 | 0 | 558
DR-1.01 | AI Data Readiness | Phase 1 | Assess | Inventory sources: SAP S/4HANA, MES, AVEVA PI, SharePoint, Coupa | AI Data Lake | Source system inventory | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 87 | 0 | 82 | 0 | 0 | 218
DR-1.02 | AI Data Readiness | Phase 1 | Assess | Classify data and tag PII | AI Data Lake | Data classification and PII tags | 7 | 0 | 0 | 0 | 40 | 0 | 0 | 20 | 96 | 0 | 0 | 0 | 0 | 156
DR-1.03 | AI Data Readiness | Phase 1 | Assess | Name data owners and stewards | AI Data Lake | Data ownership RACI | 6 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 27 | 0 | 16 | 88
DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Platform Engineering | Storage accounts and lifecycle rules | 9 | 0 | 21 | 61 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98
DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Platform Engineering | Databases provisioned | 9 | 0 | 22 | 65 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 119
DR-1.06 | AI Data Readiness | Phase 1 | Assess | Catalog and lineage baseline in Purview | AI Data Lake | Purview scans and catalog | 7 | 0 | 0 | 0 | 20 | 0 | 0 | 41 | 118 | 0 | 0 | 0 | 0 | 179
DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | AI Data Lake | Ingestion pipelines | 12 | 0 | 0 | 24 | 0 | 0 | 0 | 501 | 64 | 0 | 57 | 86 | 0 | 732
DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Foundry | Document ingestion pipeline | 11 | 0 | 0 | 12 | 0 | 18 | 159 | 123 | 0 | 0 | 0 | 49 | 0 | 361
DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Foundry | Embedding service | 9 | 0 | 0 | 4 | 0 | 22 | 77 | 0 | 0 | 0 | 0 | 16 | 0 | 119
DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Foundry | Search indexes | 11 | 0 | 0 | 9 | 0 | 44 | 150 | 41 | 0 | 0 | 0 | 41 | 0 | 285
DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | AI Data Lake | Data quality rules and reports | 9 | 0 | 0 | 10 | 0 | 0 | 0 | 152 | 65 | 0 | 25 | 49 | 0 | 301
DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | AI Data Lake | Fabric workspace and lakehouse | 10 | 0 | 24 | 60 | 0 | 0 | 0 | 205 | 41 | 0 | 0 | 0 | 0 | 330
DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Foundry | Knowledge graph | 11 | 0 | 0 | 17 | 0 | 99 | 246 | 98 | 0 | 0 | 0 | 49 | 0 | 509
DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Foundry | Entity extraction model | 9 | 0 | 0 | 9 | 0 | 14 | 149 | 61 | 0 | 0 | 20 | 20 | 0 | 273
DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | AI Data Lake | Streaming pipeline | 10 | 0 | 29 | 72 | 0 | 0 | 0 | 274 | 22 | 0 | 0 | 57 | 0 | 454
DR-3.04 | AI Data Readiness | Phase 3 | Enrich | Semantic memory indexes per domain | Foundry | Domain indexes | 8 | 0 | 0 | 7 | 0 | 10 | 122 | 40 | 0 | 0 | 20 | 0 | 0 | 199
DR-3.05 | AI Data Readiness | Phase 3 | Enrich | Row and document-level security on indexes | Platform Engineering | Security trimming on search | 7 | 0 | 13 | 0 | 107 | 0 | 73 | 0 | 0 | 0 | 0 | 49 | 0 | 242
DR-3.06 | AI Data Readiness | Phase 3 | Enrich | Golden test sets for evaluation | Factory | Golden datasets | 7 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 15 | 0 | 132 | 73 | 0 | 268
DR-4.01 | AI Data Readiness | Phase 4 | Sustain | Automated re-indexing and freshness checks | AI Data Lake | Scheduled refresh jobs | 8 | 0 | 0 | 20 | 0 | 0 | 32 | 60 | 6 | 0 | 0 | 0 | 0 | 118
DR-4.02 | AI Data Readiness | Phase 4 | Sustain | End-to-end lineage in Purview | AI Data Lake | Lineage maps | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 76 | 0 | 0 | 0 | 0 | 108
DR-4.03 | AI Data Readiness | Phase 4 | Sustain | Retention and archive policies | AI Data Lake | Retention policies applied | 5 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 71
DR-4.04 | AI Data Readiness | Phase 4 | Sustain | Search index and storage backups | Platform Engineering | Backup jobs | 7 | 0 | 4 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 79
DR-4.05 | AI Data Readiness | Phase 4 | Sustain | Data drift monitoring | Foundry | Drift monitors | 7 | 0 | 0 | 3 | 0 | 5 | 58 | 32 | 0 | 0 | 0 | 0 | 0 | 98
DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | AI Data Lake | Plant onboarding kit | 9 | 0 | 0 | 22 | 0 | 0 | 0 | 310 | 80 | 0 | 147 | 0 | 98 | 657
UC-1.01 | AI Use Cases | Phase 1 | Discover | Build use-case backlog with plant and business owners | Factory | Use-case backlog | 6 | 40 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 119 | 0 | 0 | 179
UC-1.02 | AI Use Cases | Phase 1 | Discover | Rank by value and data readiness | Factory | Prioritized use-case list | 5 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 58 | 0 | 0 | 106
UC-1.03 | AI Use Cases | Phase 1 | Discover | Set success KPIs and baselines | Factory | KPI baseline | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 91 | 0 | 0 | 111
UC-1.04 | AI Use Cases | Phase 1 | Discover | Pick pilots: Analyst agent, Spec agent | Factory | Pilot charters | 5 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 71
UC-1.05 | AI Use Cases | Phase 1 | Discover | Define approval rules per use case | Factory | Human approval rules | 5 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 71
UC-1.06 | AI Use Cases | Phase 1 | Discover | Responsible-AI review | Foundry | Responsible-AI assessment | 5 | 0 | 0 | 0 | 16 | 39 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 71
UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Factory | Analyst agent | 11 | 0 | 0 | 24 | 0 | 35 | 316 | 121 | 0 | 48 | 73 | 98 | 0 | 715
UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Factory | Spec agent | 10 | 0 | 0 | 19 | 0 | 28 | 251 | 48 | 0 | 48 | 74 | 98 | 0 | 566
UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Factory | Teams app | 9 | 0 | 0 | 7 | 16 | 10 | 16 | 0 | 0 | 117 | 0 | 33 | 0 | 199
UC-2.04 | AI Use Cases | Phase 2 | Pilot | Pilot at one or two plants | Factory | Pilot run | 6 | 48 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 154 | 0 | 97 | 348
UC-2.05 | AI Use Cases | Phase 2 | Pilot | Collect user feedback and evaluations | Factory | Feedback and evaluation report | 5 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 59 | 16 | 0 | 107
UC-2.06 | AI Use Cases | Phase 2 | Pilot | Go / no-go against KPIs | Factory | Go / no-go decision | 4 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 51
UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Factory | Maintenance agent | 12 | 0 | 0 | 28 | 0 | 43 | 378 | 146 | 0 | 73 | 98 | 98 | 0 | 864
UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Factory | Quality agent | 11 | 0 | 0 | 24 | 0 | 37 | 318 | 121 | 0 | 49 | 98 | 98 | 0 | 745
UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Factory | Supply agent | 10 | 0 | 0 | 24 | 0 | 37 | 317 | 121 | 0 | 48 | 98 | 98 | 0 | 743
UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Foundry | Planner agent | 9 | 0 | 0 | 16 | 0 | 97 | 291 | 0 | 0 | 0 | 0 | 73 | 0 | 477
UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | Factory | Web and mobile apps | 11 | 0 | 0 | 24 | 20 | 35 | 0 | 0 | 0 | 478 | 61 | 102 | 0 | 720
UC-3.06 | AI Use Cases | Phase 3 | Expand | Roll out to more plants | Factory | Plant rollout | 7 | 66 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 158 | 0 | 214 | 503
UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Factory | Sustainability agent | 10 | 0 | 0 | 20 | 0 | 29 | 254 | 121 | 0 | 0 | 98 | 73 | 0 | 595
UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Platform Engineering | Partner API products | 9 | 0 | 16 | 52 | 61 | 0 | 0 | 0 | 0 | 153 | 0 | 41 | 0 | 323
UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Factory | SAP write-back actions | 10 | 0 | 0 | 19 | 58 | 29 | 201 | 0 | 0 | 115 | 57 | 114 | 0 | 593
UC-4.04 | AI Use Cases | Phase 4 | Industrialize | Reusable agent templates | Foundry | Agent template library | 8 | 0 | 0 | 5 | 0 | 40 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 159
UC-4.05 | AI Use Cases | Phase 4 | Industrialize | Adoption tracking and change management | Factory | Adoption dashboard and training | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 61 | 0 | 155 | 240
UC-4.06 | AI Use Cases | Phase 4 | Industrialize | Retire or refresh low-value agents | Factory | Agent portfolio review | 4 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 51
PM-1.01 | Program Management | Phase 1 | Mobilize | Program management, planning, status and steering (added) | All teams | Plans, status reports, RAID log | 5 | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414
PM-2.01 | Program Management | Phase 2 | Build | Program management, planning, status and steering (added) | All teams | Plans, status reports, RAID log | 5 | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414
PM-3.01 | Program Management | Phase 3 | Scale | Program management, planning, status and steering (added) | All teams | Plans, status reports, RAID log | 5 | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414
PM-4.01 | Program Management | Phase 4 | Hand-over | Program management, planning, status and steering (added) | All teams | Plans, status reports, RAID log | 5 | 366 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414
PS-3.07 | AI Platform Setup | Phase 3 | Scale | Platform security assessment and penetration test (added) | Platform Engineering | Pen-test report and closed findings | 4 | 0 | 8 | 24 | 65 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 0 | 145
PS-4.07 | AI Platform Setup | Phase 4 | Optimize | Run handover: SRE, ServiceNow and support model (added) | Platform Engineering | Support model, ITSM integration, runbooks | 4 | 8 | 8 | 56 | 0 | 0 | 16 | 8 | 0 | 16 | 0 | 8 | 0 | 120
PS-3.08 | AI Platform Setup | Phase 3 | Scale | Developer enablement and Foundry training (added) | Foundry | Training curriculum, labs, office hours | 4 | 0 | 0 | 0 | 0 | 24 | 64 | 0 | 0 | 0 | 0 | 0 | 8 | 96
UC-2.07 | AI Use Cases | Phase 2 | Pilot | Hypercare and production support for live agents (added) | Factory | Stable agents in production, issue log | 3 | 8 | 0 | 0 | 0 | 0 | 65 | 16 | 0 | 32 | 8 | 16 | 0 | 145
UC-3.07 | AI Use Cases | Phase 3 | Expand | Hypercare and production support for live agents (added) | Factory | Stable agents in production, issue log | 3 | 12 | 0 | 0 | 0 | 0 | 98 | 24 | 0 | 48 | 12 | 24 | 0 | 218
UC-4.07 | AI Use Cases | Phase 4 | Industrialize | Hypercare and production support for live agents (added) | Factory | Stable agents in production, issue log | 3 | 16 | 0 | 0 | 0 | 0 | 130 | 33 | 0 | 66 | 16 | 33 | 0 | 294
Total | [6 empty] | 677 | 1734 | 692 | 2649 | 1027 | 1358 | 5748 | 2935 | 754 | 2031 | 2225 | 2259 | 588 | 24000

## Task Breakdown
Task breakdown: every implementation task with hours by role
Hours in blue on yellow are the planning inputs for the whole workbook. Edit them here; Activity Hours, the phase sheets and the Summary all recalculate.
Task ID | Activity ID | Track | Phase | Phase name | Activity | Task | Owner team | PM | CA | DO | SE | AIA | AIE | DE | DG | DEV | BA | QA | CM | Total hours
PS-1.01.01 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Define management-group and subscription hierarchy (prod, non-prod, sandbox) | Platform Engineering | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
PS-1.01.02 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Design hub-and-spoke network, IP address plan and DNS | Platform Engineering | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
PS-1.01.03 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Deploy hub VNet, Azure Firewall and spoke VNets | Platform Engineering | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
PS-1.01.04 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Set up ExpressRoute / VPN to Ball data centers and plants | Platform Engineering | 0 | 10 | 31 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46
PS-1.01.05 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Configure private endpoints and private DNS zones for PaaS services | Platform Engineering | 0 | 0 | 41 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
PS-1.01.06 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Apply Azure Policy baseline (allowed regions, tagging, no public IPs) | Platform Engineering | 0 | 5 | 20 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
PS-1.01.07 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Enable Defender for Cloud and diagnostic settings | Platform Engineering | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-1.01.08 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Validate connectivity and policy compliance | Platform Engineering | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 30
PS-1.01.09 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Detailed design and design review | Platform Engineering | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
PS-1.01.10 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
PS-1.01.11 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
PS-1.01.12 | PS-1.01 | AI Platform Setup | Phase 1 | Foundation | Azure landing zone, subscriptions, VNets, private endpoints | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
PS-1.02.01 | PS-1.02 | AI Platform Setup | Phase 1 | Foundation | Entra ID SSO, MFA / PIM, conditional access | Register enterprise apps and app registrations for platform services | Platform Engineering | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-1.02.02 | PS-1.02 | AI Platform Setup | Phase 1 | Foundation | Entra ID SSO, MFA / PIM, conditional access | Configure SSO (OIDC / SAML) for web, mobile and Teams clients | Platform Engineering | 0 | 0 | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
PS-1.02.03 | PS-1.02 | AI Platform Setup | Phase 1 | Foundation | Entra ID SSO, MFA / PIM, conditional access | Enforce MFA and create conditional access policies (device, location, risk) | Platform Engineering | 0 | 8 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
PS-1.02.04 | PS-1.02 | AI Platform Setup | Phase 1 | Foundation | Entra ID SSO, MFA / PIM, conditional access | Set up PIM for privileged roles with approval and time limits | Platform Engineering | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-1.02.05 | PS-1.02 | AI Platform Setup | Phase 1 | Foundation | Entra ID SSO, MFA / PIM, conditional access | Create managed identities for services and agents | Platform Engineering | 0 | 8 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-1.02.06 | PS-1.02 | AI Platform Setup | Phase 1 | Foundation | Entra ID SSO, MFA / PIM, conditional access | Test sign-in flows and break-glass accounts | Platform Engineering | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 20
PS-1.02.07 | PS-1.02 | AI Platform Setup | Phase 1 | Foundation | Entra ID SSO, MFA / PIM, conditional access | Detailed design and design review | Platform Engineering | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
PS-1.02.08 | PS-1.02 | AI Platform Setup | Phase 1 | Foundation | Entra ID SSO, MFA / PIM, conditional access | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-1.03.01 | PS-1.03 | AI Platform Setup | Phase 1 | Foundation | RBAC / ABAC roles and fine-grained permissions | Gather personas and access needs (plant ops, engineers, analysts, admins) | Platform Engineering | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 30
PS-1.03.02 | PS-1.03 | AI Platform Setup | Phase 1 | Foundation | RBAC / ABAC roles and fine-grained permissions | Design role model and permission matrix (RBAC + ABAC attributes: plant, region, function) | Platform Engineering | 0 | 15 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
PS-1.03.03 | PS-1.03 | AI Platform Setup | Phase 1 | Foundation | RBAC / ABAC roles and fine-grained permissions | Create Entra security groups and custom Azure roles | Platform Engineering | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-1.03.04 | PS-1.03 | AI Platform Setup | Phase 1 | Foundation | RBAC / ABAC roles and fine-grained permissions | Map agent and tool permissions to roles | Platform Engineering | 0 | 5 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-1.03.05 | PS-1.03 | AI Platform Setup | Phase 1 | Foundation | RBAC / ABAC roles and fine-grained permissions | Document access request and periodic access review process | Platform Engineering | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
PS-1.03.06 | PS-1.03 | AI Platform Setup | Phase 1 | Foundation | RBAC / ABAC roles and fine-grained permissions | Detailed design and design review | Platform Engineering | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
PS-1.03.07 | PS-1.03 | AI Platform Setup | Phase 1 | Foundation | RBAC / ABAC roles and fine-grained permissions | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-1.04.01 | PS-1.04 | AI Platform Setup | Phase 1 | Foundation | Key Vault, TDE / TLS encryption | Deploy Key Vaults per environment with private endpoints | Platform Engineering | 0 | 0 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-1.04.02 | PS-1.04 | AI Platform Setup | Phase 1 | Foundation | Key Vault, TDE / TLS encryption | Define secret, key and certificate naming and rotation policy | Platform Engineering | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-1.04.03 | PS-1.04 | AI Platform Setup | Phase 1 | Foundation | Key Vault, TDE / TLS encryption | Enable TDE with customer-managed keys on SQL, PostgreSQL and Storage | Platform Engineering | 0 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
PS-1.04.04 | PS-1.04 | AI Platform Setup | Phase 1 | Foundation | Key Vault, TDE / TLS encryption | Enforce TLS 1.2+ and manage certificates for custom domains | Platform Engineering | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-1.04.05 | PS-1.04 | AI Platform Setup | Phase 1 | Foundation | Key Vault, TDE / TLS encryption | Configure vault RBAC and audit logging | Platform Engineering | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-1.04.06 | PS-1.04 | AI Platform Setup | Phase 1 | Foundation | Key Vault, TDE / TLS encryption | Detailed design and design review | Platform Engineering | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-1.04.07 | PS-1.04 | AI Platform Setup | Phase 1 | Foundation | Key Vault, TDE / TLS encryption | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
PS-1.05.01 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Design gateway topology (Front Door to APIM to backends) | Platform Engineering | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-1.05.02 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Deploy Front Door with WAF policy | Platform Engineering | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
PS-1.05.03 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Deploy APIM in internal VNet mode with custom domains | Platform Engineering | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
PS-1.05.04 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Configure products, subscriptions and JWT validation policy | Platform Engineering | 0 | 0 | 26 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
PS-1.05.05 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Configure rate limiting, quotas, routing and request validation policies | Platform Engineering | 0 | 10 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
PS-1.05.06 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Test routing, throttling and authentication failure paths | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20
PS-1.05.07 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Detailed design and design review | Platform Engineering | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
PS-1.05.08 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
PS-1.05.09 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
PS-1.05.10 | PS-1.05 | AI Platform Setup | Phase 1 | Foundation | Front Door + API Management gateway | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
PS-1.06.01 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Choose IaC standard, repository structure and module conventions | Platform Engineering | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-1.06.02 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Set up remote state, environments and workload identity for pipelines | Platform Engineering | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
PS-1.06.03 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Build reusable modules: network, storage, Key Vault, APIM, AKS, AI services | Platform Engineering | 0 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
PS-1.06.04 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Build GitHub Actions pipelines: plan, approval gates, apply | Platform Engineering | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
PS-1.06.05 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Add policy-as-code and security scanning (tfsec / Checkov) | Platform Engineering | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-1.06.06 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Build application CI/CD templates (build, test, container push, deploy) | Platform Engineering | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
PS-1.06.07 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Test pipelines end to end in non-prod | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20
PS-1.06.08 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Detailed design and design review | Platform Engineering | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
PS-1.06.09 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
PS-1.06.10 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
PS-1.06.11 | PS-1.06 | AI Platform Setup | Phase 1 | Foundation | Terraform / Bicep IaC, GitHub Actions CI/CD | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-1.07.01 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Decide hosting model per workload (AKS, Container Apps, Functions) | Platform Engineering | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
PS-1.07.02 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Deploy Azure Container Registry with private endpoint and image scanning | Platform Engineering | 0 | 0 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-1.07.03 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Deploy AKS cluster: node pools, autoscaling, workload identity | Platform Engineering | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
PS-1.07.04 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Install ingress controller, cert-manager and Key Vault CSI driver | Platform Engineering | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
PS-1.07.05 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Deploy Container Apps environment inside the VNet | Platform Engineering | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-1.07.06 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Apply pod security, network policies and Defender for Containers | Platform Engineering | 0 | 0 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-1.07.07 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Set up GPU node pool for self-hosted models | Platform Engineering | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-1.07.08 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Detailed design and design review | Platform Engineering | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
PS-1.07.09 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
PS-1.07.10 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
PS-1.07.11 | PS-1.07 | AI Platform Setup | Phase 1 | Foundation | ACR, AKS and Container Apps | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
PS-2.01.01 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Design Foundry hub and project structure per domain and environment | Foundry | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-2.01.02 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Deploy Foundry hub with managed VNet and private endpoints | Foundry | 0 | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
PS-2.01.03 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Create projects and connect AI Search, Storage, Key Vault, App Insights | Foundry | 0 | 0 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 32
PS-2.01.04 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Deploy base chat and embedding models with capacity / PTU plan | Foundry | 0 | 0 | 0 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 24
PS-2.01.05 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Set up project RBAC and developer access | Foundry | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-2.01.06 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Smoke-test model endpoints from the SDK | Foundry | 0 | 0 | 0 | 0 | 4 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-2.01.07 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
PS-2.01.08 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Promote through dev / test / prod and release | Foundry | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-2.01.09 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-2.01.10 | PS-2.01 | AI Platform Setup | Phase 2 | Core AI build | AI Foundry hub and projects | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11
PS-2.02.01 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Define model routing policy (task type, cost, latency, fallback) | Foundry | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
PS-2.02.02 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Configure APIM AI gateway backends: Azure OpenAI, Anthropic, Gemini, self-hosted | Foundry | 0 | 0 | 43 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 61
PS-2.02.03 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Implement token-based rate limits and quotas per team and agent | Foundry | 0 | 0 | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 36
PS-2.02.04 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Implement retry and fallback across regions and models | Foundry | 0 | 0 | 0 | 0 | 6 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 43
PS-2.02.05 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Deploy self-hosted model (vLLM on AKS) behind the gateway | Foundry | 0 | 0 | 12 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 49
PS-2.02.06 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Emit token metrics and log prompts / responses securely | Foundry | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 24
PS-2.02.07 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Use managed identity for model access (no keys in apps) | Foundry | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
PS-2.02.08 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Load and failover testing | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49
PS-2.02.09 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
PS-2.02.10 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Promote through dev / test / prod and release | Foundry | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
PS-2.02.11 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13
PS-2.02.12 | PS-2.02 | AI Platform Setup | Phase 2 | Core AI build | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-2.03.01 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Evaluate and select orchestration options (Foundry Agent Service, Semantic Kernel, LangGraph) | Foundry | 0 | 0 | 0 | 0 | 37 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 62
PS-2.03.02 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Define agent design standards: tools, state, guardrails, handoff | Foundry | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
PS-2.03.03 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Build orchestration service skeleton (API, sessions, state store) | Foundry | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 37 | 0 | 0 | 0 | 110
PS-2.03.04 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Implement tool calling and agent-to-agent handoff | Foundry | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73
PS-2.03.05 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Implement checkpoints, retries, timeouts and human-in-the-loop hooks | Foundry | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49
PS-2.03.06 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Build a reference agent end to end | Foundry | 0 | 0 | 0 | 0 | 18 | 73 | 0 | 0 | 37 | 0 | 0 | 0 | 128
PS-2.03.07 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Write developer guide and starter template | Foundry | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-2.03.08 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Integration and failure-mode testing | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 73
PS-2.03.09 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
PS-2.03.10 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Promote through dev / test / prod and release | Foundry | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
PS-2.03.11 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 22
PS-2.03.12 | PS-2.03 | AI Platform Setup | Phase 2 | Core AI build | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 43
PS-2.04.01 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Design memory types and retention (working, conversation, long-term, episodic) | Foundry | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-2.04.02 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Implement conversation memory store in Cosmos DB with TTL | Foundry | 0 | 0 | 0 | 0 | 0 | 31 | 10 | 0 | 0 | 0 | 0 | 0 | 41
PS-2.04.03 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Implement working memory / session state in Redis | Foundry | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 26
PS-2.04.04 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Implement long-term semantic memory with embeddings | Foundry | 0 | 0 | 0 | 0 | 0 | 41 | 10 | 0 | 0 | 0 | 0 | 0 | 51
PS-2.04.05 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Add summarization and memory pruning | Foundry | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 26
PS-2.04.06 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Add PII handling and per-user isolation | Foundry | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 30
PS-2.04.07 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Test recall quality and user isolation | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 31
PS-2.04.08 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
PS-2.04.09 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Promote through dev / test / prod and release | Foundry | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
PS-2.04.10 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9
PS-2.04.11 | PS-2.04 | AI Platform Setup | Phase 2 | Core AI build | Memory layer: working, conversation, long-term | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18
PS-2.05.01 | PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Define prompt template standards and metadata | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 4 | 0 | 0 | 16
PS-2.05.02 | PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Set up prompt repository with versioning and approvals | Foundry | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-2.05.03 | PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Build system-prompt and guardrail templates for each agent type | Foundry | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 12 | 0 | 0 | 32
PS-2.05.04 | PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Wire prompt versions into the deployment pipeline | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-2.05.05 | PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Regression-test prompts against a sample set | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 16
PS-2.05.06 | PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
PS-2.05.07 | PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Promote through dev / test / prod and release | Foundry | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
PS-2.05.08 | PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
PS-2.05.09 | PS-2.05 | AI Platform Setup | Phase 2 | Core AI build | Prompt library, templates, versioning | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
PS-2.06.01 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Define safety policy and severity thresholds | Foundry | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-2.06.02 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Enable Azure AI Content Safety filters per model deployment | Foundry | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
PS-2.06.03 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Enable Prompt Shields for jailbreak and indirect injection | Foundry | 0 | 0 | 0 | 10 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-2.06.04 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Add PII detection and redaction on inputs and outputs | Foundry | 0 | 0 | 0 | 10 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 30
PS-2.06.05 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Set up blocklists and safety incident logging | Foundry | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 30
PS-2.06.06 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Red-team testing | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 41
PS-2.06.07 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
PS-2.06.08 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Promote through dev / test / prod and release | Foundry | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
PS-2.06.09 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7
PS-2.06.10 | PS-2.06 | AI Platform Setup | Phase 2 | Core AI build | Content Safety and Prompt Shields | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13
PS-3.01.01 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Design cache strategy and TTLs (semantic, embedding, response) | Platform Engineering | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-3.01.02 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Deploy Azure Cache for Redis with private endpoint | Platform Engineering | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-3.01.03 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Implement semantic cache in the AI gateway | Platform Engineering | 0 | 0 | 12 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 32
PS-3.01.04 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Implement embedding cache in the ingestion pipeline | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-3.01.05 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Add cache metrics and invalidation | Platform Engineering | 0 | 0 | 12 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-3.01.06 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Measure hit rate and answer correctness | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 16
PS-3.01.07 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Detailed design and design review | Platform Engineering | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
PS-3.01.08 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-3.01.09 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-3.01.10 | PS-3.01 | AI Platform Setup | Phase 3 | Scale | Redis semantic, embedding and response caches | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10
PS-3.02.01 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Design event model, topics and queues | Platform Engineering | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-3.02.02 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Deploy Service Bus namespaces, topics and dead-letter queues | Platform Engineering | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
PS-3.02.03 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Deploy Event Grid topics and subscriptions | Platform Engineering | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-3.02.04 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Build Durable Functions for long-running agent workflows | Platform Engineering | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 61
PS-3.02.05 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Build Logic Apps for notifications and approvals | Platform Engineering | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 30
PS-3.02.06 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Set up monitoring and dead-letter alerting | Platform Engineering | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-3.02.07 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Test retries, ordering and poison-message handling | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 31
PS-3.02.08 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Detailed design and design review | Platform Engineering | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
PS-3.02.09 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
PS-3.02.10 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
PS-3.02.11 | PS-3.02 | AI Platform Setup | Phase 3 | Scale | Service Bus, Event Grid, Durable Functions | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
PS-3.03.01 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Define MCP server standards and tool contract | Foundry | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
PS-3.03.02 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Build tool registry (catalog, owners, versions) | Foundry | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 43 | 0 | 0 | 0 | 86
PS-3.03.03 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Build MCP servers: SAP S/4HANA, SharePoint, AVEVA PI, FactoryTalk MES, Coupa, Azure SQL | Foundry | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100
PS-3.03.04 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Implement per-tool permissions and on-behalf-of authentication | Foundry | 0 | 0 | 0 | 43 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 57
PS-3.03.05 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Register MCP servers behind APIM | Foundry | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 28
PS-3.03.06 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Threat-model tools (read vs write actions) | Foundry | 0 | 0 | 0 | 14 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43
PS-3.03.07 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Contract and permission testing | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 57
PS-3.03.08 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
PS-3.03.09 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Promote through dev / test / prod and release | Foundry | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-3.03.10 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-3.03.11 | PS-3.03 | AI Platform Setup | Phase 3 | Scale | Tool and MCP registry with permissions | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 32
PS-3.04.01 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Define approval points and escalation rules with the business | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 37
PS-3.04.02 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Build approval request UI (Teams adaptive cards and web) | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 73
PS-3.04.03 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Implement pause / resume in the orchestrator | Foundry | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49
PS-3.04.04 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Build edit-and-feedback capture | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 37 | 0 | 0 | 0 | 49
PS-3.04.05 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Build escalation and SLA timers | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 37 | 0 | 0 | 0 | 49
PS-3.04.06 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Define audit trail of decisions | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12
PS-3.04.07 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Test approval and timeout scenarios | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49
PS-3.04.08 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
PS-3.04.09 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Promote through dev / test / prod and release | Foundry | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
PS-3.04.10 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13
PS-3.04.11 | PS-3.04 | AI Platform Setup | Phase 3 | Scale | Human-in-the-loop review and escalation | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 25
PS-3.05.01 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Gather admin requirements and wireframes | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 37
PS-3.05.02 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Build agent registry screens (create, version, enable / disable) | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 73
PS-3.05.03 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Build user and role management screens | Platform Engineering | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 61
PS-3.05.04 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Build policy, prompt and knowledge-base management screens | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 61
PS-3.05.05 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Build logs, usage and chargeback views | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 61
PS-3.05.06 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Security review | Platform Engineering | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-3.05.07 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | UAT with administrators | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 73 | 0 | 85
PS-3.05.08 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Detailed design and design review | Platform Engineering | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
PS-3.05.09 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-3.05.10 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16
PS-3.05.11 | PS-3.05 | AI Platform Setup | Phase 3 | Scale | Admin panel: agent registry, users, policies | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 31
PS-3.06.01 | PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Instrument services with OpenTelemetry | Platform Engineering | 0 | 0 | 10 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 36
PS-3.06.02 | PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Enable Foundry tracing for agent runs | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
PS-3.06.03 | PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Configure Log Analytics workspaces and retention | Platform Engineering | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-3.06.04 | PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Build dashboards: latency, errors, token use, agent steps | Platform Engineering | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
PS-3.06.05 | PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Set up trace correlation across gateway, agents and tools | Platform Engineering | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-3.06.06 | PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Detailed design and design review | Platform Engineering | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
PS-3.06.07 | PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-3.06.08 | PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-3.06.09 | PS-3.06 | AI Platform Setup | Phase 3 | Scale | Tracing in Azure Monitor and App Insights | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
PS-4.01.01 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Define evaluation metrics per use case (groundedness, relevance, correctness, safety) | Foundry | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 24
PS-4.01.02 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Set up Azure AI evaluation SDK and RAGAS pipeline | Foundry | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49
PS-4.01.03 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Build hallucination and groundedness checks | Foundry | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 37
PS-4.01.04 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Add evaluation gate to CI/CD | Foundry | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 31
PS-4.01.05 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Run online evaluation on sampled production traffic | Foundry | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 37
PS-4.01.06 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Build evaluation dashboard | Foundry | 0 | 0 | 0 | 0 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 30
PS-4.01.07 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Review results with the business | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 73 | 0 | 85
PS-4.01.08 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
PS-4.01.09 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Promote through dev / test / prod and release | Foundry | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-4.01.10 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-4.01.11 | PS-4.01 | AI Platform Setup | Phase 4 | Optimize | Evaluation: AI eval SDK, RAGAS, hallucination checks | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24
PS-4.02.01 | PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Define cost-allocation tags (team, agent, use case) | Foundry | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16
PS-4.02.02 | PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Capture token metrics per call from the gateway | Foundry | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-4.02.03 | PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Build usage and chargeback dashboard | Foundry | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-4.02.04 | PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Configure budgets and alerts per agent | Foundry | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-4.02.05 | PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Set up monthly usage review | Foundry | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 24
PS-4.02.06 | PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
PS-4.02.07 | PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Promote through dev / test / prod and release | Foundry | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
PS-4.02.08 | PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
PS-4.02.09 | PS-4.02 | AI Platform Setup | Phase 4 | Optimize | Token usage tracking and budgets per agent | Defect fixing and rework after testing | Foundry | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
PS-4.03.01 | PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Design experiment framework (traffic split, success metrics) | Foundry | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-4.03.02 | PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Implement traffic splitting in gateway / orchestrator | Foundry | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 16 | 0 | 0 | 0 | 41
PS-4.03.03 | PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Build experiment results analysis | Foundry | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-4.03.04 | PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Build experiment admin screen | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16
PS-4.03.05 | PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Run first prompt / model experiment | Foundry | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 32
PS-4.03.06 | PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
PS-4.03.07 | PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Promote through dev / test / prod and release | Foundry | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-4.03.08 | PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
PS-4.03.09 | PS-4.03 | AI Platform Setup | Phase 4 | Optimize | A/B testing of prompts and models | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11
PS-4.04.01 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Define RPO / RTO per component | Platform Engineering | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
PS-4.04.02 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Configure database backups and point-in-time restore | Platform Engineering | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
PS-4.04.03 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Configure storage geo-redundancy and soft delete | Platform Engineering | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
PS-4.04.04 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Back up AI Search indexes and configuration as code | Platform Engineering | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
PS-4.04.05 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Plan secondary-region deployment | Platform Engineering | 0 | 6 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
PS-4.04.06 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Write DR runbook | Platform Engineering | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
PS-4.04.07 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Run DR drill | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49
PS-4.04.08 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Detailed design and design review | Platform Engineering | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
PS-4.04.09 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
PS-4.04.10 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
PS-4.04.11 | PS-4.04 | AI Platform Setup | Phase 4 | Optimize | Backup, DR, point-in-time recovery | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-4.05.01 | PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Define SLOs and SLIs per service | Platform Engineering | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
PS-4.05.02 | PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Create alert rules and action groups | Platform Engineering | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PS-4.05.03 | PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Integrate alerts with Teams / PagerDuty | Platform Engineering | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
PS-4.05.04 | PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Write on-call runbooks | Platform Engineering | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
PS-4.05.05 | PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Set up security alerting from Defender / Sentinel | Platform Engineering | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
PS-4.05.06 | PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Detailed design and design review | Platform Engineering | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
PS-4.05.07 | PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
PS-4.05.08 | PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
PS-4.05.09 | PS-4.05 | AI Platform Setup | Phase 4 | Optimize | SLO alerting to Teams / PagerDuty | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
PS-4.06.01 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Assess plant network zones (ISA-95 / Purdue) and OT security rules | Platform Engineering | 0 | 33 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66
PS-4.06.02 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Design plant-to-cloud pattern (Azure Arc, IoT Edge, self-hosted gateway) | Platform Engineering | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
PS-4.06.03 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Deploy edge gateway at the pilot plant | Platform Engineering | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65
PS-4.06.04 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Configure outbound-only secure connectivity and certificates | Platform Engineering | 0 | 0 | 49 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82
PS-4.06.05 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Connect MES and AVEVA PI data feeds | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 65
PS-4.06.06 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | OT security review | Platform Engineering | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
PS-4.06.07 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Failover and latency testing | Platform Engineering | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 114
PS-4.06.08 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Detailed design and design review | Platform Engineering | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
PS-4.06.09 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
PS-4.06.10 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
PS-4.06.11 | PS-4.06 | AI Platform Setup | Phase 4 | Optimize | On-prem MES gateway, plant to cloud | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
DR-1.01.01 | DR-1.01 | AI Data Readiness | Phase 1 | Assess | Inventory sources: SAP S/4HANA, MES, AVEVA PI, SharePoint, Coupa | Run workshops with SAP, MES, AVEVA PI, SharePoint and Coupa owners | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 49 | 0 | 0 | 74
DR-1.01.02 | DR-1.01 | AI Data Readiness | Phase 1 | Assess | Inventory sources: SAP S/4HANA, MES, AVEVA PI, SharePoint, Coupa | Document systems, tables, volumes, refresh rates and access methods | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 25 | 0 | 0 | 0 | 0 | 62
DR-1.01.03 | DR-1.01 | AI Data Readiness | Phase 1 | Assess | Inventory sources: SAP S/4HANA, MES, AVEVA PI, SharePoint, Coupa | Identify document repositories (specs, SOPs, quality records) | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 25 | 0 | 0 | 37
DR-1.01.04 | DR-1.01 | AI Data Readiness | Phase 1 | Assess | Inventory sources: SAP S/4HANA, MES, AVEVA PI, SharePoint, Coupa | Build the data source register | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 25
DR-1.01.05 | DR-1.01 | AI Data Readiness | Phase 1 | Assess | Inventory sources: SAP S/4HANA, MES, AVEVA PI, SharePoint, Coupa | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12
DR-1.01.06 | DR-1.01 | AI Data Readiness | Phase 1 | Assess | Inventory sources: SAP S/4HANA, MES, AVEVA PI, SharePoint, Coupa | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8
DR-1.02.01 | DR-1.02 | AI Data Readiness | Phase 1 | Assess | Classify data and tag PII | Define classification scheme (public, internal, confidential, restricted) | AI Data Lake | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 30
DR-1.02.02 | DR-1.02 | AI Data Readiness | Phase 1 | Assess | Classify data and tag PII | Run Purview automated classification scans | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 30
DR-1.02.03 | DR-1.02 | AI Data Readiness | Phase 1 | Assess | Classify data and tag PII | Review results and tag PII / sensitive columns | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 31 | 0 | 0 | 0 | 0 | 41
DR-1.02.04 | DR-1.02 | AI Data Readiness | Phase 1 | Assess | Classify data and tag PII | Define handling rules per class for AI use | AI Data Lake | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 30
DR-1.02.05 | DR-1.02 | AI Data Readiness | Phase 1 | Assess | Classify data and tag PII | Apply sensitivity labels to documents | AI Data Lake | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
DR-1.02.06 | DR-1.02 | AI Data Readiness | Phase 1 | Assess | Classify data and tag PII | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9
DR-1.02.07 | DR-1.02 | AI Data Readiness | Phase 1 | Assess | Classify data and tag PII | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6
DR-1.03.01 | DR-1.03 | AI Data Readiness | Phase 1 | Assess | Name data owners and stewards | Identify owners per domain (production, quality, supply, finance) | AI Data Lake | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 20
DR-1.03.02 | DR-1.03 | AI Data Readiness | Phase 1 | Assess | Name data owners and stewards | Define steward responsibilities and RACI | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 16
DR-1.03.03 | DR-1.03 | AI Data Readiness | Phase 1 | Assess | Name data owners and stewards | Kick-off and training for stewards | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 16 | 24
DR-1.03.04 | DR-1.03 | AI Data Readiness | Phase 1 | Assess | Name data owners and stewards | Ownership sign-off | AI Data Lake | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 20
DR-1.03.05 | DR-1.03 | AI Data Readiness | Phase 1 | Assess | Name data owners and stewards | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5
DR-1.03.06 | DR-1.03 | AI Data Readiness | Phase 1 | Assess | Name data owners and stewards | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
DR-1.04.01 | DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Design zones (raw, curated, serving) and container layout | Platform Engineering | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
DR-1.04.02 | DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Deploy ADLS Gen2 with hierarchical namespace and private endpoints | Platform Engineering | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
DR-1.04.03 | DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Configure lifecycle tiers (hot, cool, archive) | Platform Engineering | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
DR-1.04.04 | DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Set ACLs aligned to the role model | Platform Engineering | 0 | 0 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
DR-1.04.05 | DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Enable soft delete and versioning | Platform Engineering | 0 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
DR-1.04.06 | DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Detailed design and design review | Platform Engineering | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
DR-1.04.07 | DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
DR-1.04.08 | DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
DR-1.04.09 | DR-1.04 | AI Data Readiness | Phase 1 | Assess | ADLS Gen2 / Blob storage tiers | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
DR-1.05.01 | DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Size and design databases (application metadata, vectors) | Platform Engineering | 0 | 12 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 20
DR-1.05.02 | DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Deploy Azure SQL and PostgreSQL Flexible Server | Platform Engineering | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
DR-1.05.03 | DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Enable pgvector extension and create schemas | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 16
DR-1.05.04 | DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Configure high availability, backups and private access | Platform Engineering | 0 | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
DR-1.05.05 | DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Set up schema migration tooling (Flyway / Liquibase) | Platform Engineering | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 16
DR-1.05.06 | DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Detailed design and design review | Platform Engineering | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
DR-1.05.07 | DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
DR-1.05.08 | DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
DR-1.05.09 | DR-1.05 | AI Data Readiness | Phase 1 | Assess | Azure SQL, PostgreSQL + pgvector | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
DR-1.06.01 | DR-1.06 | AI Data Readiness | Phase 1 | Assess | Catalog and lineage baseline in Purview | Deploy Purview Unified Catalog and register sources | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 30
DR-1.06.02 | DR-1.06 | AI Data Readiness | Phase 1 | Assess | Catalog and lineage baseline in Purview | Configure scans for SAP, SQL, ADLS and SharePoint | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 31
DR-1.06.03 | DR-1.06 | AI Data Readiness | Phase 1 | Assess | Catalog and lineage baseline in Purview | Build business glossary of manufacturing terms | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 41
DR-1.06.04 | DR-1.06 | AI Data Readiness | Phase 1 | Assess | Catalog and lineage baseline in Purview | Set up catalog collections and access | AI Data Lake | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 30
DR-1.06.05 | DR-1.06 | AI Data Readiness | Phase 1 | Assess | Catalog and lineage baseline in Purview | Capture baseline lineage | AI Data Lake | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 30
DR-1.06.06 | DR-1.06 | AI Data Readiness | Phase 1 | Assess | Catalog and lineage baseline in Purview | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10
DR-1.06.07 | DR-1.06 | AI Data Readiness | Phase 1 | Assess | Catalog and lineage baseline in Purview | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 7
DR-2.01.01 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Define ingestion pattern per source (batch, CDC, event) | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 14 | 0 | 0 | 0 | 0 | 43
DR-2.01.02 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Set up SAP connectivity (SAP Datasphere / BDC / ODP) | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86
DR-2.01.03 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Build SAP pipelines: materials, orders, maintenance, quality notifications | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 114
DR-2.01.04 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Build MES pipelines: production, downtime, scrap | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86
DR-2.01.05 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Build SharePoint and file-share connectors for documents | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 57
DR-2.01.06 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Map business rules and transformations with users | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 57 | 0 | 0 | 71
DR-2.01.07 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Add scheduling, alerting and error handling | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 57
DR-2.01.08 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Reconciliation testing against source systems | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 86
DR-2.01.09 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 36
DR-2.01.10 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Promote through dev / test / prod and release | AI Data Lake | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
DR-2.01.11 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 24
DR-2.01.12 | DR-2.01 | AI Data Readiness | Phase 2 | Prepare | Pipelines from SAP, MES and file shares | Defect fixing and rework after testing | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 48
DR-2.02.01 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Profile document types (PDF specs, scans, Excel, drawings) | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 24
DR-2.02.02 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Set up Azure AI Document Intelligence for OCR and layout | Foundry | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 25
DR-2.02.03 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Build parsing for tables, headers and sections | Foundry | 0 | 0 | 0 | 0 | 0 | 37 | 25 | 0 | 0 | 0 | 0 | 0 | 62
DR-2.02.04 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Implement chunking strategy (structure-aware, size, overlap) | Foundry | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 37
DR-2.02.05 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Extract metadata (plant, product, revision, date) | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 25 | 0 | 0 | 0 | 0 | 0 | 37
DR-2.02.06 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Build incremental ingestion (new, changed, deleted documents) | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 61
DR-2.02.07 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Quality checks on extracted text | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49
DR-2.02.08 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
DR-2.02.09 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Promote through dev / test / prod and release | Foundry | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
DR-2.02.10 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12
DR-2.02.11 | DR-2.02 | AI Data Readiness | Phase 2 | Prepare | Document ingestion: OCR, parsing, chunking | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24
DR-2.03.01 | DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Benchmark embedding models on Ball documents | Foundry | 0 | 0 | 0 | 0 | 8 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 33
DR-2.03.02 | DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Select model and vector dimensions | Foundry | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
DR-2.03.03 | DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Deploy embedding endpoints (Foundry and self-hosted BGE / E5) | Foundry | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
DR-2.03.04 | DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Build batch embedding job with retries | Foundry | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
DR-2.03.05 | DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Embedding quality testing | Foundry | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 24
DR-2.03.06 | DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
DR-2.03.07 | DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Promote through dev / test / prod and release | Foundry | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
DR-2.03.08 | DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
DR-2.03.09 | DR-2.03 | AI Data Readiness | Phase 2 | Prepare | Embedding models: text-embedding-3, Cohere, BGE / E5 | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
DR-2.04.01 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Design index schema and fields | Foundry | 0 | 0 | 0 | 0 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 25
DR-2.04.02 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Deploy Azure AI Search (tier, replicas, partitions) | Foundry | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10
DR-2.04.03 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Build indexers / push pipeline from the chunk store | Foundry | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 62
DR-2.04.04 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Configure vector + BM25 hybrid search and semantic ranker | Foundry | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 31
DR-2.04.05 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Add filters (plant, document type, security) | Foundry | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 30
DR-2.04.06 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Tune relevance with test queries | Foundry | 0 | 0 | 0 | 0 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 35
DR-2.04.07 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Search quality testing | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 41
DR-2.04.08 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
DR-2.04.09 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Promote through dev / test / prod and release | Foundry | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
DR-2.04.10 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9
DR-2.04.11 | DR-2.04 | AI Data Readiness | Phase 2 | Prepare | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 19
DR-2.05.01 | DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | Define quality rules with data owners | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 50
DR-2.05.02 | DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | Implement rules (completeness, validity, freshness) in pipelines | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73
DR-2.05.03 | DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | Build data quality dashboard and alerts | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 37
DR-2.05.04 | DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | Define issue triage process | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 25
DR-2.05.05 | DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | Test the rules | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 49 | 0 | 61
DR-2.05.06 | DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 15
DR-2.05.07 | DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | Promote through dev / test / prod and release | AI Data Lake | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
DR-2.05.08 | DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10
DR-2.05.09 | DR-2.05 | AI Data Readiness | Phase 2 | Prepare | Data quality validation rules | Defect fixing and rework after testing | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 20
DR-2.06.01 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Design Fabric workspaces and capacity | AI Data Lake | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
DR-2.06.02 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Provision Fabric capacity and workspaces | AI Data Lake | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
DR-2.06.03 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Set up OneLake shortcuts to ADLS | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 25
DR-2.06.04 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Build lakehouse / warehouse models (production, quality, supply) | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 98
DR-2.06.05 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Build semantic model for the Analyst agent | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 49
DR-2.06.06 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Apply workspace security and governance | AI Data Lake | 0 | 6 | 18 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 49
DR-2.06.07 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 16
DR-2.06.08 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Promote through dev / test / prod and release | AI Data Lake | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
DR-2.06.09 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 11
DR-2.06.10 | DR-2.06 | AI Data Readiness | Phase 2 | Prepare | Fabric / OneLake for analytics | Defect fixing and rework after testing | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 22
DR-3.01.01 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Design ontology (plants, lines, equipment, products, specs, suppliers) | Foundry | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
DR-3.01.02 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Deploy Cosmos DB for Gremlin | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12
DR-3.01.03 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Build graph load pipelines from SAP / MES master data | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73
DR-3.01.04 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Implement GraphRAG indexing over documents | Foundry | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 98
DR-3.01.05 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Build graph query tools for agents (Gremlin / Cypher) | Foundry | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 61
DR-3.01.06 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Validate ontology with SMEs | Foundry | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 50
DR-3.01.07 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Graph quality testing | Foundry | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 49 | 0 | 74
DR-3.01.08 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
DR-3.01.09 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Promote through dev / test / prod and release | Foundry | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
DR-3.01.10 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 17
DR-3.01.11 | DR-3.01 | AI Data Readiness | Phase 3 | Enrich | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 33
DR-3.02.01 | DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Define entity types and linking rules | Foundry | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 0 | 30
DR-3.02.02 | DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Build LLM / AI Language extraction pipeline | Foundry | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 51
DR-3.02.03 | DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Resolve entities to master data (SAP material, equipment IDs) | Foundry | 0 | 0 | 0 | 0 | 0 | 31 | 41 | 0 | 0 | 0 | 0 | 0 | 72
DR-3.02.04 | DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Write relationships to the graph | Foundry | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 30
DR-3.02.05 | DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Precision / recall evaluation | Foundry | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 40
DR-3.02.06 | DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
DR-3.02.07 | DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Promote through dev / test / prod and release | Foundry | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
DR-3.02.08 | DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9
DR-3.02.09 | DR-3.02 | AI Data Readiness | Phase 3 | Enrich | Entity extraction and relationship linking | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18
DR-3.03.01 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Design streaming architecture and select tags | AI Data Lake | 0 | 29 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 58
DR-3.03.02 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Deploy Event Hubs with capture to ADLS | AI Data Lake | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
DR-3.03.03 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Connect AVEVA PI historian to Event Hubs | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 71
DR-3.03.04 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Build stream processing for aggregates (Stream Analytics / Fabric Real-Time) | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86
DR-3.03.05 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Set up anomaly alerting | AI Data Lake | 0 | 0 | 21 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 64
DR-3.03.06 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Throughput and lag testing | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 57
DR-3.03.07 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 22
DR-3.03.08 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Promote through dev / test / prod and release | AI Data Lake | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
DR-3.03.09 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 15
DR-3.03.10 | DR-3.03 | AI Data Readiness | Phase 3 | Enrich | Event Hubs streaming of plant telemetry | Defect fixing and rework after testing | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 30
DR-3.04.01 | DR-3.04 | AI Data Readiness | Phase 3 | Enrich | Semantic memory indexes per domain | Define knowledge domains (maintenance, quality, supply, specs) | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20
DR-3.04.02 | DR-3.04 | AI Data Readiness | Phase 3 | Enrich | Semantic memory indexes per domain | Build domain indexes and query routing | Foundry | 0 | 0 | 0 | 0 | 0 | 51 | 20 | 0 | 0 | 0 | 0 | 0 | 71
DR-3.04.03 | DR-3.04 | AI Data Readiness | Phase 3 | Enrich | Semantic memory indexes per domain | Domain-specific chunking and metadata | Foundry | 0 | 0 | 0 | 0 | 0 | 31 | 20 | 0 | 0 | 0 | 0 | 0 | 51
DR-3.04.04 | DR-3.04 | AI Data Readiness | Phase 3 | Enrich | Semantic memory indexes per domain | Retrieval tuning per domain | Foundry | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20
DR-3.04.05 | DR-3.04 | AI Data Readiness | Phase 3 | Enrich | Semantic memory indexes per domain | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
DR-3.04.06 | DR-3.04 | AI Data Readiness | Phase 3 | Enrich | Semantic memory indexes per domain | Promote through dev / test / prod and release | Foundry | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
DR-3.04.07 | DR-3.04 | AI Data Readiness | Phase 3 | Enrich | Semantic memory indexes per domain | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7
DR-3.04.08 | DR-3.04 | AI Data Readiness | Phase 3 | Enrich | Semantic memory indexes per domain | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13
DR-3.05.01 | DR-3.05 | AI Data Readiness | Phase 3 | Enrich | Row and document-level security on indexes | Map document ACLs from SharePoint / SAP to index fields | Platform Engineering | 0 | 0 | 0 | 37 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 49
DR-3.05.02 | DR-3.05 | AI Data Readiness | Phase 3 | Enrich | Row and document-level security on indexes | Implement security-trimming filters in retrieval | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49
DR-3.05.03 | DR-3.05 | AI Data Readiness | Phase 3 | Enrich | Row and document-level security on indexes | Sync ACL changes to the index | Platform Engineering | 0 | 0 | 0 | 24 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 36
DR-3.05.04 | DR-3.05 | AI Data Readiness | Phase 3 | Enrich | Row and document-level security on indexes | Security review | Platform Engineering | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
DR-3.05.05 | DR-3.05 | AI Data Readiness | Phase 3 | Enrich | Row and document-level security on indexes | Negative access testing | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 49
DR-3.05.06 | DR-3.05 | AI Data Readiness | Phase 3 | Enrich | Row and document-level security on indexes | Detailed design and design review | Platform Engineering | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
DR-3.05.07 | DR-3.05 | AI Data Readiness | Phase 3 | Enrich | Row and document-level security on indexes | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
DR-3.06.01 | DR-3.06 | AI Data Readiness | Phase 3 | Enrich | Golden test sets for evaluation | Collect real questions from plant users | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49
DR-3.06.02 | DR-3.06 | AI Data Readiness | Phase 3 | Enrich | Golden test sets for evaluation | Write expected answers and sources with SMEs | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 73
DR-3.06.03 | DR-3.06 | AI Data Readiness | Phase 3 | Enrich | Golden test sets for evaluation | Store test sets in a versioned repository | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24
DR-3.06.04 | DR-3.06 | AI Data Readiness | Phase 3 | Enrich | Golden test sets for evaluation | Wire test sets into the evaluation pipeline | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24
DR-3.06.05 | DR-3.06 | AI Data Readiness | Phase 3 | Enrich | Golden test sets for evaluation | Review coverage | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 73
DR-3.06.06 | DR-3.06 | AI Data Readiness | Phase 3 | Enrich | Golden test sets for evaluation | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 15
DR-3.06.07 | DR-3.06 | AI Data Readiness | Phase 3 | Enrich | Golden test sets for evaluation | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10
DR-4.01.01 | DR-4.01 | AI Data Readiness | Phase 4 | Sustain | Automated re-indexing and freshness checks | Define freshness SLAs per source | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8
DR-4.01.02 | DR-4.01 | AI Data Readiness | Phase 4 | Sustain | Automated re-indexing and freshness checks | Schedule incremental re-indexing | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
DR-4.01.03 | DR-4.01 | AI Data Readiness | Phase 4 | Sustain | Automated re-indexing and freshness checks | Freshness monitoring and alerts | AI Data Lake | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 32
DR-4.01.04 | DR-4.01 | AI Data Readiness | Phase 4 | Sustain | Automated re-indexing and freshness checks | Re-embed content when models change | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
DR-4.01.05 | DR-4.01 | AI Data Readiness | Phase 4 | Sustain | Automated re-indexing and freshness checks | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6
DR-4.01.06 | DR-4.01 | AI Data Readiness | Phase 4 | Sustain | Automated re-indexing and freshness checks | Promote through dev / test / prod and release | AI Data Lake | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
DR-4.01.07 | DR-4.01 | AI Data Readiness | Phase 4 | Sustain | Automated re-indexing and freshness checks | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4
DR-4.01.08 | DR-4.01 | AI Data Readiness | Phase 4 | Sustain | Automated re-indexing and freshness checks | Defect fixing and rework after testing | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8
DR-4.02.01 | DR-4.02 | AI Data Readiness | Phase 4 | Sustain | End-to-end lineage in Purview | Connect pipeline lineage (Data Factory / Fabric) to Purview | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 24
DR-4.02.02 | DR-4.02 | AI Data Readiness | Phase 4 | Sustain | End-to-end lineage in Purview | Add lineage from indexes and agents back to sources | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 33 | 0 | 0 | 0 | 0 | 41
DR-4.02.03 | DR-4.02 | AI Data Readiness | Phase 4 | Sustain | End-to-end lineage in Purview | Publish lineage views for auditors | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 33
DR-4.02.04 | DR-4.02 | AI Data Readiness | Phase 4 | Sustain | End-to-end lineage in Purview | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6
DR-4.02.05 | DR-4.02 | AI Data Readiness | Phase 4 | Sustain | End-to-end lineage in Purview | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
DR-4.03.01 | DR-4.03 | AI Data Readiness | Phase 4 | Sustain | Retention and archive policies | Define retention per data class and legal holds | AI Data Lake | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 32
DR-4.03.02 | DR-4.03 | AI Data Readiness | Phase 4 | Sustain | Retention and archive policies | Configure lifecycle and deletion policies | AI Data Lake | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
DR-4.03.03 | DR-4.03 | AI Data Readiness | Phase 4 | Sustain | Retention and archive policies | Apply retention to logs and conversation history | AI Data Lake | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16
DR-4.03.04 | DR-4.03 | AI Data Readiness | Phase 4 | Sustain | Retention and archive policies | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
DR-4.03.05 | DR-4.03 | AI Data Readiness | Phase 4 | Sustain | Retention and archive policies | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3
DR-4.04.01 | DR-4.04 | AI Data Readiness | Phase 4 | Sustain | Search index and storage backups | Automate AI Search index export / rebuild scripts | Platform Engineering | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
DR-4.04.02 | DR-4.04 | AI Data Readiness | Phase 4 | Sustain | Search index and storage backups | Set storage and database backup schedules | Platform Engineering | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
DR-4.04.03 | DR-4.04 | AI Data Readiness | Phase 4 | Sustain | Search index and storage backups | Restore test | Platform Engineering | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 24
DR-4.04.04 | DR-4.04 | AI Data Readiness | Phase 4 | Sustain | Search index and storage backups | Detailed design and design review | Platform Engineering | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
DR-4.04.05 | DR-4.04 | AI Data Readiness | Phase 4 | Sustain | Search index and storage backups | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
DR-4.04.06 | DR-4.04 | AI Data Readiness | Phase 4 | Sustain | Search index and storage backups | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
DR-4.04.07 | DR-4.04 | AI Data Readiness | Phase 4 | Sustain | Search index and storage backups | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
DR-4.05.01 | DR-4.05 | AI Data Readiness | Phase 4 | Sustain | Data drift monitoring | Define drift signals (data, embeddings, answer quality) | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12
DR-4.05.02 | DR-4.05 | AI Data Readiness | Phase 4 | Sustain | Data drift monitoring | Build drift jobs and dashboards | Foundry | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 48
DR-4.05.03 | DR-4.05 | AI Data Readiness | Phase 4 | Sustain | Data drift monitoring | Set alert thresholds and review cadence | Foundry | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 20
DR-4.05.04 | DR-4.05 | AI Data Readiness | Phase 4 | Sustain | Data drift monitoring | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
DR-4.05.05 | DR-4.05 | AI Data Readiness | Phase 4 | Sustain | Data drift monitoring | Promote through dev / test / prod and release | Foundry | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
DR-4.05.06 | DR-4.05 | AI Data Readiness | Phase 4 | Sustain | Data drift monitoring | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
DR-4.05.07 | DR-4.05 | AI Data Readiness | Phase 4 | Sustain | Data drift monitoring | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7
DR-4.06.01 | DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | Plant data readiness checklist | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 49 | 0 | 0 | 73
DR-4.06.02 | DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | Parameterize pipelines for plant codes | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 147
DR-4.06.03 | DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | Connect plant sources and validate | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 98
DR-4.06.04 | DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | Onboard local data owners | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 98 | 122
DR-4.06.05 | DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | Plant go-live sign-off | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 98
DR-4.06.06 | DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | Detailed design and design review | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 32
DR-4.06.07 | DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | Promote through dev / test / prod and release | AI Data Lake | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
DR-4.06.08 | DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | Documentation, runbook and knowledge transfer | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 22
DR-4.06.09 | DR-4.06 | AI Data Readiness | Phase 4 | Sustain | Onboard new plants and regions | Defect fixing and rework after testing | AI Data Lake | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 43
UC-1.01.01 | UC-1.01 | AI Use Cases | Phase 1 | Discover | Build use-case backlog with plant and business owners | Plan and run discovery workshops at plants and functions | Factory | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 61
UC-1.01.02 | UC-1.01 | AI Use Cases | Phase 1 | Discover | Build use-case backlog with plant and business owners | Capture pain points and ideas in a standard template | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 41
UC-1.01.03 | UC-1.01 | AI Use Cases | Phase 1 | Discover | Build use-case backlog with plant and business owners | Map ideas to agent types and architecture | Factory | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
UC-1.01.04 | UC-1.01 | AI Use Cases | Phase 1 | Discover | Build use-case backlog with plant and business owners | Consolidate the backlog | Factory | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 40
UC-1.01.05 | UC-1.01 | AI Use Cases | Phase 1 | Discover | Build use-case backlog with plant and business owners | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10
UC-1.01.06 | UC-1.01 | AI Use Cases | Phase 1 | Discover | Build use-case backlog with plant and business owners | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 7
UC-1.02.01 | UC-1.02 | AI Use Cases | Phase 1 | Discover | Rank by value and data readiness | Define scoring (value, feasibility, data readiness, risk) | Factory | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 24
UC-1.02.02 | UC-1.02 | AI Use Cases | Phase 1 | Discover | Rank by value and data readiness | Score each use case | Factory | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 24 | 0 | 0 | 56
UC-1.02.03 | UC-1.02 | AI Use Cases | Phase 1 | Discover | Rank by value and data readiness | Leadership prioritization session | Factory | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16
UC-1.02.04 | UC-1.02 | AI Use Cases | Phase 1 | Discover | Rank by value and data readiness | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6
UC-1.02.05 | UC-1.02 | AI Use Cases | Phase 1 | Discover | Rank by value and data readiness | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
UC-1.03.01 | UC-1.03 | AI Use Cases | Phase 1 | Discover | Set success KPIs and baselines | Define KPIs per use case (MTTR, OEE, scrap, time saved) | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 41
UC-1.03.02 | UC-1.03 | AI Use Cases | Phase 1 | Discover | Set success KPIs and baselines | Collect baseline data | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 40
UC-1.03.03 | UC-1.03 | AI Use Cases | Phase 1 | Discover | Set success KPIs and baselines | KPI sign-off with owners | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20
UC-1.03.04 | UC-1.03 | AI Use Cases | Phase 1 | Discover | Set success KPIs and baselines | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6
UC-1.03.05 | UC-1.03 | AI Use Cases | Phase 1 | Discover | Set success KPIs and baselines | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
UC-1.04.01 | UC-1.04 | AI Use Cases | Phase 1 | Discover | Pick pilots: Analyst agent, Spec agent | Confirm pilot plants and users | Factory | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 20
UC-1.04.02 | UC-1.04 | AI Use Cases | Phase 1 | Discover | Pick pilots: Analyst agent, Spec agent | Write pilot charters (scope, KPIs, team, success criteria) | Factory | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 28
UC-1.04.03 | UC-1.04 | AI Use Cases | Phase 1 | Discover | Pick pilots: Analyst agent, Spec agent | Solution outline for Analyst and Spec agents | Factory | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
UC-1.04.04 | UC-1.04 | AI Use Cases | Phase 1 | Discover | Pick pilots: Analyst agent, Spec agent | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
UC-1.04.05 | UC-1.04 | AI Use Cases | Phase 1 | Discover | Pick pilots: Analyst agent, Spec agent | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
UC-1.05.01 | UC-1.05 | AI Use Cases | Phase 1 | Discover | Define approval rules per use case | Classify agent actions by risk (read, recommend, act) | Factory | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 24
UC-1.05.02 | UC-1.05 | AI Use Cases | Phase 1 | Discover | Define approval rules per use case | Define approvers and thresholds | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16
UC-1.05.03 | UC-1.05 | AI Use Cases | Phase 1 | Discover | Define approval rules per use case | Security and audit requirements | Factory | 0 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
UC-1.05.04 | UC-1.05 | AI Use Cases | Phase 1 | Discover | Define approval rules per use case | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
UC-1.05.05 | UC-1.05 | AI Use Cases | Phase 1 | Discover | Define approval rules per use case | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
UC-1.06.01 | UC-1.06 | AI Use Cases | Phase 1 | Discover | Responsible-AI review | Complete Responsible-AI impact assessment | Foundry | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 24
UC-1.06.02 | UC-1.06 | AI Use Cases | Phase 1 | Discover | Responsible-AI review | Privacy and security review | Foundry | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
UC-1.06.03 | UC-1.06 | AI Use Cases | Phase 1 | Discover | Responsible-AI review | Agree mitigations and sign-off | Foundry | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 24
UC-1.06.04 | UC-1.06 | AI Use Cases | Phase 1 | Discover | Responsible-AI review | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
UC-1.06.05 | UC-1.06 | AI Use Cases | Phase 1 | Discover | Responsible-AI review | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
UC-2.01.01 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Gather question catalog and metric definitions | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49
UC-2.01.02 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Prepare semantic model and metadata for NL-to-SQL / DAX | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73
UC-2.01.03 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Build NL-to-SQL tool with schema grounding | Factory | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 98
UC-2.01.04 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Add result explanation and chart generation | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 24 | 0 | 0 | 0 | 73
UC-2.01.05 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Add guardrails (row limits, read-only, row-level security) | Factory | 0 | 0 | 0 | 0 | 0 | 37 | 24 | 0 | 0 | 0 | 0 | 0 | 61
UC-2.01.06 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Integrate with orchestrator and memory | Factory | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 24 | 0 | 0 | 0 | 61
UC-2.01.07 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Accuracy testing on the golden set | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 24 | 98 | 0 | 170
UC-2.01.08 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
UC-2.01.09 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Promote through dev / test / prod and release | Factory | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
UC-2.01.10 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24
UC-2.01.11 | UC-2.01 | AI Use Cases | Phase 2 | Pilot | Analyst agent: plain-English questions over Fabric / SQL | Defect fixing and rework after testing | Factory | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 47
UC-2.02.01 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Collect spec and SOP corpus with document owners | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 37 | 0 | 0 | 61
UC-2.02.02 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Build retrieval chain with citations | Factory | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73
UC-2.02.03 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Handle revisions and plant-specific variants | Factory | 0 | 0 | 0 | 0 | 0 | 37 | 24 | 0 | 0 | 0 | 0 | 0 | 61
UC-2.02.04 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Format answers with source links | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 48
UC-2.02.05 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Integrate with the orchestrator | Factory | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 24 | 0 | 0 | 0 | 61
UC-2.02.06 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Accuracy testing with SMEs | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 37 | 98 | 0 | 159
UC-2.02.07 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
UC-2.02.08 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Promote through dev / test / prod and release | Factory | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
UC-2.02.09 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 19
UC-2.02.10 | UC-2.02 | AI Use Cases | Phase 2 | Pilot | Spec agent: RAG over specs and SOPs | Defect fixing and rework after testing | Factory | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 37
UC-2.03.01 | UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Register Teams app / Copilot agent | Factory | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 24
UC-2.03.02 | UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Build bot with adaptive cards and SSO | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 49
UC-2.03.03 | UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Connect to orchestrator API through APIM | Factory | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 32
UC-2.03.04 | UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Admin approval and publish to Teams catalog | Factory | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 24
UC-2.03.05 | UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Test across desktop, web and mobile | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 33
UC-2.03.06 | UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
UC-2.03.07 | UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Promote through dev / test / prod and release | Factory | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
UC-2.03.08 | UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7
UC-2.03.09 | UC-2.03 | AI Use Cases | Phase 2 | Pilot | Deliver in Teams / Copilot | Defect fixing and rework after testing | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13
UC-2.04.01 | UC-2.04 | AI Use Cases | Phase 2 | Pilot | Pilot at one or two plants | Pilot plan and schedule | Factory | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 48
UC-2.04.02 | UC-2.04 | AI Use Cases | Phase 2 | Pilot | Pilot at one or two plants | Train pilot users | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 73
UC-2.04.03 | UC-2.04 | AI Use Cases | Phase 2 | Pilot | Pilot at one or two plants | Hypercare support during the pilot | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 49 | 0 | 0 | 98
UC-2.04.04 | UC-2.04 | AI Use Cases | Phase 2 | Pilot | Pilot at one or two plants | Weekly pilot reviews | Factory | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 24 | 97
UC-2.04.05 | UC-2.04 | AI Use Cases | Phase 2 | Pilot | Pilot at one or two plants | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 19
UC-2.04.06 | UC-2.04 | AI Use Cases | Phase 2 | Pilot | Pilot at one or two plants | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 13
UC-2.05.01 | UC-2.05 | AI Use Cases | Phase 2 | Pilot | Collect user feedback and evaluations | Capture in-app ratings and comments | Factory | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
UC-2.05.02 | UC-2.05 | AI Use Cases | Phase 2 | Pilot | Collect user feedback and evaluations | Run user surveys and interviews | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 33
UC-2.05.03 | UC-2.05 | AI Use Cases | Phase 2 | Pilot | Collect user feedback and evaluations | Analyse feedback and evaluation results | Factory | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 16 | 0 | 48
UC-2.05.04 | UC-2.05 | AI Use Cases | Phase 2 | Pilot | Collect user feedback and evaluations | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6
UC-2.05.05 | UC-2.05 | AI Use Cases | Phase 2 | Pilot | Collect user feedback and evaluations | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
UC-2.06.01 | UC-2.06 | AI Use Cases | Phase 2 | Pilot | Go / no-go against KPIs | Compare KPIs to baseline | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12
UC-2.06.02 | UC-2.06 | AI Use Cases | Phase 2 | Pilot | Go / no-go against KPIs | Write pilot report and recommendation | Factory | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 24
UC-2.06.03 | UC-2.06 | AI Use Cases | Phase 2 | Pilot | Go / no-go against KPIs | Steering committee decision | Factory | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
UC-2.06.04 | UC-2.06 | AI Use Cases | Phase 2 | Pilot | Go / no-go against KPIs | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
UC-3.01.01 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Gather requirements with maintenance teams | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49
UC-3.01.02 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Build AVEVA PI tool: tag lookup, trends, anomalies | Factory | 0 | 0 | 0 | 0 | 0 | 73 | 49 | 0 | 0 | 0 | 0 | 0 | 122
UC-3.01.03 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Build SAP PM tool: work orders, history, notifications | Factory | 0 | 0 | 0 | 0 | 0 | 61 | 49 | 0 | 0 | 0 | 0 | 0 | 110
UC-3.01.04 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | RAG over equipment manuals and failure history | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 0 | 0 | 0 | 73
UC-3.01.05 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Root-cause and recommended-action logic | Factory | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73
UC-3.01.06 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Draft work orders with approval step | Factory | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 49 | 0 | 0 | 0 | 86
UC-3.01.07 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Surface agent in Teams / Plant Ops app | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24
UC-3.01.08 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | SME and functional testing | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 49 | 98 | 0 | 171
UC-3.01.09 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43
UC-3.01.10 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Promote through dev / test / prod and release | Factory | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
UC-3.01.11 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 28
UC-3.01.12 | UC-3.01 | AI Use Cases | Phase 3 | Expand | Maintenance agent: AVEVA PI signals + work orders | Defect fixing and rework after testing | Factory | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 57
UC-3.02.01 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Gather requirements with quality teams | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49
UC-3.02.02 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Connect SPC, inspection and defect data | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73
UC-3.02.03 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Defect triage and pattern detection | Factory | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 98
UC-3.02.04 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | RAG over quality procedures and NCRs | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 0 | 0 | 0 | 73
UC-3.02.05 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Draft NCR / CAPA with approval step | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 37 | 0 | 0 | 0 | 86
UC-3.02.06 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Surface agent in user channels | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12
UC-3.02.07 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Testing with quality engineers | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 49 | 98 | 0 | 220
UC-3.02.08 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
UC-3.02.09 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Promote through dev / test / prod and release | Factory | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
UC-3.02.10 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24
UC-3.02.11 | UC-3.02 | AI Use Cases | Phase 3 | Expand | Quality agent: defect and SPC triage | Defect fixing and rework after testing | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49
UC-3.03.01 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Gather requirements with supply chain | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49
UC-3.03.02 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Build SAP MM / Coupa tools: inventory, POs, supplier data | Factory | 0 | 0 | 0 | 0 | 0 | 73 | 73 | 0 | 0 | 0 | 0 | 0 | 146
UC-3.03.03 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Supply risk signals and scoring | Factory | 0 | 0 | 0 | 0 | 0 | 73 | 24 | 0 | 0 | 0 | 0 | 0 | 97
UC-3.03.04 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Alerts and recommended actions | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 24 | 0 | 0 | 0 | 73
UC-3.03.05 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Surface agent in user channels | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24
UC-3.03.06 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Testing with planners | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 49 | 98 | 0 | 220
UC-3.03.07 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
UC-3.03.08 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Promote through dev / test / prod and release | Factory | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
UC-3.03.09 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24
UC-3.03.10 | UC-3.03 | AI Use Cases | Phase 3 | Expand | Supply agent: SAP / Coupa supply risk | Defect fixing and rework after testing | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49
UC-3.04.01 | UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Design multi-agent coordination (routing, handoff, shared context) | Foundry | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
UC-3.04.02 | UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Build intent router and task planner | Foundry | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 98
UC-3.04.03 | UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Implement handoff protocol with specialist agents | Foundry | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73
UC-3.04.04 | UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Add conflict and loop safeguards | Foundry | 0 | 0 | 0 | 0 | 24 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 73
UC-3.04.05 | UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Multi-agent scenario testing | Foundry | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 73 | 0 | 97
UC-3.04.06 | UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
UC-3.04.07 | UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Promote through dev / test / prod and release | Foundry | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
UC-3.04.08 | UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
UC-3.04.09 | UC-3.04 | AI Use Cases | Phase 3 | Expand | Planner agent coordinating other agents | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 31
UC-3.05.01 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | UX research and wireframes | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 41
UC-3.05.02 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | UI design system and screens | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 61
UC-3.05.03 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | Build web app (chat, dashboards, approvals) | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 163
UC-3.05.04 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | Build mobile app (React Native / PWA) | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 122
UC-3.05.05 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | SSO, device policies and offline handling | Factory | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 61
UC-3.05.06 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | Accessibility and usability review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 40
UC-3.05.07 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | Functional and device testing | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 102
UC-3.05.08 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
UC-3.05.09 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | Promote through dev / test / prod and release | Factory | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
UC-3.05.10 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24
UC-3.05.11 | UC-3.05 | AI Use Cases | Phase 3 | Expand | Plant Ops web and mobile apps | Defect fixing and rework after testing | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 47
UC-3.06.01 | UC-3.06 | AI Use Cases | Phase 3 | Expand | Roll out to more plants | Rollout wave plan | Factory | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 66
UC-3.06.02 | UC-3.06 | AI Use Cases | Phase 3 | Expand | Roll out to more plants | Plant readiness assessments | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 65
UC-3.06.03 | UC-3.06 | AI Use Cases | Phase 3 | Expand | Roll out to more plants | Train-the-trainer and user training | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 130
UC-3.06.04 | UC-3.06 | AI Use Cases | Phase 3 | Expand | Roll out to more plants | Go-live support | Factory | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 33 | 0 | 33 | 131
UC-3.06.05 | UC-3.06 | AI Use Cases | Phase 3 | Expand | Roll out to more plants | Rollout communications | Factory | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 66
UC-3.06.06 | UC-3.06 | AI Use Cases | Phase 3 | Expand | Roll out to more plants | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 27
UC-3.06.07 | UC-3.06 | AI Use Cases | Phase 3 | Expand | Roll out to more plants | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18
UC-4.01.01 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Gather requirements with sustainability team (energy, carbon, water, recycled content) | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 49
UC-4.01.02 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Connect energy meters and utility data | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 73
UC-4.01.03 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Build emission-factor and calculation tools | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 24 | 0 | 0 | 0 | 0 | 0 | 73
UC-4.01.04 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Draft ESG and customer sustainability reports | Factory | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73
UC-4.01.05 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Detect energy-saving opportunities | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49
UC-4.01.06 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Validate numbers with sustainability team | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 49 | 73 | 0 | 170
UC-4.01.07 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
UC-4.01.08 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Promote through dev / test / prod and release | Factory | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
UC-4.01.09 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20
UC-4.01.10 | UC-4.01 | AI Use Cases | Phase 4 | Industrialize | Sustainability agent: energy and carbon reporting | Defect fixing and rework after testing | Factory | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 39
UC-4.02.01 | UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Define partner use cases and API contracts | Platform Engineering | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 30
UC-4.02.02 | UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Build APIs and publish in the APIM developer portal | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 0 | 0 | 81
UC-4.02.03 | UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Partner onboarding: OAuth clients, keys, quotas | Platform Engineering | 0 | 0 | 26 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46
UC-4.02.04 | UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Security testing and penetration test | Platform Engineering | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
UC-4.02.05 | UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Integration testing with a first partner | Platform Engineering | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 41 | 0 | 76
UC-4.02.06 | UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Detailed design and design review | Platform Engineering | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
UC-4.02.07 | UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Promote through dev / test / prod and release | Platform Engineering | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
UC-4.02.08 | UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Documentation, runbook and knowledge transfer | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11
UC-4.02.09 | UC-4.02 | AI Use Cases | Phase 4 | Industrialize | Partner APIs for customers and suppliers | Defect fixing and rework after testing | Platform Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 21
UC-4.03.01 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Select write actions (create notification, work order, PO change) | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 43
UC-4.03.02 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Build write tools via SAP APIs / BAPIs | Factory | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 86 | 0 | 0 | 0 | 115
UC-4.03.03 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Enforce approvals and dual control | Factory | 0 | 0 | 0 | 29 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 86
UC-4.03.04 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Idempotency, rollback and audit logging | Factory | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 29 | 0 | 0 | 0 | 86
UC-4.03.05 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Security review | Factory | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
UC-4.03.06 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Testing in SAP QA system | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 114 | 0 | 128
UC-4.03.07 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
UC-4.03.08 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Promote through dev / test / prod and release | Factory | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
UC-4.03.09 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 19
UC-4.03.10 | UC-4.03 | AI Use Cases | Phase 4 | Industrialize | Approved write-back actions into SAP | Defect fixing and rework after testing | Factory | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 39
UC-4.04.01 | UC-4.04 | AI Use Cases | Phase 4 | Industrialize | Reusable agent templates | Extract common patterns from built agents | Foundry | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UC-4.04.02 | UC-4.04 | AI Use Cases | Phase 4 | Industrialize | Reusable agent templates | Build template repository (agent, RAG, tool, evaluation) | Foundry | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 49
UC-4.04.03 | UC-4.04 | AI Use Cases | Phase 4 | Industrialize | Reusable agent templates | Build scaffolding pipeline for new agents | Foundry | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 33
UC-4.04.04 | UC-4.04 | AI Use Cases | Phase 4 | Industrialize | Reusable agent templates | Template documentation | Foundry | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
UC-4.04.05 | UC-4.04 | AI Use Cases | Phase 4 | Industrialize | Reusable agent templates | Detailed design and design review | Foundry | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
UC-4.04.06 | UC-4.04 | AI Use Cases | Phase 4 | Industrialize | Reusable agent templates | Promote through dev / test / prod and release | Foundry | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
UC-4.04.07 | UC-4.04 | AI Use Cases | Phase 4 | Industrialize | Reusable agent templates | Documentation, runbook and knowledge transfer | Foundry | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
UC-4.04.08 | UC-4.04 | AI Use Cases | Phase 4 | Industrialize | Reusable agent templates | Defect fixing and rework after testing | Foundry | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11
UC-4.05.01 | UC-4.05 | AI Use Cases | Phase 4 | Industrialize | Adoption tracking and change management | Define adoption metrics | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24
UC-4.05.02 | UC-4.05 | AI Use Cases | Phase 4 | Industrialize | Adoption tracking and change management | Build adoption dashboard | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 48
UC-4.05.03 | UC-4.05 | AI Use Cases | Phase 4 | Industrialize | Adoption tracking and change management | Build change network of plant champions | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 49
UC-4.05.04 | UC-4.05 | AI Use Cases | Phase 4 | Industrialize | Adoption tracking and change management | Ongoing training and communications | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 73
UC-4.05.05 | UC-4.05 | AI Use Cases | Phase 4 | Industrialize | Adoption tracking and change management | Adoption reviews | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24
UC-4.05.06 | UC-4.05 | AI Use Cases | Phase 4 | Industrialize | Adoption tracking and change management | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 13
UC-4.05.07 | UC-4.05 | AI Use Cases | Phase 4 | Industrialize | Adoption tracking and change management | Documentation, runbook and knowledge transfer | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9
UC-4.06.01 | UC-4.06 | AI Use Cases | Phase 4 | Industrialize | Retire or refresh low-value agents | Quarterly agent value review | Factory | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 18
UC-4.06.02 | UC-4.06 | AI Use Cases | Phase 4 | Industrialize | Retire or refresh low-value agents | Decide refresh or retire per agent | Factory | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
UC-4.06.03 | UC-4.06 | AI Use Cases | Phase 4 | Industrialize | Retire or refresh low-value agents | Decommission or upgrade plan | Factory | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 18
UC-4.06.04 | UC-4.06 | AI Use Cases | Phase 4 | Industrialize | Retire or refresh low-value agents | Detailed design and design review | Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
PM-1.01.01 | PM-1.01 | Program Management | Phase 1 | Mobilize | Program management, planning, status and steering (added) | Phase plan and schedule | All teams | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
PM-1.01.02 | PM-1.01 | Program Management | Phase 1 | Mobilize | Program management, planning, status and steering (added) | Weekly status reporting and RAID log | All teams | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122
PM-1.01.03 | PM-1.01 | Program Management | Phase 1 | Mobilize | Program management, planning, status and steering (added) | Steering committee preparation | All teams | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
PM-1.01.04 | PM-1.01 | Program Management | Phase 1 | Mobilize | Program management, planning, status and steering (added) | Architecture design authority reviews | All teams | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
PM-1.01.05 | PM-1.01 | Program Management | Phase 1 | Mobilize | Program management, planning, status and steering (added) | Resource and vendor coordination | All teams | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98
PM-2.01.01 | PM-2.01 | Program Management | Phase 2 | Build | Program management, planning, status and steering (added) | Phase plan and schedule | All teams | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
PM-2.01.02 | PM-2.01 | Program Management | Phase 2 | Build | Program management, planning, status and steering (added) | Weekly status reporting and RAID log | All teams | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122
PM-2.01.03 | PM-2.01 | Program Management | Phase 2 | Build | Program management, planning, status and steering (added) | Steering committee preparation | All teams | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
PM-2.01.04 | PM-2.01 | Program Management | Phase 2 | Build | Program management, planning, status and steering (added) | Architecture design authority reviews | All teams | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
PM-2.01.05 | PM-2.01 | Program Management | Phase 2 | Build | Program management, planning, status and steering (added) | Resource and vendor coordination | All teams | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98
PM-3.01.01 | PM-3.01 | Program Management | Phase 3 | Scale | Program management, planning, status and steering (added) | Phase plan and schedule | All teams | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
PM-3.01.02 | PM-3.01 | Program Management | Phase 3 | Scale | Program management, planning, status and steering (added) | Weekly status reporting and RAID log | All teams | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122
PM-3.01.03 | PM-3.01 | Program Management | Phase 3 | Scale | Program management, planning, status and steering (added) | Steering committee preparation | All teams | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
PM-3.01.04 | PM-3.01 | Program Management | Phase 3 | Scale | Program management, planning, status and steering (added) | Architecture design authority reviews | All teams | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
PM-3.01.05 | PM-3.01 | Program Management | Phase 3 | Scale | Program management, planning, status and steering (added) | Resource and vendor coordination | All teams | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98
PM-4.01.01 | PM-4.01 | Program Management | Phase 4 | Hand-over | Program management, planning, status and steering (added) | Phase plan and schedule | All teams | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
PM-4.01.02 | PM-4.01 | Program Management | Phase 4 | Hand-over | Program management, planning, status and steering (added) | Weekly status reporting and RAID log | All teams | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122
PM-4.01.03 | PM-4.01 | Program Management | Phase 4 | Hand-over | Program management, planning, status and steering (added) | Steering committee preparation | All teams | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
PM-4.01.04 | PM-4.01 | Program Management | Phase 4 | Hand-over | Program management, planning, status and steering (added) | Architecture design authority reviews | All teams | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
PM-4.01.05 | PM-4.01 | Program Management | Phase 4 | Hand-over | Program management, planning, status and steering (added) | Resource and vendor coordination | All teams | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98
PS-3.07.01 | PS-3.07 | AI Platform Setup | Phase 3 | Scale | Platform security assessment and penetration test (added) | Threat-model the end-to-end platform | Platform Engineering | 0 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
PS-3.07.02 | PS-3.07 | AI Platform Setup | Phase 3 | Scale | Platform security assessment and penetration test (added) | Scope and run external penetration test | Platform Engineering | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
PS-3.07.03 | PS-3.07 | AI Platform Setup | Phase 3 | Scale | Platform security assessment and penetration test (added) | Remediate findings across platform, agents and apps | Platform Engineering | 0 | 0 | 24 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 56
PS-3.07.04 | PS-3.07 | AI Platform Setup | Phase 3 | Scale | Platform security assessment and penetration test (added) | Retest and close findings | Platform Engineering | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 24
PS-4.07.01 | PS-4.07 | AI Platform Setup | Phase 4 | Optimize | Run handover: SRE, ServiceNow and support model (added) | Define L1 / L2 / L3 support model and SLAs | Platform Engineering | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
PS-4.07.02 | PS-4.07 | AI Platform Setup | Phase 4 | Optimize | Run handover: SRE, ServiceNow and support model (added) | Integrate alerts and incidents with ServiceNow | Platform Engineering | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 40
PS-4.07.03 | PS-4.07 | AI Platform Setup | Phase 4 | Optimize | Run handover: SRE, ServiceNow and support model (added) | Runbooks and knowledge-transfer sessions to run team | Platform Engineering | 0 | 0 | 24 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 48
PS-4.07.04 | PS-4.07 | AI Platform Setup | Phase 4 | Optimize | Run handover: SRE, ServiceNow and support model (added) | Operational readiness review | Platform Engineering | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 16
PS-3.08.01 | PS-3.08 | AI Platform Setup | Phase 3 | Scale | Developer enablement and Foundry training (added) | Build training curriculum for agent developers | Foundry | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 32
PS-3.08.02 | PS-3.08 | AI Platform Setup | Phase 3 | Scale | Developer enablement and Foundry training (added) | Hands-on labs using Foundry templates | Foundry | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24
PS-3.08.03 | PS-3.08 | AI Platform Setup | Phase 3 | Scale | Developer enablement and Foundry training (added) | Weekly office hours and design clinics | Foundry | 0 | 0 | 0 | 0 | 8 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 32
PS-3.08.04 | PS-3.08 | AI Platform Setup | Phase 3 | Scale | Developer enablement and Foundry training (added) | Enablement communications | Foundry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
UC-2.07.01 | UC-2.07 | AI Use Cases | Phase 2 | Pilot | Hypercare and production support for live agents (added) | L2 support for live agents (monitor, triage, answer users) | Factory | 0 | 0 | 0 | 0 | 0 | 41 | 16 | 0 | 16 | 0 | 0 | 0 | 73
UC-2.07.02 | UC-2.07 | AI Use Cases | Phase 2 | Pilot | Hypercare and production support for live agents (added) | Fix production defects and tune prompts / retrieval | Factory | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 16 | 0 | 16 | 0 | 56
UC-2.07.03 | UC-2.07 | AI Use Cases | Phase 2 | Pilot | Hypercare and production support for live agents (added) | Weekly operations and quality review | Factory | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16
UC-3.07.01 | UC-3.07 | AI Use Cases | Phase 3 | Expand | Hypercare and production support for live agents (added) | L2 support for live agents (monitor, triage, answer users) | Factory | 0 | 0 | 0 | 0 | 0 | 61 | 24 | 0 | 24 | 0 | 0 | 0 | 109
UC-3.07.02 | UC-3.07 | AI Use Cases | Phase 3 | Expand | Hypercare and production support for live agents (added) | Fix production defects and tune prompts / retrieval | Factory | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 24 | 0 | 24 | 0 | 85
UC-3.07.03 | UC-3.07 | AI Use Cases | Phase 3 | Expand | Hypercare and production support for live agents (added) | Weekly operations and quality review | Factory | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 24
UC-4.07.01 | UC-4.07 | AI Use Cases | Phase 4 | Industrialize | Hypercare and production support for live agents (added) | L2 support for live agents (monitor, triage, answer users) | Factory | 0 | 0 | 0 | 0 | 0 | 81 | 33 | 0 | 33 | 0 | 0 | 0 | 147
UC-4.07.02 | UC-4.07 | AI Use Cases | Phase 4 | Industrialize | Hypercare and production support for live agents (added) | Fix production defects and tune prompts / retrieval | Factory | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 33 | 0 | 33 | 0 | 115
UC-4.07.03 | UC-4.07 | AI Use Cases | Phase 4 | Industrialize | Hypercare and production support for live agents (added) | Weekly operations and quality review | Factory | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 32
Total hours | [7 empty] | 1734 | 692 | 2649 | 1027 | 1358 | 5748 | 2935 | 754 | 2031 | 2225 | 2259 | 588 | 24000

## Estimation Basis
Estimation basis: what drives the hours for each item
Hours and task counts are live from Activity Hours.
ID | Track | Phase | Item | Owner team | Scope driver | Hours | Tasks
PS-1.01 | AI Platform Setup | Phase 1 | Azure landing zone, subscriptions, VNets, private endpoints | Platform Engineering | 3 environments x 2 regions; fit into Ball's existing hub, firewall and change process; ExpressRoute to several sites | 334 | 12
PS-1.02 | AI Platform Setup | Phase 1 | Entra ID SSO, MFA / PIM, conditional access | Platform Engineering | Existing tenant and CAB approvals; web, mobile, Teams and partner clients | 145 | 8
PS-1.03 | AI Platform Setup | Phase 1 | RBAC / ABAC roles and fine-grained permissions | Platform Engineering | Attributes for plant, region and function across many plants; agent and tool permissions | 133 | 7
PS-1.04 | AI Platform Setup | Phase 1 | Key Vault, TDE / TLS encryption | Platform Engineering | Customer-managed keys and rotation automation in 3 environments | 88 | 7
PS-1.05 | AI Platform Setup | Phase 1 | Front Door + API Management gateway | Platform Engineering | Multi-region APIM with per-product policies and WAF tuning | 211 | 10
PS-1.06 | AI Platform Setup | Phase 1 | Terraform / Bicep IaC, GitHub Actions CI/CD | Platform Engineering | Module library for 15+ Azure services, 3 environments, policy-as-code | 299 | 11
PS-1.07 | AI Platform Setup | Phase 1 | ACR, AKS and Container Apps | Platform Engineering | Production-grade clusters in 2 regions plus GPU pool for self-hosted models | 222 | 11
PS-2.01 | AI Platform Setup | Phase 2 | AI Foundry hub and projects | Foundry | Hub and projects per domain and environment, managed network | 157 | 10
PS-2.02 | AI Platform Setup | Phase 2 | AI gateway / model router: Azure OpenAI, Anthropic, Gemini, self-hosted | Foundry | 4 model providers, quotas per team, multi-region failover, self-hosted models | 387 | 12
PS-2.03 | AI Platform Setup | Phase 2 | Agent orchestrator: Foundry Agent Service, Semantic Kernel, LangGraph | Foundry | Shared framework every agent depends on; production hardening and patterns | 657 | 12
PS-2.04 | AI Platform Setup | Phase 2 | Memory layer: working, conversation, long-term | Foundry | Several memory types, PII isolation, retention rules | 275 | 11
PS-2.05 | AI Platform Setup | Phase 2 | Prompt library, templates, versioning | Foundry | Templates for 7 agent types with approval workflow | 118 | 9
PS-2.06 | AI Platform Setup | Phase 2 | Content Safety and Prompt Shields | Foundry | Policies and red-teaming per agent type | 198 | 10
PS-3.01 | AI Platform Setup | Phase 3 | Redis semantic, embedding and response caches | Platform Engineering | Three cache types in 2 regions | 148 | 10
PS-3.02 | AI Platform Setup | Phase 3 | Service Bus, Event Grid, Durable Functions | Platform Engineering | Async workflows for long-running and approval-based agents | 261 | 11
PS-3.03 | AI Platform Setup | Phase 3 | Tool and MCP registry with permissions | Foundry | 6 enterprise systems; each MCP server needs auth, paging, errors, write controls | 488 | 11
PS-3.04 | AI Platform Setup | Phase 3 | Human-in-the-loop review and escalation | Foundry | Approval flows across Teams and web for every action-taking agent | 388 | 11
PS-3.05 | AI Platform Setup | Phase 3 | Admin panel: agent registry, users, policies | Platform Engineering | Full internal application with role-based screens | 477 | 11
PS-3.06 | AI Platform Setup | Phase 3 | Tracing in Azure Monitor and App Insights | Platform Engineering | End-to-end correlation across gateway, agents, tools and plants | 149 | 9
PS-4.01 | AI Platform Setup | Phase 4 | Evaluation: AI eval SDK, RAGAS, hallucination checks | Foundry | Offline and online evaluation for every agent, CI/CD gates | 359 | 11
PS-4.02 | AI Platform Setup | Phase 4 | Token usage tracking and budgets per agent | Foundry | Chargeback by team, agent and plant | 119 | 9
PS-4.03 | AI Platform Setup | Phase 4 | A/B testing of prompts and models | Foundry | Experiment framework reused by all agents | 159 | 9
PS-4.04 | AI Platform Setup | Phase 4 | Backup, DR, point-in-time recovery | Platform Engineering | Cross-region DR design and drills | 240 | 11
PS-4.05 | AI Platform Setup | Phase 4 | SLO alerting to Teams / PagerDuty | Platform Engineering | SLOs for every service and agent; on-call setup | 86 | 9
PS-4.06 | AI Platform Setup | Phase 4 | On-prem MES gateway, plant to cloud | Platform Engineering | OT network variation across 5 plants; strict OT security reviews | 558 | 11
DR-1.01 | AI Data Readiness | Phase 1 | Inventory sources: SAP S/4HANA, MES, AVEVA PI, SharePoint, Coupa | AI Data Lake | 5 source systems with plant-by-plant variation | 218 | 6
DR-1.02 | AI Data Readiness | Phase 1 | Classify data and tag PII | AI Data Lake | Large estate of SAP, SharePoint and plant data | 156 | 7
DR-1.03 | AI Data Readiness | Phase 1 | Name data owners and stewards | AI Data Lake | Owners per domain and per region | 88 | 6
DR-1.04 | AI Data Readiness | Phase 1 | ADLS Gen2 / Blob storage tiers | Platform Engineering | Zones and ACLs in 3 environments | 98 | 9
DR-1.05 | AI Data Readiness | Phase 1 | Azure SQL, PostgreSQL + pgvector | Platform Engineering | HA databases in 3 environments | 119 | 9
DR-1.06 | AI Data Readiness | Phase 1 | Catalog and lineage baseline in Purview | AI Data Lake | Scans and glossary across all sources | 179 | 7
DR-2.01 | AI Data Readiness | Phase 2 | Pipelines from SAP, MES and file shares | AI Data Lake | SAP extraction across several modules (PM, QM, MM, PP, SD); MES variation by plant | 732 | 12
DR-2.02 | AI Data Readiness | Phase 2 | Document ingestion: OCR, parsing, chunking | Foundry | Scanned, multi-language and drawing-heavy documents at scale | 361 | 11
DR-2.03 | AI Data Readiness | Phase 2 | Embedding models: text-embedding-3, Cohere, BGE / E5 | Foundry | Benchmarking on Ball content; re-embedding strategy | 119 | 9
DR-2.04 | AI Data Readiness | Phase 2 | Hybrid index in Azure AI Search (vector + BM25 + ranker) | Foundry | Several indexes, filters and relevance tuning per domain | 285 | 11
DR-2.05 | AI Data Readiness | Phase 2 | Data quality validation rules | AI Data Lake | Rules for every critical table and source | 301 | 9
DR-2.06 | AI Data Readiness | Phase 2 | Fabric / OneLake for analytics | AI Data Lake | Analytical models for production, quality, supply and energy | 330 | 10
DR-3.01 | AI Data Readiness | Phase 3 | Knowledge graph: Cosmos DB Gremlin, GraphRAG | Foundry | Ontology across plants, equipment, products and suppliers | 509 | 11
DR-3.02 | AI Data Readiness | Phase 3 | Entity extraction and relationship linking | Foundry | Matching to SAP master data with low tolerance for errors | 273 | 9
DR-3.03 | AI Data Readiness | Phase 3 | Event Hubs streaming of plant telemetry | AI Data Lake | AVEVA PI historians at several plants; high data volume | 454 | 10
DR-3.04 | AI Data Readiness | Phase 3 | Semantic memory indexes per domain | Foundry | 4 domain indexes with routing | 199 | 8
DR-3.05 | AI Data Readiness | Phase 3 | Row and document-level security on indexes | Platform Engineering | ACL sync from SharePoint and SAP; strict negative testing | 242 | 7
DR-3.06 | AI Data Readiness | Phase 3 | Golden test sets for evaluation | Factory | Test sets for each agent and domain, built with SMEs | 268 | 7
DR-4.01 | AI Data Readiness | Phase 4 | Automated re-indexing and freshness checks | AI Data Lake | Freshness for all sources | 118 | 8
DR-4.02 | AI Data Readiness | Phase 4 | End-to-end lineage in Purview | AI Data Lake | Lineage across pipelines, indexes and agents | 108 | 5
DR-4.03 | AI Data Readiness | Phase 4 | Retention and archive policies | AI Data Lake | Policies per data class and region | 71 | 5
DR-4.04 | AI Data Readiness | Phase 4 | Search index and storage backups | Platform Engineering | Backups in 2 regions | 79 | 7
DR-4.05 | AI Data Readiness | Phase 4 | Data drift monitoring | Foundry | Drift checks for every agent | 98 | 7
DR-4.06 | AI Data Readiness | Phase 4 | Onboard new plants and regions | AI Data Lake | 15 additional plants in Phase 4, each with its own systems and owners | 657 | 9
UC-1.01 | AI Use Cases | Phase 1 | Build use-case backlog with plant and business owners | Factory | Workshops across regions and functions | 179 | 6
UC-1.02 | AI Use Cases | Phase 1 | Rank by value and data readiness | Factory | Scoring across a large backlog | 106 | 5
UC-1.03 | AI Use Cases | Phase 1 | Set success KPIs and baselines | Factory | Baselines per agent and plant | 111 | 5
UC-1.04 | AI Use Cases | Phase 1 | Pick pilots: Analyst agent, Spec agent | Factory | Charters for 2 pilots at 2 plants | 71 | 5
UC-1.05 | AI Use Cases | Phase 1 | Define approval rules per use case | Factory | Rules for each action-taking agent | 71 | 5
UC-1.06 | AI Use Cases | Phase 1 | Responsible-AI review | Foundry | Assessment per agent | 71 | 5
UC-2.01 | AI Use Cases | Phase 2 | Analyst agent: plain-English questions over Fabric / SQL | Factory | Enterprise semantic model; high accuracy bar for numbers | 715 | 11
UC-2.02 | AI Use Cases | Phase 2 | Spec agent: RAG over specs and SOPs | Factory | Large spec / SOP corpus with revisions and plant variants | 566 | 10
UC-2.03 | AI Use Cases | Phase 2 | Deliver in Teams / Copilot | Factory | Teams and Copilot channels, enterprise app approval | 199 | 9
UC-2.04 | AI Use Cases | Phase 2 | Pilot at one or two plants | Factory | 2 plants, shifts and multiple user groups | 348 | 6
UC-2.05 | AI Use Cases | Phase 2 | Collect user feedback and evaluations | Factory | Feedback across pilot plants | 107 | 5
UC-2.06 | AI Use Cases | Phase 2 | Go / no-go against KPIs | Factory | Formal steering decision | 51 | 4
UC-3.01 | AI Use Cases | Phase 3 | Maintenance agent: AVEVA PI signals + work orders | Factory | PI and SAP PM integration; safety-relevant recommendations | 864 | 12
UC-3.02 | AI Use Cases | Phase 3 | Quality agent: defect and SPC triage | Factory | SPC, inspection and NCR / CAPA integration | 745 | 11
UC-3.03 | AI Use Cases | Phase 3 | Supply agent: SAP / Coupa supply risk | Factory | SAP MM and Coupa integration; risk scoring | 743 | 10
UC-3.04 | AI Use Cases | Phase 3 | Planner agent coordinating other agents | Foundry | Coordination across all specialist agents | 477 | 9
UC-3.05 | AI Use Cases | Phase 3 | Plant Ops web and mobile apps | Factory | Web and mobile apps with offline use on the plant floor | 720 | 11
UC-3.06 | AI Use Cases | Phase 3 | Roll out to more plants | Factory | Rollout to 5 plants in waves | 503 | 7
UC-4.01 | AI Use Cases | Phase 4 | Sustainability agent: energy and carbon reporting | Factory | Energy and carbon data across plants; audit-grade numbers | 595 | 10
UC-4.02 | AI Use Cases | Phase 4 | Partner APIs for customers and suppliers | Platform Engineering | External security, onboarding and support | 323 | 9
UC-4.03 | AI Use Cases | Phase 4 | Approved write-back actions into SAP | Factory | SOX / ITGC controls on SAP changes | 593 | 10
UC-4.04 | AI Use Cases | Phase 4 | Reusable agent templates | Foundry | Templates for agent, RAG, tool and evaluation | 159 | 8
UC-4.05 | AI Use Cases | Phase 4 | Adoption tracking and change management | Factory | Change network across many plants | 240 | 7
UC-4.06 | AI Use Cases | Phase 4 | Retire or refresh low-value agents | Factory | Quarterly portfolio review | 51 | 4
PM-1.01 | Program Management | Phase 1 | Program management, planning, status and steering (added) | All teams | Program across 3 teams, many plants and vendors | 414 | 5
PM-2.01 | Program Management | Phase 2 | Program management, planning, status and steering (added) | All teams | Program across 3 teams, many plants and vendors | 414 | 5
PM-3.01 | Program Management | Phase 3 | Program management, planning, status and steering (added) | All teams | Program across 3 teams, many plants and vendors | 414 | 5
PM-4.01 | Program Management | Phase 4 | Program management, planning, status and steering (added) | All teams | Program across 3 teams, many plants and vendors | 414 | 5
PS-3.07 | AI Platform Setup | Phase 3 | Platform security assessment and penetration test (added) | Platform Engineering | Not on the slides; added for a complete delivery plan | 145 | 4
PS-4.07 | AI Platform Setup | Phase 4 | Run handover: SRE, ServiceNow and support model (added) | Platform Engineering | Not on the slides; added for a complete delivery plan | 120 | 4
PS-3.08 | AI Platform Setup | Phase 3 | Developer enablement and Foundry training (added) | Foundry | Not on the slides; added for a complete delivery plan | 96 | 4
UC-2.07 | AI Use Cases | Phase 2 | Hypercare and production support for live agents (added) | Factory | Not on the slides; added for a complete delivery plan (support grows as more agents go live) | 145 | 3
UC-3.07 | AI Use Cases | Phase 3 | Hypercare and production support for live agents (added) | Factory | Not on the slides; added for a complete delivery plan (support grows as more agents go live) | 218 | 3
UC-4.07 | AI Use Cases | Phase 4 | Hypercare and production support for live agents (added) | Factory | Not on the slides; added for a complete delivery plan (support grows as more agents go live) | 294 | 3
|  |  | Total |  |  | 24000 | 677

## Scope & Assumptions
Scope and assumptions behind the 24,000-hour estimate
Scope driver | Assumption used for sizing
Target total | 24,000 hours across all phases, teams and roles
Environments | 3: dev, test, production
Azure regions | 2: primary and DR / secondary
Plants | 2 pilot plants (Phase 2), 5 plants live by end of Phase 3, 15 more plants onboarded in Phase 4
Enterprise systems integrated | 6: SAP S/4HANA, FactoryTalk MES, AVEVA PI, SharePoint, Coupa, Azure SQL
Agents built | 7: Analyst, Spec, Maintenance, Quality, Supply, Planner, Sustainability
Model providers | 4: Azure OpenAI, Anthropic, Google Gemini, self-hosted open models
Applications | Teams / Copilot app, Plant Ops web app, mobile app, admin panel, partner APIs
Controls | SOX / ITGC controls on SAP write-back; OT security review for plant connectivity; Responsible-AI review per agent
Delivery standard | Every slide item gets design review, dev-test-prod promotion, documentation and defect-fix effort
Out of scope | Plant SMEs' time, SAP / MES / PI application owners, vendor licences, Azure consumption, hardware at plants
Method | Bottom-up: every slide item broken into implementation tasks, each sized by role for the scope above, plus design review, dev-test-prod promotion, documentation and defect fixing on every item

## Resources
Resource roles and planning basis
Working hours per person-week | 40 | Input: used only to convert hours to person-weeks.
Code | Role | Main team
PM | Program / Project Manager | All teams
CA | Cloud / Platform Architect | Platform Engineering
DO | Platform / DevOps Engineer | Platform Engineering
SE | Security Engineer | Platform Engineering
AIA | AI Architect | Foundry
AIE | AI / ML Engineer | Foundry
DE | Data Engineer | AI Data Lake
DG | Data Architect / Governance | AI Data Lake
DEV | Full-stack Developer | Factory
BA | Business Analyst / Product Owner | Factory
QA | QA / Test Engineer | All teams
CM | Change & Training Lead | Factory
Notes
Activities come from the deck's three track slides; each is broken into implementation tasks on the Task Breakdown sheet.
Owner teams: Platform Engineering, Foundry, AI Data Lake (Data Engineers and Data Architect / Governance), Factory. Data readiness items led by data engineering or governance belong to AI Data Lake. Program management rows (one per phase) are not on the slides.
Hours are an enterprise-wide planning estimate of 24,000 hours for the scope on the Scope & Assumptions sheet. Validate with each team lead before committing.
Hours exclude plant SMEs, SAP / MES / AVEVA PI application owners, licences and Azure consumption.
Testing effort sits inside each activity (QA tasks) rather than a separate test phase.