## Slide 1
Ball Corp — Enterprise Agentic AI Program
Estimate: Agentic AI framework · IDE integrations (SAP, JDE, Databricks) · ERP knowledge base · Agentic workflows
Delivery model: 5 resources — 4 offshore ($40/hr) + 1 onsite ($150/hr) · blended $62/hr
Landscape: SAP · JDE · Databricks Lakehouse · FactoryTalk · Azure (AKS, APIM/Kong, AI Foundry)

## Slide 2
Executive summary
Two scope views, one team of 5 (4 offshore + 1 onsite)
Lean — Phase 1
$285k–384k
4,600–6,200 hrs · 6–8 months
Gateway + MCP platform, IDE pilots, 5 KB modules, 4 read-only workflows; platform/security layers owned by Ball Corp teams
PROGRAM ENVELOPE
Full — entire org
$508k–735k
8,200–11,850 hrs · 10–14 months
All 14 ERP modules, 10 production workflows, org-wide IDE rollout; WS1 fixed at 1,500 hrs, WS4 at 2,000 hrs
Recommended funding ask (full-scope midpoint): $620k · 10,000 hrs · 12 months · 5 resources
Release the lean tranche ($285k–384k) as the Phase-1 commitment; remainder gated by a 2–3 week Discovery producing the story-level backlog.
Baseline split: offshore ~8,000 hrs ≈ $320k · onsite ~2,000 hrs ≈ $300k

## Slide 3
Commercial & delivery model
4 offshore @ $40/hr + 1 onsite @ $150/hr
Blended rate
$62/hr
Capacity
200 hrs/wk
Offshore share
80% hrs
Onsite share
48% cost
Role split
Resource | Rate | Owns
Onsite lead / architect (1) | $150 | Architecture & decision gates (gateway, MCP ADRs), stakeholder & SME workshops, security reviews, UAT interface — the SME/US-hours bridge
Offshore engineers (4) | $40 | MCP server builds, AKS/CI-CD infrastructure, KB curation pipelines, workflow development, IDE tooling & extensions
Working rhythm risk: KB module curation and workflow UAT need Ball Corp SMEs in US hours. The onsite lead batches context handoffs to offshore daily; without this, $40/hr hours stall waiting on inputs. Full scope at a fixed 5 FTE runs ~10–14 months; each added offshore engineer (+$40/hr) buys back calendar if a shorter cap matters.

## Slide 4
Workstream roll-up
Hours and cost at $62/hr blended — lean / full
Workstream | Lean hrs | Full hrs | Lean $ | Full $
WS1 — Agentic AI framework & MCP platform (gateway, 6 MCP servers, AKS, security) | 950–1,250 | 1,500 | $59k–78k | $93k
WS2 — IDE integrations: SAP ABAP/BTP, JDE Orchestrator, Databricks + metadata grounding | 900–1,400 | 1,400–2,600 | $56k–87k | $87k–161k
WS3 — ERP knowledge base (5 modules lean / 14 modules full: 10 SAP + 4 JDE) | 1,100–1,700 | 2,400–4,200 | $68k–105k | $149k–260k
WS4 — Agentic workflows (4 read-only lean / 10 production full) | 800–1,300 | 2,000 | $50k–81k | $124k
Program overhead — PM, architecture governance, change mgmt (12–15%) | 450–650 | 900–1,550 | $28k–40k | $56k–96k
TOTAL | 4,600–6,200 | 8,200–11,850 | $285k–384k | $508k–735k
Lean assumes platform/security layers owned by Ball Corp teams and no contingency; full is program-owned with 10–15% contingency. WS1 MCP metadata servers are reused by WS2 — that synergy is already netted out.

## Slide 5
WS1 — Agentic AI framework & MCP platform
1,500 hrs full ($93k @ $62/hr) · 950–1,250 lean
Component | Hours
AI Gateway — Path A managed (APIM / Kong Konnect) or Path B self-hosted Kong OSS; incl. week-1–2 gateway/control-plane decision matrix (Galileo as eval/guardrail candidate) | 140
MCP application layer: base server template, 6 target servers (SAP, JDE, Databricks, FactoryTalk +2) @ 1 wk each, per-server testing/docs, agent tool-call integration, evaluation & UAT | 480
Infrastructure layer: AKS provisioning (4–5 wks), ingress/egress, traffic routing & telemetry, NSG/firewall, CI/CD + IaC, multi-environment promotion | 400
Security & enablement: Entra ID auth on MCP endpoints, target-system enablement (SAP CDS/OData, JDE AIS, Databricks SP/Unity Catalog, FactoryTalk), hardening | 160
Agent orchestration standard: AI Foundry/LangGraph patterns, agent templates, tool registry, memory/state, HITL checkpoints for SAP writes | 200
Evaluation & observability: platform decision + build (Galileo integration vs. native Foundry/MLflow) | 120
Lean = Path A gateway + B/C layers transferred to Ball Corp platform & security teams with named owners.

## Slide 6
MCP complete list — A. Application layer
Subtotal: 448–536 hrs · 11.2–13.4 wks · $28k–33k @ $62/hr
# | Work item | Duration | Hours
A1 | Core base MCP server: Dockerfile, env-variable/config ingestion, schema setup, reusable template | 1 wk | 40
A2 | 6 custom MCP target servers (SAP, JDE, Databricks, FactoryTalk + 2) @ 1 wk each | 6 wks | 240
A3 | Per-server integration testing + docs: test cases vs. real systems, tool manifests, publishing (8–16 h/server) | 1.2–2.4 wks | 48–96
A4 | AI agent integration: MCP tool-call mapping, LLM function-calling, execution graphs | 2 wks | 80
A5 | Agent evaluation & UAT: tool-selection accuracy, loop/hallucination guards, business validation | 1–2 wks | 40–80
Watch item — FactoryTalk: 1 week holds only if an IT-side historian/broker already exposes plant data. Direct OT/plant-network integration crosses the IT/OT boundary and is a separate project with its own security review.

## Slide 7
MCP list — B. Infrastructure · C. Security
B: 360–480 hrs ($22k–30k) · C: 104–248 hrs ($6k–15k) @ $62/hr
# | Work item | Duration | Hours
B1 | AKS cluster deployment & provisioning | 4–5 wks | 160–200
B2 | Ingress & egress routing configuration | 1 wk | 40
B3 | Traffic routing & live telemetry (probes, Prometheus / Managed Grafana) | 1 wk | 40
B4 | Network rules & firewall settings (NSGs, Azure Firewall egress, private endpoints) | 1 wk | 40
B5 | CI/CD + registry + IaC: ACR, pipelines, Bicep/Terraform for AKS workloads | 1–2 wks | 40–80
B6 | Multi-environment promotion: dev → test → prod config, secrets, network per env | 1–2 wks | 40–80
C1 | Auth on MCP endpoints: Entra ID OAuth inbound; workload identity + Key Vault outbound | 1–2 wks | 40–80
C2 | Target-system enablement: SAP service user + CDS/OData, JDE AIS/Orchestrator, Databricks SP + Unity Catalog grants, FactoryTalk connectivity (+ approval calendar wait) | 1–3 wks | 40–120
C3 | Security review support & hardening: image scanning, pod security, egress lockdown, pen-test remediation | 0.6–1.2 wks | 24–48
Strike-with-owner options: B5/B6 → platform team · C1/C3 → security engineering · C2 → SAP Basis / JDE CNC / Databricks admins. Striking all returns the MCP package to ~640–680 hrs — with ownership made explicit.

## Slide 8
WS2 — IDE integrations (SAP · JDE · Databricks)
1,400–2,600 hrs full · 900–1,400 lean (pilot cohorts)
Component | Hours
Developer AI standard: evaluate/deploy assistant layer (Copilot / Claude Code / Databricks Assistant / SAP Joule–Build Code), licensing, security review, org policy | 160–280
SAP: ABAP/BTP tooling (VS Code / Eclipse ADT), metadata MCP server (tables, CDS views, BAPIs, transports) grounding the IDE agent; OData/CDS scaffolding + test generation | 400–760
JDE: Orchestrator Studio patterns, AIS REST scaffolding, MCP server exposing JDE object/UDO metadata and orchestration inventory | 280–520
Databricks: VS Code extension + Assistant rollout, Unity Catalog schema/lineage grounding so generated code targets correct Gold tables; notebook/DLT/dbt templates | 240–420
Org rollout: pilot cohorts, secure config (no code exfiltration), prompt/usage guidelines, training for 3 developer communities | 320–620
Lean = one pilot cohort per stack, org-wide training deferred. Metadata MCP servers built in WS1 are reused here.

## Slide 9
WS3 — ERP knowledge base (all modules)
2,400–4,200 hrs full (14 modules) · 1,100–1,700 lean (5 modules)
Component | Hours
KB platform foundation: ingestion pipelines (SOPs, functional specs, config docs), chunking/embedding into Databricks Vector Search, refresh automation, module-level access control | 300–480
Semantic layer: YAML manifests / metric definitions on Gold tables per module for correct text-to-SQL interpretation | 280–520
Per-module curation: SME document collection, glossary + synonyms (SAP T-codes, JDE object names), table/CDS dictionary enrichment, Q&A eval sets — 120–220 h × 14 modules (10 SAP: FI, CO, MM, SD, PP, QM, PM, EWM, IBP, MDG + 4 JDE domains) | 1,680–3,080
Quality gates: per-module retrieval accuracy testing and functional-owner sign-off | 140–220
Binding constraint is SME availability, not engineering: each module needs 2–4 hrs/week from a Ball Corp functional expert during its curation window — in US hours, brokered by the onsite lead. Lean Phase-1 set: FI, MM, SD, IBP + one JDE domain.

## Slide 10
WS4 — Agentic workflows
2,000 hrs full ($124k @ $62/hr, 10 workflows) · 800–1,300 lean (4 read-only)
Component | Hours
Workflow discovery & prioritization with business owners; value/feasibility scoring | 150
Build per workflow (~165 h avg × 10): agent design, tool wiring, prompts, HITL approval steps, evaluation, UAT — candidates: supply-chain risk, IBP demand vs. actuals, MDM duplicate stewardship, AP invoice exceptions, order-to-cash exceptions, FactoryTalk anomaly triage, procurement recommendations | 1,650
Production hardening: monitoring, fallback paths, incident runbooks per workflow | 200
Lean = 4 read-only workflows: deferring SAP write-back defers the heaviest security reviews. At 165 h average per workflow, the mix must stay balanced — write-back workflows run 220–280 h each, so heavy write-back scope displaces simpler workflows within the 2,000-hr cap.
Program overhead across all workstreams (PM, architecture governance, change management, steering): 12–15% → 900–1,550 hrs full / 450–650 lean.

## Slide 11
Sequencing — 12-month baseline
Discovery-gated; lean tranche first, full scope after gate
Months 1–2
Discovery + foundations: gateway/control-plane decision matrix, MCP ADRs (AKS confirmed), landing zone, base MCP template, Phase-0 data-readiness verification
→
Months 2–5
6 MCP servers + agent integration; KB foundation + first 2 modules; IDE pilot cohort per stack
→
Months 5–8
First 4 read-only workflows to production; KB modules 3–5; IDE rollout begins; Phase-1 gate review
→
Months 8–12+
Full scope: KB modules 6–14, workflows 5–10 (incl. write-back with HITL + security reviews), org-wide IDE training
Go/no-go gates: end of Discovery (backlog + firm Phase-1 estimate), first MCP server + agent pair live (~month 3), Phase-1 review (~month 8) releasing the full-scope tranche.

## Slide 12
Assumptions, risks & decision gates
What the numbers depend on
Assumptions
Phase-0 data readiness (10-wk Gold-layer plan) complete — else add 400–800 hrs
1 wk/MCP server holds for documented APIs on the shared template
FactoryTalk reached via IT-side broker, not direct OT integration
AKS landing zone + approvals timely; lean view assumes named Ball Corp owners for B/C layers
SMEs available 2–4 hrs/wk per module in US hours
Risks & gates
Cross-team approvals (security, network, SAP Basis) burn calendar, not hours — escalate at >2 days/wk waiting
SAP write-back workflows each need HITL design + production security review
Offshore stall risk if SME context isn't batched through the onsite lead
Fixed 5 FTE puts full-scope upper bound at ~14 months; add offshore engineers to hold 12
Gateway & eval-platform decisions (APIM/Kong · Galileo vs. native) are week-1–2 gates
ROM estimate (±30–50%) → converts to budgetary (±20–30%) after the 2–3 week Discovery produces the story-level backlog.

## Slide 13
The ask
$620k · 10,000 hrs · 12 months · 5 resources
Phase-1 commitment: $285k–384k (lean tranche) — gateway + MCP platform, IDE pilots, 5 KB modules, 4 workflows.
Full-scope release: gated by Discovery backlog and the month-3 first server/agent pair — all 14 ERP modules, 10 workflows, org-wide IDE rollout.
Team: 4 offshore @ $40/hr + 1 onsite @ $150/hr · blended $62/hr · ~200 hrs/week capacity