## Slide 1
Azure AI Gateway & MCP Server Program
Effort estimate for a single dedicated Data/Cloud Engineer
Scope: AI Gateway setup • Operationalization • 6 MCP servers • 6 agent onboardings
All-Azure deployment — APIM GenAI Gateway, Azure AI Foundry, Azure Container Apps

## Slide 2
Executive summary
Three planning scenarios — total effort for one engineer, end to end
Optimistic
22 weeks
880 hrs
Simple connectors, clean APIs, no legacy systems
RECOMMENDED
Realistic
32–36 weeks
1,180–1,240 hrs
Mixed connector complexity, normal enterprise friction
Pessimistic
49 weeks
1,760 hrs
Legacy integrations, strict security review cycles
Selected planning baseline (calculator scenario)
Total hours
1,500
Duration
50 wks
Calendar
~11.5 mo
1500 Hrs*($)
Est. cost
Realistic band assumes a mixed portfolio — 2 simple, 3 standard, 1 complex MCP server — plus ~15% contingency for enterprise approval cycles.

## Slide 3
Planning baseline — selected scenario
Mixed portfolio (2 simple / 3 standard / 1 complex), 15% contingency, 36 productive hrs/week, $120/hr blended rate
Total hours
1500
Duration
50 wks
Calendar
~11.0 mo
Est. cost
$ .?
How this rolls up: gateway 160 h + operationalization 60 h + MCP servers 800 h (incl. 80 h platform foundation) + agent onboarding 300 h = 1,350 h base; 15% contingency adds ~232 h.
Sits at the upper-realistic end of the range because it prices in enterprise friction (approvals, reviews) rather than assuming a clean path. First server/agent pair live ≈ week 13 — the go/no-go checkpoint.

## Slide 4
Task 1 — Azure AI Gateway & agent setup
3–5 weeks / 120–200 hours
Work item | Hours
APIM provisioning (Premium/StandardV2), VNet integration, private endpoints | 24–40
GenAI gateway policies: per-consumer token rate limits, token metrics, semantic caching | 32–48
Backend pools: load balancing + circuit breakers across AOAI, cross-region failover | 24–40
Azure AI Foundry hub/project provisioning, model deployments, quota requests | 16–32
Entra ID managed identity wiring (APIM ↔ Azure OpenAI ↔ Foundry) | 16–24
Validation: policy load testing, failover drills | 8–16
Watch-out: Azure OpenAI quota/PTU approvals and firewall change requests commonly add 1–2 weeks of calendar wait — start them in week 1.

## Slide 5
Task 2 — Operationalization & guidance
1–2 weeks / 40–80 hours
Observability foundation
8–16 hrs
Azure Monitor + Log Analytics workspace; diagnostic settings on APIM, ACA, and Azure OpenAI
LLM metric workbooks
12–24 hrs
Prompt/completion tokens per app, latency P50/P95, MCP tool-call success rate
Alerting
4–8 hrs
Action groups for 429 spikes, error rates, and cost anomalies
Governance pack
16–32 hrs
Entra ID patterns, RBAC model, key rotation, onboarding runbook for consumer apps
Deliverables: live dashboards and alerts, plus a security-reviewed governance runbook that lets new consumer applications onboard without engineering hand-holding.

## Slide 6
Task 3 — Design, build & publish 6 MCP servers
13–24 weeks / 520–960 hours (largest workstream)
Simple tier
2–3 wks
80–120 hrs each
Azure SQL, Cosmos DB, Blob Storage
Standard tier
3.5–4.5 wks
140–180 hrs each
Dynamics 365, ServiceNow, SAP on Azure
Complex tier
5–7 wks
200–280 hrs each
Legacy systems: state mgmt, pooling, payload mapping
One-time platform foundation (60–100 hrs): ACA environment, container registry, IaC templates, CI/CD pipeline, reusable MCP server template (Python/TypeScript SDK) fronted by APIM with Entra ID auth.
Host on Azure Container Apps, not Functions: SSE/Streamable HTTP needs persistent connections; scale-to-zero cold starts break sessions. Each server carries ~10–15% for docs and APIM developer-portal publishing.

## Slide 7
Task 4 — Onboard 6 AI agents to MCP servers
5–12 weeks / 200–480 hours
Work item (per agent) | Hrs each | 6 agents
Register MCP endpoints as tools in AI Foundry / Semantic Kernel; auth wiring | 8–16 | 48–96
System prompt engineering + function-calling tuning (tool descriptions, schemas) | 12–32 | 72–192
Azure AI Evaluation SDK: groundedness, tool-call accuracy, loop/hallucination guards | 8–24 | 48–144
End-to-end integration testing and UAT support | 4–8 | 24–48
Least predictable line item: prompt tuning. Agents that call 3+ tools reliably typically need 2–3 evaluate-and-refine cycles before tool selection is dependable.

## Slide 8
Key assumptions & risks
What the estimate depends on — and what moves it
Assumptions
Senior engineer: hands-on with APIM policies, containers, IaC, and an MCP SDK
Azure subscriptions, networking, and landing-zone prerequisites already exist
Target-system API access, credentials, and docs provided promptly
Single resource — no parallelization; MCP servers are built sequentially
Risk multipliers
Cross-team dependencies: security review, firewall rules, service-principal approvals — add 10–20%
Undocumented legacy APIs can push a "standard" server into the complex tier
Scope creep on agent behaviors after first demos
Zero parallelization means calendar time stays long even when each server is modest
Mitigation: treat the first server/agent pair (≈ week 13) as a go/no-go gate and re-baseline before committing dates.